## Planilha1
Causes | Cluster | Paper ID | Reference
In project management, time pressure arises when overly ambitious timelines push teams to complete vital tasks hastily, compromising quality checks and coordination. | Time & Planning | 0 | LOVE P.E.D.; MATTHEWS J.; IKA L.A. (2024). Rework in relational engineer-to-order production systems: An ‘error-as-process’ archetype. Int J Prod Econ. Vol. 274. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.ijpe.2024.109310
In project management, time pressure arises when overly ambitious timelines push teams to complete vital tasks hastily, compromising quality checks and coordination. | Human Resources | 0 | LOVE P.E.D.; MATTHEWS J.; IKA L.A. (2024). Rework in relational engineer-to-order production systems: An ‘error-as-process’ archetype. Int J Prod Econ. Vol. 274. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.ijpe.2024.109310
In project management, time pressure arises when overly ambitious timelines push teams to complete vital tasks hastily, compromising quality checks and coordination. | Management and Supervision | 0 | LOVE P.E.D.; MATTHEWS J.; IKA L.A. (2024). Rework in relational engineer-to-order production systems: An ‘error-as-process’ archetype. Int J Prod Econ. Vol. 274. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.ijpe.2024.109310
In project management, time pressure arises when overly ambitious timelines push teams to complete vital tasks hastily, compromising quality checks and coordination. | Human Resources | 0 | LOVE P.E.D.; MATTHEWS J.; IKA L.A. (2024). Rework in relational engineer-to-order production systems: An ‘error-as-process’ archetype. Int J Prod Econ. Vol. 274. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.ijpe.2024.109310
In project management, time pressure arises when overly ambitious timelines push teams to complete vital tasks hastily, compromising quality checks and coordination. | Safety Culture | 0 | LOVE P.E.D.; MATTHEWS J.; IKA L.A. (2024). Rework in relational engineer-to-order production systems: An ‘error-as-process’ archetype. Int J Prod Econ. Vol. 274. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.ijpe.2024.109310
In project management, time pressure arises when overly ambitious timelines push teams to complete vital tasks hastily, compromising quality checks and coordination. | Communication | 0 | LOVE P.E.D.; MATTHEWS J.; IKA L.A. (2024). Rework in relational engineer-to-order production systems: An ‘error-as-process’ archetype. Int J Prod Econ. Vol. 274. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.ijpe.2024.109310
In project management, time pressure arises when overly ambitious timelines push teams to complete vital tasks hastily, compromising quality checks and coordination. | Design | 0 | LOVE P.E.D.; MATTHEWS J.; IKA L.A. (2024). Rework in relational engineer-to-order production systems: An ‘error-as-process’ archetype. Int J Prod Econ. Vol. 274. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.ijpe.2024.109310
In project management, time pressure arises when overly ambitious timelines push teams to complete vital tasks hastily, compromising quality checks and coordination. | Design | 2 | ASADI R.; WILKINSON S.; ROTIMI J.O.B. (2023). The common causes of rework in construction contracts: a diagnostic approach. J. Eng. Des. Technol.. Vol. 21. Iss. 4. doi: https://doi.org/10.1108/JEDT-04-2021-0215
In project management, time pressure arises when overly ambitious timelines push teams to complete vital tasks hastily, compromising quality checks and coordination. | Design | 2 | ASADI R.; WILKINSON S.; ROTIMI J.O.B. (2023). The common causes of rework in construction contracts: a diagnostic approach. J. Eng. Des. Technol.. Vol. 21. Iss. 4. doi: https://doi.org/10.1108/JEDT-04-2021-0215
In project management, time pressure arises when overly ambitious timelines push teams to complete vital tasks hastily, compromising quality checks and coordination. | Documentation & Information Management | 2 | ASADI R.; WILKINSON S.; ROTIMI J.O.B. (2023). The common causes of rework in construction contracts: a diagnostic approach. J. Eng. Des. Technol.. Vol. 21. Iss. 4. doi: https://doi.org/10.1108/JEDT-04-2021-0215
The presence of contradictory or missing information in project data. | Documentation & Information Management | 2 | ASADI R.; WILKINSON S.; ROTIMI J.O.B. (2023). The common causes of rework in construction contracts: a diagnostic approach. J. Eng. Des. Technol.. Vol. 21. Iss. 4. doi: https://doi.org/10.1108/JEDT-04-2021-0215
Frequent alterations to design or construction plans. | Design | 2 | ASADI R.; WILKINSON S.; ROTIMI J.O.B. (2023). The common causes of rework in construction contracts: a diagnostic approach. J. Eng. Des. Technol.. Vol. 21. Iss. 4. doi: https://doi.org/10.1108/JEDT-04-2021-0215
Inadequate expertise among personnel that increases the likelihood of errors. | Human Resources | 2 | ASADI R.; WILKINSON S.; ROTIMI J.O.B. (2023). The common causes of rework in construction contracts: a diagnostic approach. J. Eng. Des. Technol.. Vol. 21. Iss. 4. doi: https://doi.org/10.1108/JEDT-04-2021-0215
Insufficient supervisory oversight during project execution. | Management and Supervision | 2 | ASADI R.; WILKINSON S.; ROTIMI J.O.B. (2023). The common causes of rework in construction contracts: a diagnostic approach. J. Eng. Des. Technol.. Vol. 21. Iss. 4. doi: https://doi.org/10.1108/JEDT-04-2021-0215
Project teams often face time pressure due to tight and unrealistic deadlines, which leads to rushing through important processes with little room for error handling or quality control. | Time & Planning | 2 | ASADI R.; WILKINSON S.; ROTIMI J.O.B. (2023). The common causes of rework in construction contracts: a diagnostic approach. J. Eng. Des. Technol.. Vol. 21. Iss. 4. doi: https://doi.org/10.1108/JEDT-04-2021-0215
Deficient project planning leading to overloading and mismanagement. | Time & Planning | 2 | ASADI R.; WILKINSON S.; ROTIMI J.O.B. (2023). The common causes of rework in construction contracts: a diagnostic approach. J. Eng. Des. Technol.. Vol. 21. Iss. 4. doi: https://doi.org/10.1108/JEDT-04-2021-0215
Poor management and control over project documentation. | Documentation & Information Management | 2 | ASADI R.; WILKINSON S.; ROTIMI J.O.B. (2023). The common causes of rework in construction contracts: a diagnostic approach. J. Eng. Des. Technol.. Vol. 21. Iss. 4. doi: https://doi.org/10.1108/JEDT-04-2021-0215
Flawed procurement processes and contract management that lead to execution issues. | Contractor Selection & Performance | 2 | ASADI R.; WILKINSON S.; ROTIMI J.O.B. (2023). The common causes of rework in construction contracts: a diagnostic approach. J. Eng. Des. Technol.. Vol. 21. Iss. 4. doi: https://doi.org/10.1108/JEDT-04-2021-0215
Ineffective overall management and on-site practices. | Management and Supervision | 2 | ASADI R.; WILKINSON S.; ROTIMI J.O.B. (2023). The common causes of rework in construction contracts: a diagnostic approach. J. Eng. Des. Technol.. Vol. 21. Iss. 4. doi: https://doi.org/10.1108/JEDT-04-2021-0215
Workforce lacking adequate skills for the tasks required. | Human Resources | 2 | ASADI R.; WILKINSON S.; ROTIMI J.O.B. (2023). The common causes of rework in construction contracts: a diagnostic approach. J. Eng. Des. Technol.. Vol. 21. Iss. 4. doi: https://doi.org/10.1108/JEDT-04-2021-0215
Not enough personnel available to meet project demands. | Human Resources | 2 | ASADI R.; WILKINSON S.; ROTIMI J.O.B. (2023). The common causes of rework in construction contracts: a diagnostic approach. J. Eng. Des. Technol.. Vol. 21. Iss. 4. doi: https://doi.org/10.1108/JEDT-04-2021-0215
Choosing contractors/subcontractors who are ill-suited for the work. | Contractor Selection & Performance | 2 | ASADI R.; WILKINSON S.; ROTIMI J.O.B. (2023). The common causes of rework in construction contracts: a diagnostic approach. J. Eng. Des. Technol.. Vol. 21. Iss. 4. doi: https://doi.org/10.1108/JEDT-04-2021-0215
Designs that are not practical or feasible to construct. | Design | 2 | ASADI R.; WILKINSON S.; ROTIMI J.O.B. (2023). The common causes of rework in construction contracts: a diagnostic approach. J. Eng. Des. Technol.. Vol. 21. Iss. 4. doi: https://doi.org/10.1108/JEDT-04-2021-0215
Use of materials that fail to meet the required specifications. | Material Resources | 2 | ASADI R.; WILKINSON S.; ROTIMI J.O.B. (2023). The common causes of rework in construction contracts: a diagnostic approach. J. Eng. Des. Technol.. Vol. 21. Iss. 4. doi: https://doi.org/10.1108/JEDT-04-2021-0215
Inadequate technical or practical knowledge among project staff. | Human Resources | 2 | ASADI R.; WILKINSON S.; ROTIMI J.O.B. (2023). The common causes of rework in construction contracts: a diagnostic approach. J. Eng. Des. Technol.. Vol. 21. Iss. 4. doi: https://doi.org/10.1108/JEDT-04-2021-0215
Inefficient communication channels that lead to misunderstandings. | Communication | 2 | ASADI R.; WILKINSON S.; ROTIMI J.O.B. (2023). The common causes of rework in construction contracts: a diagnostic approach. J. Eng. Des. Technol.. Vol. 21. Iss. 4. doi: https://doi.org/10.1108/JEDT-04-2021-0215
Use of substandard materials or errors arising from prefabrication processes. | Material Resources | 2 | ASADI R.; WILKINSON S.; ROTIMI J.O.B. (2023). The common causes of rework in construction contracts: a diagnostic approach. J. Eng. Des. Technol.. Vol. 21. Iss. 4. doi: https://doi.org/10.1108/JEDT-04-2021-0215
Poor craftsmanship and negative attitudes that affect work quality. | Human Resources | 2 | ASADI R.; WILKINSON S.; ROTIMI J.O.B. (2023). The common causes of rework in construction contracts: a diagnostic approach. J. Eng. Des. Technol.. Vol. 21. Iss. 4. doi: https://doi.org/10.1108/JEDT-04-2021-0215
Errors in design arising from factors such as unqualified designers, tight design/review schedules, lack of coordination, improper planning, unclear scope, and re‑using previous designs. | Design | 5 | MAHAMID I. (2024). Rework investigation in residential building projects: Cost, factors and effects. Int. Rev. Appl. Sci. Eng.. Vol. 15. Iss. 1. doi: https://doi.org/10.1556/1848.2023.00694
Inadequate skills among laborers, which leads to mistakes in work execution resulting in damaged work that must be redone. | Human Resources | 5 | MAHAMID I. (2024). Rework investigation in residential building projects: Cost, factors and effects. Int. Rev. Appl. Sci. Eng.. Vol. 15. Iss. 1. doi: https://doi.org/10.1556/1848.2023.00694
Contractors or subcontractors selected primarily on the basis of low bid prices who lack the necessary resources, qualifications, or experienced staff to perform the work properly. | Contractor Selection & Performance | 5 | MAHAMID I. (2024). Rework investigation in residential building projects: Cost, factors and effects. Int. Rev. Appl. Sci. Eng.. Vol. 15. Iss. 1. doi: https://doi.org/10.1556/1848.2023.00694
Failure to meet the required design and quality standards, often due to the use of substandard materials or improper workmanship aimed at reducing cost. | Design | 5 | MAHAMID I. (2024). Rework investigation in residential building projects: Cost, factors and effects. Int. Rev. Appl. Sci. Eng.. Vol. 15. Iss. 1. doi: https://doi.org/10.1556/1848.2023.00694
The common practice of awarding contracts to the lowest bidder without adequate evaluation of qualifications, leading to the selection of underqualified firms. | Contractor Selection & Performance | 5 | MAHAMID I. (2024). Rework investigation in residential building projects: Cost, factors and effects. Int. Rev. Appl. Sci. Eng.. Vol. 15. Iss. 1. doi: https://doi.org/10.1556/1848.2023.00694
A deficiency in workers’ expertise caused by labor shortages, substandard licensing, and inadequate training. | Human Resources | 6 | LAMBERS R.; LAMARI F.; SKITMORE M.; RAJENDRA D. (2024). Key residential construction defects: a framework for their identification and correlated causes. Constr. Innov.. Vol. 24. Iss. 6. doi: https://doi.org/10.1108/CI-05-2022-0103
The use of substandard or incorrect materials (often to reduce cost) that do not meet quality requirements. | Material Resources | 6 | LAMBERS R.; LAMARI F.; SKITMORE M.; RAJENDRA D. (2024). Key residential construction defects: a framework for their identification and correlated causes. Constr. Innov.. Vol. 24. Iss. 6. doi: https://doi.org/10.1108/CI-05-2022-0103
Inadequate or ineffective supervisory practices that fail to monitor and rectify defects. | Management and Supervision | 6 | LAMBERS R.; LAMARI F.; SKITMORE M.; RAJENDRA D. (2024). Key residential construction defects: a framework for their identification and correlated causes. Constr. Innov.. Vol. 24. Iss. 6. doi: https://doi.org/10.1108/CI-05-2022-0103
Insufficient training provided to workers, resulting in inadequate skills and knowledge for proper task execution. | Human Resources | 6 | LAMBERS R.; LAMARI F.; SKITMORE M.; RAJENDRA D. (2024). Key residential construction defects: a framework for their identification and correlated causes. Constr. Innov.. Vol. 24. Iss. 6. doi: https://doi.org/10.1108/CI-05-2022-0103
A lack of emphasis on quality by management—often due to financial pressures or competing priorities. | Management and Supervision | 6 | LAMBERS R.; LAMARI F.; SKITMORE M.; RAJENDRA D. (2024). Key residential construction defects: a framework for their identification and correlated causes. Constr. Innov.. Vol. 24. Iss. 6. doi: https://doi.org/10.1108/CI-05-2022-0103
When schedules are excessively aggressive in project management, they impose time pressure that forces rapid execution of tasks at the expense of accuracy and teamwork. | Time & Planning | 6 | LAMBERS R.; LAMARI F.; SKITMORE M.; RAJENDRA D. (2024). Key residential construction defects: a framework for their identification and correlated causes. Constr. Innov.. Vol. 24. Iss. 6. doi: https://doi.org/10.1108/CI-05-2022-0103
Time pressure in projects is caused by deadlines that leave no margin for error, prompting teams to bypass critical steps like quality assurance and coordination. | Time & Planning | 10 | YOUSRY AKAL A.; METWALLY EL-KHOLY A. (2024). Exploring the critical frequent factors of rework and assigning strategies to mitigate their occurrence in the Egyptian construction projects. J. King Saud Univ. Eng. Sci.. Vol. 36. Iss. 7. doi: https://doi.org/10.1016/j.jksues.2021.10.002
Reduction of the allocated budget after project commencement, pushing contractors to cut costs. | Financial Constraints | 10 | YOUSRY AKAL A.; METWALLY EL-KHOLY A. (2024). Exploring the critical frequent factors of rework and assigning strategies to mitigate their occurrence in the Egyptian construction projects. J. King Saud Univ. Eng. Sci.. Vol. 36. Iss. 7. doi: https://doi.org/10.1016/j.jksues.2021.10.002
Late release of payments by the owner, which disrupts contractors’ cash flow. | Financial Constraints | 10 | YOUSRY AKAL A.; METWALLY EL-KHOLY A. (2024). Exploring the critical frequent factors of rework and assigning strategies to mitigate their occurrence in the Egyptian construction projects. J. King Saud Univ. Eng. Sci.. Vol. 36. Iss. 7. doi: https://doi.org/10.1016/j.jksues.2021.10.002
Awarding contracts based solely on low price rather than technical capability, resulting in the selection of underqualified firms. | Contractor Selection & Performance | 10 | YOUSRY AKAL A.; METWALLY EL-KHOLY A. (2024). Exploring the critical frequent factors of rework and assigning strategies to mitigate their occurrence in the Egyptian construction projects. J. King Saud Univ. Eng. Sci.. Vol. 36. Iss. 7. doi: https://doi.org/10.1016/j.jksues.2021.10.002
Inadequate vocational education leads to a workforce that lacks essential technical skills. | Human Resources | 10 | YOUSRY AKAL A.; METWALLY EL-KHOLY A. (2024). Exploring the critical frequent factors of rework and assigning strategies to mitigate their occurrence in the Egyptian construction projects. J. King Saud Univ. Eng. Sci.. Vol. 36. Iss. 7. doi: https://doi.org/10.1016/j.jksues.2021.10.002
Insufficient internal training prevents improvement in workers’ and supervisors’ technical competencies. | Human Resources | 10 | YOUSRY AKAL A.; METWALLY EL-KHOLY A. (2024). Exploring the critical frequent factors of rework and assigning strategies to mitigate their occurrence in the Egyptian construction projects. J. King Saud Univ. Eng. Sci.. Vol. 36. Iss. 7. doi: https://doi.org/10.1016/j.jksues.2021.10.002
Errors and omissions in design documents caused by tight deadlines and frequent design iterations. | Design | 10 | YOUSRY AKAL A.; METWALLY EL-KHOLY A. (2024). Exploring the critical frequent factors of rework and assigning strategies to mitigate their occurrence in the Egyptian construction projects. J. King Saud Univ. Eng. Sci.. Vol. 36. Iss. 7. doi: https://doi.org/10.1016/j.jksues.2021.10.002
Modifications needed because the design information provided is incomplete or inaccurate. | Design | 10 | YOUSRY AKAL A.; METWALLY EL-KHOLY A. (2024). Exploring the critical frequent factors of rework and assigning strategies to mitigate their occurrence in the Egyptian construction projects. J. King Saud Univ. Eng. Sci.. Vol. 36. Iss. 7. doi: https://doi.org/10.1016/j.jksues.2021.10.002
Modifications arising from mistakes or omissions in the technical specifications of the project. | Design | 10 | YOUSRY AKAL A.; METWALLY EL-KHOLY A. (2024). Exploring the critical frequent factors of rework and assigning strategies to mitigate their occurrence in the Egyptian construction projects. J. King Saud Univ. Eng. Sci.. Vol. 36. Iss. 7. doi: https://doi.org/10.1016/j.jksues.2021.10.002
Substandard work quality caused by unqualified or poorly managed labor. | Human Resources | 10 | YOUSRY AKAL A.; METWALLY EL-KHOLY A. (2024). Exploring the critical frequent factors of rework and assigning strategies to mitigate their occurrence in the Egyptian construction projects. J. King Saud Univ. Eng. Sci.. Vol. 36. Iss. 7. doi: https://doi.org/10.1016/j.jksues.2021.10.002
Deliberate use of inferior materials to reduce costs, resulting in poor quality work that necessitates rework. | Material Resources | 10 | YOUSRY AKAL A.; METWALLY EL-KHOLY A. (2024). Exploring the critical frequent factors of rework and assigning strategies to mitigate their occurrence in the Egyptian construction projects. J. King Saud Univ. Eng. Sci.. Vol. 36. Iss. 7. doi: https://doi.org/10.1016/j.jksues.2021.10.002
Mandatory modifications forced by discrepancies between design assumptions and actual site conditions. | Design | 10 | YOUSRY AKAL A.; METWALLY EL-KHOLY A. (2024). Exploring the critical frequent factors of rework and assigning strategies to mitigate their occurrence in the Egyptian construction projects. J. King Saud Univ. Eng. Sci.. Vol. 36. Iss. 7. doi: https://doi.org/10.1016/j.jksues.2021.10.002
Inadequate communication and integration among design team members that results in design errors. (Inferred from survey ratings.) | Design | 11 | JULIANA A.; OLADIMEJI O.; ABIODUN A.O.; HADDAD A.N.; TAM V.W.Y. (2024). Influence of rework on construction project performance in Nigeria. Int. J. Constr. Manage.. Vol. 24. Iss. 8. doi: https://doi.org/10.1080/15623599.2023.2239439
Insufficient systems or procedures to ensure quality during construction, leading to defects and subsequent rework. | Management and Supervision | 11 | JULIANA A.; OLADIMEJI O.; ABIODUN A.O.; HADDAD A.N.; TAM V.W.Y. (2024). Influence of rework on construction project performance in Nigeria. Int. J. Constr. Manage.. Vol. 24. Iss. 8. doi: https://doi.org/10.1080/15623599.2023.2239439
Client-driven changes during construction that require rework to align with evolving expectations. | Client-Driven Influences | 11 | JULIANA A.; OLADIMEJI O.; ABIODUN A.O.; HADDAD A.N.; TAM V.W.Y. (2024). Influence of rework on construction project performance in Nigeria. Int. J. Constr. Manage.. Vol. 24. Iss. 8. doi: https://doi.org/10.1080/15623599.2023.2239439
Inadequate, ambiguous, or incomplete instructions given to on‑site workers resulting in errors. | Documentation & Information Management | 11 | JULIANA A.; OLADIMEJI O.; ABIODUN A.O.; HADDAD A.N.; TAM V.W.Y. (2024). Influence of rework on construction project performance in Nigeria. Int. J. Constr. Manage.. Vol. 24. Iss. 8. doi: https://doi.org/10.1080/15623599.2023.2239439
Inconsistencies and conflicts within the design team that lead to unclear design outputs. | Design | 11 | JULIANA A.; OLADIMEJI O.; ABIODUN A.O.; HADDAD A.N.; TAM V.W.Y. (2024). Influence of rework on construction project performance in Nigeria. Int. J. Constr. Manage.. Vol. 24. Iss. 8. doi: https://doi.org/10.1080/15623599.2023.2239439
Contractor-initiated changes (without proper approval) that deviate from the original design. | Contractor Selection & Performance | 11 | JULIANA A.; OLADIMEJI O.; ABIODUN A.O.; HADDAD A.N.; TAM V.W.Y. (2024). Influence of rework on construction project performance in Nigeria. Int. J. Constr. Manage.. Vol. 24. Iss. 8. doi: https://doi.org/10.1080/15623599.2023.2239439
Inadequate supervisory oversight due to unqualified or insufficiently trained supervisors. | Management and Supervision | 11 | JULIANA A.; OLADIMEJI O.; ABIODUN A.O.; HADDAD A.N.; TAM V.W.Y. (2024). Influence of rework on construction project performance in Nigeria. Int. J. Constr. Manage.. Vol. 24. Iss. 8. doi: https://doi.org/10.1080/15623599.2023.2239439
Failure to monitor or properly manage key construction activities, leading to errors. | Management and Supervision | 11 | JULIANA A.; OLADIMEJI O.; ABIODUN A.O.; HADDAD A.N.; TAM V.W.Y. (2024). Influence of rework on construction project performance in Nigeria. Int. J. Constr. Manage.. Vol. 24. Iss. 8. doi: https://doi.org/10.1080/15623599.2023.2239439
The selection and use of materials that do not meet quality standards, leading to rework for replacement or repair. | Material Resources | 11 | JULIANA A.; OLADIMEJI O.; ABIODUN A.O.; HADDAD A.N.; TAM V.W.Y. (2024). Influence of rework on construction project performance in Nigeria. Int. J. Constr. Manage.. Vol. 24. Iss. 8. doi: https://doi.org/10.1080/15623599.2023.2239439
Missing items or details in the contract documents that lead to gaps in project execution. | Documentation & Information Management | 11 | JULIANA A.; OLADIMEJI O.; ABIODUN A.O.; HADDAD A.N.; TAM V.W.Y. (2024). Influence of rework on construction project performance in Nigeria. Int. J. Constr. Manage.. Vol. 24. Iss. 8. doi: https://doi.org/10.1080/15623599.2023.2239439
Inadequate or superficial review processes that fail to catch defects early. | Design | 11 | JULIANA A.; OLADIMEJI O.; ABIODUN A.O.; HADDAD A.N.; TAM V.W.Y. (2024). Influence of rework on construction project performance in Nigeria. Int. J. Constr. Manage.. Vol. 24. Iss. 8. doi: https://doi.org/10.1080/15623599.2023.2239439
Mistakes in the contract documents that lead to misinterpretation and execution errors. | Documentation & Information Management | 11 | JULIANA A.; OLADIMEJI O.; ABIODUN A.O.; HADDAD A.N.; TAM V.W.Y. (2024). Influence of rework on construction project performance in Nigeria. Int. J. Constr. Manage.. Vol. 24. Iss. 8. doi: https://doi.org/10.1080/15623599.2023.2239439
Inadequate training and insufficient experience among workers and supervisors, resulting in errors. | Human Resources | 11 | JULIANA A.; OLADIMEJI O.; ABIODUN A.O.; HADDAD A.N.; TAM V.W.Y. (2024). Influence of rework on construction project performance in Nigeria. Int. J. Constr. Manage.. Vol. 24. Iss. 8. doi: https://doi.org/10.1080/15623599.2023.2239439
Not allocating enough time to prepare detailed and accurate contract documents. | Time & Planning | 11 | JULIANA A.; OLADIMEJI O.; ABIODUN A.O.; HADDAD A.N.; TAM V.W.Y. (2024). Influence of rework on construction project performance in Nigeria. Int. J. Constr. Manage.. Vol. 24. Iss. 8. doi: https://doi.org/10.1080/15623599.2023.2239439
Inadequate scheduling of tasks and workload distribution, causing overburdened teams and errors. | Time & Planning | 11 | JULIANA A.; OLADIMEJI O.; ABIODUN A.O.; HADDAD A.N.; TAM V.W.Y. (2024). Influence of rework on construction project performance in Nigeria. Int. J. Constr. Manage.. Vol. 24. Iss. 8. doi: https://doi.org/10.1080/15623599.2023.2239439
Issues with the practicality of the design, where designs are unfeasible or hard to construct. | Design | 11 | JULIANA A.; OLADIMEJI O.; ABIODUN A.O.; HADDAD A.N.; TAM V.W.Y. (2024). Influence of rework on construction project performance in Nigeria. Int. J. Constr. Manage.. Vol. 24. Iss. 8. doi: https://doi.org/10.1080/15623599.2023.2239439
Insufficient skills, knowledge, and expertise among site operatives, project managers, and supervisors, leading to errors and mismanagement that cause rework. | Human Resources | 12 | OLANREWAJU A. (2025). Application of structural equation modelling (SEM) to evaluate reworks in sustainable buildings. Front. Eng. Built. Environ.. Vol. UNKNOWN. Iss. UNKNOWN. doi: https://doi.org/10.1108/FEBE-07-2024-0033
Inadequate or ambiguous information flow among stakeholders, resulting in misinterpretations and errors during execution. | Communication | 12 | OLANREWAJU A. (2025). Application of structural equation modelling (SEM) to evaluate reworks in sustainable buildings. Front. Eng. Built. Environ.. Vol. UNKNOWN. Iss. UNKNOWN. doi: https://doi.org/10.1108/FEBE-07-2024-0033
Errors, omissions, or vagueness in design documentation that force corrections during construction. | Design | 12 | OLANREWAJU A. (2025). Application of structural equation modelling (SEM) to evaluate reworks in sustainable buildings. Front. Eng. Built. Environ.. Vol. UNKNOWN. Iss. UNKNOWN. doi: https://doi.org/10.1108/FEBE-07-2024-0033
Lack of robust systems, procedures, and controls to ensure quality during construction, resulting in recurring defects. | Management and Supervision | 12 | OLANREWAJU A. (2025). Application of structural equation modelling (SEM) to evaluate reworks in sustainable buildings. Front. Eng. Built. Environ.. Vol. UNKNOWN. Iss. UNKNOWN. doi: https://doi.org/10.1108/FEBE-07-2024-0033
Insufficient financial resources and delayed payments that disrupt project cash flow, leading to compromises in materials and workmanship. | Financial Constraints | 12 | OLANREWAJU A. (2025). Application of structural equation modelling (SEM) to evaluate reworks in sustainable buildings. Front. Eng. Built. Environ.. Vol. UNKNOWN. Iss. UNKNOWN. doi: https://doi.org/10.1108/FEBE-07-2024-0033
Absence of a comprehensive plan that integrates sustainability objectives into project execution, resulting in deviations from required standards. | Design | 12 | OLANREWAJU A. (2025). Application of structural equation modelling (SEM) to evaluate reworks in sustainable buildings. Front. Eng. Built. Environ.. Vol. UNKNOWN. Iss. UNKNOWN. doi: https://doi.org/10.1108/FEBE-07-2024-0033
Changes initiated by the client during construction, which force the project team to modify work already completed. | Client-Driven Influences | 12 | OLANREWAJU A. (2025). Application of structural equation modelling (SEM) to evaluate reworks in sustainable buildings. Front. Eng. Built. Environ.. Vol. UNKNOWN. Iss. UNKNOWN. doi: https://doi.org/10.1108/FEBE-07-2024-0033
Interruptions in material supply or procurement of materials that fail to meet quality and sustainability criteria, necessitating rework. | Material Resources | 12 | OLANREWAJU A. (2025). Application of structural equation modelling (SEM) to evaluate reworks in sustainable buildings. Front. Eng. Built. Environ.. Vol. UNKNOWN. Iss. UNKNOWN. doi: https://doi.org/10.1108/FEBE-07-2024-0033
An intense, time-constrained work environment where ambitious schedules and high production demands lead to rushed work and overlooked errors. | Time & Planning | 13 | LOVE P.E.D.; MATTHEWS J. (2024). Error Mastery in Alliance Transport Megaprojects. IEEE Trans Eng Manage. Vol. 71. Iss. UNKNOWN. doi: https://doi.org/10.1109/TEM.2022.3151494
A shortage of experienced and adequately supported personnel that leads to mistakes, particularly by junior engineers who must shoulder greater responsibility. | Human Resources | 13 | LOVE P.E.D.; MATTHEWS J. (2024). Error Mastery in Alliance Transport Megaprojects. IEEE Trans Eng Manage. Vol. 71. Iss. UNKNOWN. doi: https://doi.org/10.1109/TEM.2022.3151494
Failures in communication and coordination among various stakeholders (e.g., between the operator, design teams, and track groups) resulting in design changes that are not effectively disseminated. | Communication | 13 | LOVE P.E.D.; MATTHEWS J. (2024). Error Mastery in Alliance Transport Megaprojects. IEEE Trans Eng Manage. Vol. 71. Iss. UNKNOWN. doi: https://doi.org/10.1109/TEM.2022.3151494
Limited early involvement and underutilization of specialist subcontractors’ expertise—often compounded by selecting them solely on lowest bid criteria—resulting in quality issues and rework. | Contractor Selection & Performance | 13 | LOVE P.E.D.; MATTHEWS J. (2024). Error Mastery in Alliance Transport Megaprojects. IEEE Trans Eng Manage. Vol. 71. Iss. UNKNOWN. doi: https://doi.org/10.1109/TEM.2022.3151494
Unrealistic cost and programme expectations that force decisions to compromise quality. | Client-Driven Influences | 14 | FORD G.; GOSLING J. (2024). Professional perceptions of right-first-time and quality management in construction projects through open-ended feedback. Int. J. Qual. Reliab. Manage.. Vol. 41. Iss. 10. doi: https://doi.org/10.1108/IJQRM-08-2023-0246
A project delivery mindset that prioritizes short-term, measurable outputs (cost and time) over long-term quality outcomes. | Time & Planning | 14 | FORD G.; GOSLING J. (2024). Professional perceptions of right-first-time and quality management in construction projects through open-ended feedback. Int. J. Qual. Reliab. Manage.. Vol. 41. Iss. 10. doi: https://doi.org/10.1108/IJQRM-08-2023-0246
Lack of clear quality direction, accountability, and vision from project leaders. | Management and Supervision | 14 | FORD G.; GOSLING J. (2024). Professional perceptions of right-first-time and quality management in construction projects through open-ended feedback. Int. J. Qual. Reliab. Manage.. Vol. 41. Iss. 10. doi: https://doi.org/10.1108/IJQRM-08-2023-0246
Inadequate training, experience, and support among project personnel, leading to errors in execution. | Human Resources | 14 | FORD G.; GOSLING J. (2024). Professional perceptions of right-first-time and quality management in construction projects through open-ended feedback. Int. J. Qual. Reliab. Manage.. Vol. 41. Iss. 10. doi: https://doi.org/10.1108/IJQRM-08-2023-0246
Inadequate on-site oversight that allows errors to go undetected until rework is necessary. | Management and Supervision | 14 | FORD G.; GOSLING J. (2024). Professional perceptions of right-first-time and quality management in construction projects through open-ended feedback. Int. J. Qual. Reliab. Manage.. Vol. 41. Iss. 10. doi: https://doi.org/10.1108/IJQRM-08-2023-0246
Building work commencing without final or approved design details, which leads to errors and subsequent rework. | Design | 14 | FORD G.; GOSLING J. (2024). Professional perceptions of right-first-time and quality management in construction projects through open-ended feedback. Int. J. Qual. Reliab. Manage.. Vol. 41. Iss. 10. doi: https://doi.org/10.1108/IJQRM-08-2023-0246
Failure to clearly articulate and agree on quality requirements and expectations among all stakeholders at an early stage. | Communication | 14 | FORD G.; GOSLING J. (2024). Professional perceptions of right-first-time and quality management in construction projects through open-ended feedback. Int. J. Qual. Reliab. Manage.. Vol. 41. Iss. 10. doi: https://doi.org/10.1108/IJQRM-08-2023-0246
Uncertainty and lack of clarity over responsibilities and coordination between different engineering disciplines, resulting in errors in construction work. | Management and Supervision | 16 | LOVE P.E.D.; MATTHEWS J., PH.D. (2023). Hold-Ups and Failures in Negotiated Order: Unearthing the Nuances of Rework Causation in Construction. J Constr Eng Manage. Vol. 149. Iss. 3. doi: https://doi.org/10.1061/JCEMD4.COENG-13026
Failure to effectively communicate critical discrepancies and resource requirements, causing delays and additional work during project execution. | Communication | 16 | LOVE P.E.D.; MATTHEWS J., PH.D. (2023). Hold-Ups and Failures in Negotiated Order: Unearthing the Nuances of Rework Causation in Construction. J Constr Eng Manage. Vol. 149. Iss. 3. doi: https://doi.org/10.1061/JCEMD4.COENG-13026
Encompasses issues related to workforce attributes—including insufficient skilled manpower, inadequate supervision, poor knowledge, and substandard workmanship—that lead to errors requiring rework. | Human Resources | 17 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2023). Analyzing Underlying Factors of Rework in Generating Contractual Claims in Construction Projects. J Constr Eng Manage. Vol. 149. Iss. 6. doi: https://doi.org/10.1061/JCEMD4.COENG-12141
Involves issues such as poor-quality or defective materials, prefabrication errors, and untimely deliveries of materials and equipment that force rework when project specifications are not met. | Material Resources | 17 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2023). Analyzing Underlying Factors of Rework in Generating Contractual Claims in Construction Projects. J Constr Eng Manage. Vol. 149. Iss. 6. doi: https://doi.org/10.1061/JCEMD4.COENG-12141
Relates to shortcomings in work processes—such as incomplete design, frequent design changes, errors/omissions in drawings, and inadequate procurement methods—that lead directly to rework. | Design | 17 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2023). Analyzing Underlying Factors of Rework in Generating Contractual Claims in Construction Projects. J Constr Eng Manage. Vol. 149. Iss. 6. doi: https://doi.org/10.1061/JCEMD4.COENG-12141
Structural design modifications (by the owner) were not communicated to the track team, so guardrails were omitted. | Client-Driven Influences | 19 | LOVE P.E.D.; MATTHEWS J. (2024). The social organization of errors and the manifestation of rework: learning from narratives of practice. Prod Plann Control. Vol. 35. Iss. 6. doi: https://doi.org/10.1080/09537287.2022.2117664
An engineer assumed that a subcontractor misinterpreted the drawings, resulting in a drainage pit being installed 330 mm too high. | Contractor Selection & Performance | 19 | LOVE P.E.D.; MATTHEWS J. (2024). The social organization of errors and the manifestation of rework: learning from narratives of practice. Prod Plann Control. Vol. 35. Iss. 6. doi: https://doi.org/10.1080/09537287.2022.2117664
Unsatisfactory supervision during concrete cutting led to damage of a rail head. | Management and Supervision | 19 | LOVE P.E.D.; MATTHEWS J. (2024). The social organization of errors and the manifestation of rework: learning from narratives of practice. Prod Plann Control. Vol. 35. Iss. 6. doi: https://doi.org/10.1080/09537287.2022.2117664
Inadequate coordination between the design of a pedestrian bridge’s structure and its services resulted in clashes that required rework. | Management and Supervision | 19 | LOVE P.E.D.; MATTHEWS J. (2024). The social organization of errors and the manifestation of rework: learning from narratives of practice. Prod Plann Control. Vol. 35. Iss. 6. doi: https://doi.org/10.1080/09537287.2022.2117664
A late communication of design change (additional culverts required) forced an on-site pre-cast redesign and multiple formwork modifications. | Design | 19 | LOVE P.E.D.; MATTHEWS J. (2024). The social organization of errors and the manifestation of rework: learning from narratives of practice. Prod Plann Control. Vol. 35. Iss. 6. doi: https://doi.org/10.1080/09537287.2022.2117664
When actual construction (e.g., the hoisting pad design) does not meet the detailed design specifications (such as hoisting point position), increasing the risk of cracking in components. | Design | 21 | MENG F.; CAO X. (2024). An intelligent framework for rework risk identification in prefabricated construction processes based on compliance checking. Eng. Constr. Archit. Manage.. Vol. UNKNOWN. Iss. UNKNOWN. doi: https://doi.org/10.1108/ECAM-06-2023-0645
Improper stacking (e.g., exceeding recommended layers) or transportation issues (e.g., abnormal handling) that lead to abnormal stresses on prefabricated components, causing defects like cracks. | Material Resources | 21 | MENG F.; CAO X. (2024). An intelligent framework for rework risk identification in prefabricated construction processes based on compliance checking. Eng. Constr. Archit. Manage.. Vol. UNKNOWN. Iss. UNKNOWN. doi: https://doi.org/10.1108/ECAM-06-2023-0645
When components, upon onsite assembly, do not meet acceptance criteria (e.g., surface roughness, reinforcement details), thereby necessitating rework. | Material Resources | 21 | MENG F.; CAO X. (2024). An intelligent framework for rework risk identification in prefabricated construction processes based on compliance checking. Eng. Constr. Archit. Manage.. Vol. UNKNOWN. Iss. UNKNOWN. doi: https://doi.org/10.1108/ECAM-06-2023-0645
Failure to effectively integrate heterogeneous data (e.g., from BIM, sensors, inspection reports) across different PC stages can obscure potential rework risks. | Documentation & Information Management | 21 | MENG F.; CAO X. (2024). An intelligent framework for rework risk identification in prefabricated construction processes based on compliance checking. Eng. Constr. Archit. Manage.. Vol. UNKNOWN. Iss. UNKNOWN. doi: https://doi.org/10.1108/ECAM-06-2023-0645
Architects often do not possess sufficient construction knowledge and hands-on experience to integrate essential, design-specific construction input into their BIM models. | Human Resources | 22 | LUO J.; ZADEH P.; STAUB-FRENCH S. (2024). Ontology-Based Design Features for Representing Constructability in Architectural Design: Toward BIM in Off-Site Construction. J Constr Eng Manage. Vol. 150. Iss. 10. doi: https://doi.org/10.1061/JCEMD4.COENG-14764
Errors occur when design deliverables fail to capture accurate dimensions or proper connection details, leading to mismatches between the design and the actual fabrication/assembly. | Design | 22 | LUO J.; ZADEH P.; STAUB-FRENCH S. (2024). Ontology-Based Design Features for Representing Constructability in Architectural Design: Toward BIM in Off-Site Construction. J Constr Eng Manage. Vol. 150. Iss. 10. doi: https://doi.org/10.1061/JCEMD4.COENG-14764
The failure to incorporate critical construction information (e.g., manufacturing, logistics, assembly, and installation requirements) into early design stages. | Documentation & Information Management | 22 | LUO J.; ZADEH P.; STAUB-FRENCH S. (2024). Ontology-Based Design Features for Representing Constructability in Architectural Design: Toward BIM in Off-Site Construction. J Constr Eng Manage. Vol. 150. Iss. 10. doi: https://doi.org/10.1061/JCEMD4.COENG-14764
There is often limited interdisciplinary coordination between architects and construction experts, resulting in inadequate incorporation of practical construction constraints. | Management and Supervision | 22 | LUO J.; ZADEH P.; STAUB-FRENCH S. (2024). Ontology-Based Design Features for Representing Constructability in Architectural Design: Toward BIM in Off-Site Construction. J Constr Eng Manage. Vol. 150. Iss. 10. doi: https://doi.org/10.1061/JCEMD4.COENG-14764
Architectural designs may lack proper representation of key constructability aspects (e.g., details on component interfaces, tolerances, and assembly requirements), leading to rework during off-site fabrication. | Design | 22 | LUO J.; ZADEH P.; STAUB-FRENCH S. (2024). Ontology-Based Design Features for Representing Constructability in Architectural Design: Toward BIM in Off-Site Construction. J Constr Eng Manage. Vol. 150. Iss. 10. doi: https://doi.org/10.1061/JCEMD4.COENG-14764
Design teams lacking sufficient knowledge of design codes or regulatory requirements, leading to models that do not meet standards. | Design | 23 | ALSUHAIBANI A.; HAN B.; LEITE F. (2022). Investigating the Causes of Missing Field Detected Issues from BIM-Based Construction Coordination through Semistructured Interviews. J Archit Eng. Vol. 28. Iss. 4. doi: https://doi.org/10.1061/(ASCE)AE.1943-5568.0000562
Modifications to the project scope initiated by the client that lead to changes in design. These changes trigger rework—often resulting in demolition and additional material wastage. | Client-Driven Influences | 24 | MUSARAT M.A.; ALALOUL W.S.; HAMEED N.; DHINAHARAN R.; QURESHI A.H.; WAHAB M.M.A. (2023). Efficient Construction Waste Management: A Solution through Industrial Revolution (IR) 4.0 Evaluated by AHP. Sustainability. Vol. 15. Iss. 1. doi: https://doi.org/10.3390/su15010274
Inadequate or ineffective exchange of information between project parties leading to misunderstandings in design and planning. (Inferred from its frequent citation and noted severity.) | Communication | 25 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2023). Rework causes classification model with liable parties of the contract in construction projects. Front. Built Environ.. Vol. 9. Iss. UNKNOWN. doi: https://doi.org/10.3389/fbuil.2023.1143829
Frequent alterations in design documents or scope (often initiated by the client) that force redesign and rework. | Client-Driven Influences | 25 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2023). Rework causes classification model with liable parties of the contract in construction projects. Front. Built Environ.. Vol. 9. Iss. UNKNOWN. doi: https://doi.org/10.3389/fbuil.2023.1143829
Insufficient financial resources that may lead to compromised design quality and subsequent rework. | Financial Constraints | 25 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2023). Rework causes classification model with liable parties of the contract in construction projects. Front. Built Environ.. Vol. 9. Iss. UNKNOWN. doi: https://doi.org/10.3389/fbuil.2023.1143829
Ambiguities, gaps, or inconsistencies in design or contract documentation that necessitate rework. | Documentation & Information Management | 25 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2023). Rework causes classification model with liable parties of the contract in construction projects. Front. Built Environ.. Vol. 9. Iss. UNKNOWN. doi: https://doi.org/10.3389/fbuil.2023.1143829
Mistakes, omissions, or inaccuracies in design documents that require subsequent correction. | Design | 25 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2023). Rework causes classification model with liable parties of the contract in construction projects. Front. Built Environ.. Vol. 9. Iss. UNKNOWN. doi: https://doi.org/10.3389/fbuil.2023.1143829
Incomplete, ambiguous, or poorly prepared contract documents that lead to misinterpretation and subsequent rework. | Documentation & Information Management | 25 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2023). Rework causes classification model with liable parties of the contract in construction projects. Front. Built Environ.. Vol. 9. Iss. UNKNOWN. doi: https://doi.org/10.3389/fbuil.2023.1143829
Poorly planned or scheduled construction activities that create conflicts or delays, thereby increasing rework. | Time & Planning | 25 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2023). Rework causes classification model with liable parties of the contract in construction projects. Front. Built Environ.. Vol. 9. Iss. UNKNOWN. doi: https://doi.org/10.3389/fbuil.2023.1143829
Failure to properly implement quality control and monitoring measures, leading to defects and rework. | Management and Supervision | 25 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2023). Rework causes classification model with liable parties of the contract in construction projects. Front. Built Environ.. Vol. 9. Iss. UNKNOWN. doi: https://doi.org/10.3389/fbuil.2023.1143829
Alterations or revisions to design (post–Issue For Construction) prompted by mistakes in drawings or specifications. (Inferred from respondents’ comments.) | Design | 26 | LOVE P.E.D.; MATTHEWS J.; IKA L.A.; FANG W. (2022). Error culture and its impact on rework: An exploration of norms and practices in a transport mega-project. Dev. Built. Environ.. Vol. 10. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.dibe.2022.100067
An organizational norm where errors are hidden or not openly discussed due to fear of blame, leading to delayed detection. | Communication | 26 | LOVE P.E.D.; MATTHEWS J.; IKA L.A.; FANG W. (2022). Error culture and its impact on rework: An exploration of norms and practices in a transport mega-project. Dev. Built. Environ.. Vol. 10. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.dibe.2022.100067
Inadequate processes for detecting, communicating, and learning from errors. (Not provided as a formal “definition” but inferred from the discussion of error culture.) | Communication | 26 | LOVE P.E.D.; MATTHEWS J.; IKA L.A.; FANG W. (2022). Error culture and its impact on rework: An exploration of norms and practices in a transport mega-project. Dev. Built. Environ.. Vol. 10. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.dibe.2022.100067
Slow turnaround in reviewing and approving design modifications, which disrupts alignment between design intent and construction work. | Design | 26 | LOVE P.E.D.; MATTHEWS J.; IKA L.A.; FANG W. (2022). Error culture and its impact on rework: An exploration of norms and practices in a transport mega-project. Dev. Built. Environ.. Vol. 10. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.dibe.2022.100067
Absence of robust, real-time systems to capture, store, and analyze data on errors and rework events. | Documentation & Information Management | 26 | LOVE P.E.D.; MATTHEWS J.; IKA L.A.; FANG W. (2022). Error culture and its impact on rework: An exploration of norms and practices in a transport mega-project. Dev. Built. Environ.. Vol. 10. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.dibe.2022.100067
Alterations in design “spec, scope, and construction method” aimed at improving quality or constructability; these include changes initiated by clients, designers, or contractors. | Design | 27 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2022). Classification of rework root causes in the design stage of projects for contract assessment. IOP Conf. Ser. Earth Environ. Sci.. Vol. 1101. Iss. 4. doi: https://doi.org/10.1088/1755-1315/1101/4/042033
Mistakes or inaccuracies in design documents often attributed to complexity and tight time boxing. | Design | 27 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2022). Classification of rework root causes in the design stage of projects for contract assessment. IOP Conf. Ser. Earth Environ. Sci.. Vol. 1101. Iss. 4. doi: https://doi.org/10.1088/1755-1315/1101/4/042033
Inadequate management of design documents leading to omissions and misinterpretations. | Documentation & Information Management | 27 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2022). Classification of rework root causes in the design stage of projects for contract assessment. IOP Conf. Ser. Earth Environ. Sci.. Vol. 1101. Iss. 4. doi: https://doi.org/10.1088/1755-1315/1101/4/042033
Insufficient skills or training among design personnel leading to errors or omissions. | Human Resources | 27 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2022). Classification of rework root causes in the design stage of projects for contract assessment. IOP Conf. Ser. Earth Environ. Sci.. Vol. 1101. Iss. 4. doi: https://doi.org/10.1088/1755-1315/1101/4/042033
Ineffective information exchange and lack of integration between different disciplines and consultants. | Communication | 27 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2022). Classification of rework root causes in the design stage of projects for contract assessment. IOP Conf. Ser. Earth Environ. Sci.. Vol. 1101. Iss. 4. doi: https://doi.org/10.1088/1755-1315/1101/4/042033
Failure to adequately monitor and enforce quality standards during design, resulting in defects. | Management and Supervision | 27 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2022). Classification of rework root causes in the design stage of projects for contract assessment. IOP Conf. Ser. Earth Environ. Sci.. Vol. 1101. Iss. 4. doi: https://doi.org/10.1088/1755-1315/1101/4/042033
Rushed design work caused by tight deadlines, which can lead to incomplete information and omissions. | Time & Planning | 27 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2022). Classification of rework root causes in the design stage of projects for contract assessment. IOP Conf. Ser. Earth Environ. Sci.. Vol. 1101. Iss. 4. doi: https://doi.org/10.1088/1755-1315/1101/4/042033
Failure to comply with required material standards during the design phase. | Material Resources | 27 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2022). Classification of rework root causes in the design stage of projects for contract assessment. IOP Conf. Ser. Earth Environ. Sci.. Vol. 1101. Iss. 4. doi: https://doi.org/10.1088/1755-1315/1101/4/042033
The backward flow of information from a downstream activity to an upstream one; quantified as the feedback value (D̃ij) in the process architect DSM. | Documentation & Information Management | 28 | ATTARI-SHENDI M.; SAIDI-MEHRABAD M.; GHEIDAR-KHELJANI J. (2022). A Comprehensive Mathematical Model for Sequencing Interrelated Activities in Complex Product Development Projects. IEEE Trans Eng Manage. Vol. 69. Iss. 6. doi: https://doi.org/10.1109/TEM.2019.2936287
An ordering of interrelated activities that does not account for their dependencies, leading to extra iterations (or rework) when feedback is high. | Time & Planning | 28 | ATTARI-SHENDI M.; SAIDI-MEHRABAD M.; GHEIDAR-KHELJANI J. (2022). A Comprehensive Mathematical Model for Sequencing Interrelated Activities in Complex Product Development Projects. IEEE Trans Eng Manage. Vol. 69. Iss. 6. doi: https://doi.org/10.1109/TEM.2019.2936287
Low maturity (or readiness) of product components—i.e., components that have not been extensively field‐tested, thus posing higher risk of failure and necessitating rework. | Material Resources | 28 | ATTARI-SHENDI M.; SAIDI-MEHRABAD M.; GHEIDAR-KHELJANI J. (2022). A Comprehensive Mathematical Model for Sequencing Interrelated Activities in Complex Product Development Projects. IEEE Trans Eng Manage. Vol. 69. Iss. 6. doi: https://doi.org/10.1109/TEM.2019.2936287
The concurrent execution of interrelated activities; while overlapping can reduce project duration, it may force rework if later information conflicts with earlier assumptions. | Time & Planning | 28 | ATTARI-SHENDI M.; SAIDI-MEHRABAD M.; GHEIDAR-KHELJANI J. (2022). A Comprehensive Mathematical Model for Sequencing Interrelated Activities in Complex Product Development Projects. IEEE Trans Eng Manage. Vol. 69. Iss. 6. doi: https://doi.org/10.1109/TEM.2019.2936287
The mismatch between available periodic budget and the total cost (including rework cost) when activities are sequenced without regard to financial limits. | Financial Constraints | 28 | ATTARI-SHENDI M.; SAIDI-MEHRABAD M.; GHEIDAR-KHELJANI J. (2022). A Comprehensive Mathematical Model for Sequencing Interrelated Activities in Complex Product Development Projects. IEEE Trans Eng Manage. Vol. 69. Iss. 6. doi: https://doi.org/10.1109/TEM.2019.2936287
Design errors, omissions, or modifications resulting from low design quality. (Often described as “poor or inappropriate design” that leads to reworks.) | Design | 29 | SAFAPOUR E.; KERMANSHACHI S.; TANEJA P.; PAMIDIMUKKALA A. (2022). Exploratory Analysis of Human-, Organizational-, and Project-Based Reworks: Challenges and Strategies. J. Legal Aff. Disput. Resolut. Eng. Construction. Vol. 14. Iss. 1. doi: https://doi.org/10.1061/(ASCE)LA.1943-4170.0000524
Ambiguity or absence of a clearly defined project scope, causing subsequent design changes. | Design | 29 | SAFAPOUR E.; KERMANSHACHI S.; TANEJA P.; PAMIDIMUKKALA A. (2022). Exploratory Analysis of Human-, Organizational-, and Project-Based Reworks: Challenges and Strategies. J. Legal Aff. Disput. Resolut. Eng. Construction. Vol. 14. Iss. 1. doi: https://doi.org/10.1061/(ASCE)LA.1943-4170.0000524
Poor or inadequate communication channels and information sharing within the organization. | Communication | 29 | SAFAPOUR E.; KERMANSHACHI S.; TANEJA P.; PAMIDIMUKKALA A. (2022). Exploratory Analysis of Human-, Organizational-, and Project-Based Reworks: Challenges and Strategies. J. Legal Aff. Disput. Resolut. Eng. Construction. Vol. 14. Iss. 1. doi: https://doi.org/10.1061/(ASCE)LA.1943-4170.0000524
Insufficient coordination among different teams or departments, resulting in conflicting or duplicated efforts. | Management and Supervision | 29 | SAFAPOUR E.; KERMANSHACHI S.; TANEJA P.; PAMIDIMUKKALA A. (2022). Exploratory Analysis of Human-, Organizational-, and Project-Based Reworks: Challenges and Strategies. J. Legal Aff. Disput. Resolut. Eng. Construction. Vol. 14. Iss. 1. doi: https://doi.org/10.1061/(ASCE)LA.1943-4170.0000524
Employment or reliance on workers lacking sufficient experience or skill, leading to execution errors. | Human Resources | 29 | SAFAPOUR E.; KERMANSHACHI S.; TANEJA P.; PAMIDIMUKKALA A. (2022). Exploratory Analysis of Human-, Organizational-, and Project-Based Reworks: Challenges and Strategies. J. Legal Aff. Disput. Resolut. Eng. Construction. Vol. 14. Iss. 1. doi: https://doi.org/10.1061/(ASCE)LA.1943-4170.0000524
Errors resulting from workers’ misunderstanding of design or project information because of insufficient knowledge. | Human Resources | 29 | SAFAPOUR E.; KERMANSHACHI S.; TANEJA P.; PAMIDIMUKKALA A. (2022). Exploratory Analysis of Human-, Organizational-, and Project-Based Reworks: Challenges and Strategies. J. Legal Aff. Disput. Resolut. Eng. Construction. Vol. 14. Iss. 1. doi: https://doi.org/10.1061/(ASCE)LA.1943-4170.0000524
A lack of commitment to safety protocols, leading to accidents and errors that cause rework. | Safety Culture | 29 | SAFAPOUR E.; KERMANSHACHI S.; TANEJA P.; PAMIDIMUKKALA A. (2022). Exploratory Analysis of Human-, Organizational-, and Project-Based Reworks: Challenges and Strategies. J. Legal Aff. Disput. Resolut. Eng. Construction. Vol. 14. Iss. 1. doi: https://doi.org/10.1061/(ASCE)LA.1943-4170.0000524
Omissions or lack of detail in design that necessitate rework (inferred from term). | Design | 30 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2022). Investigating the Relationship between Reworks and Contractual Claims: The Salience of Contract Conditions. J. Legal Aff. Disput. Resolut. Eng. Construction. Vol. 14. Iss. 1. doi: https://doi.org/10.1061/(ASCE)LA.1943-4170.0000519
Mistakes in technical documentation or construction execution (not explicitly defined). | Documentation & Information Management | 30 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2022). Investigating the Relationship between Reworks and Contractual Claims: The Salience of Contract Conditions. J. Legal Aff. Disput. Resolut. Eng. Construction. Vol. 14. Iss. 1. doi: https://doi.org/10.1061/(ASCE)LA.1943-4170.0000519
Inadequate selection process affecting project quality (term used without detailed definition). | Contractor Selection & Performance | 30 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2022). Investigating the Relationship between Reworks and Contractual Claims: The Salience of Contract Conditions. J. Legal Aff. Disput. Resolut. Eng. Construction. Vol. 14. Iss. 1. doi: https://doi.org/10.1061/(ASCE)LA.1943-4170.0000519
Deficiencies in procurement and contract management (term not further defined). | Contractor Selection & Performance | 30 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2022). Investigating the Relationship between Reworks and Contractual Claims: The Salience of Contract Conditions. J. Legal Aff. Disput. Resolut. Eng. Construction. Vol. 14. Iss. 1. doi: https://doi.org/10.1061/(ASCE)LA.1943-4170.0000519
Inefficient management of project documents, leading to errors (not explicitly defined). | Documentation & Information Management | 30 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2022). Investigating the Relationship between Reworks and Contractual Claims: The Salience of Contract Conditions. J. Legal Aff. Disput. Resolut. Eng. Construction. Vol. 14. Iss. 1. doi: https://doi.org/10.1061/(ASCE)LA.1943-4170.0000519
Inadequate skill levels among the workforce (term used without further explanation). | Human Resources | 30 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2022). Investigating the Relationship between Reworks and Contractual Claims: The Salience of Contract Conditions. J. Legal Aff. Disput. Resolut. Eng. Construction. Vol. 14. Iss. 1. doi: https://doi.org/10.1061/(ASCE)LA.1943-4170.0000519
Inexperience among personnel affecting outcomes (inferred from the label). | Human Resources | 30 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2022). Investigating the Relationship between Reworks and Contractual Claims: The Salience of Contract Conditions. J. Legal Aff. Disput. Resolut. Eng. Construction. Vol. 14. Iss. 1. doi: https://doi.org/10.1061/(ASCE)LA.1943-4170.0000519
Inadequate training/knowledge among team members (not explicitly defined). | Human Resources | 30 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2022). Investigating the Relationship between Reworks and Contractual Claims: The Salience of Contract Conditions. J. Legal Aff. Disput. Resolut. Eng. Construction. Vol. 14. Iss. 1. doi: https://doi.org/10.1061/(ASCE)LA.1943-4170.0000519
Substandard workmanship and negative attitudes contributing to errors (term not detailed further). | Human Resources | 30 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2022). Investigating the Relationship between Reworks and Contractual Claims: The Salience of Contract Conditions. J. Legal Aff. Disput. Resolut. Eng. Construction. Vol. 14. Iss. 1. doi: https://doi.org/10.1061/(ASCE)LA.1943-4170.0000519
Frequent staffing changes that disrupt continuity (not explicitly defined). | Human Resources | 30 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2022). Investigating the Relationship between Reworks and Contractual Claims: The Salience of Contract Conditions. J. Legal Aff. Disput. Resolut. Eng. Construction. Vol. 14. Iss. 1. doi: https://doi.org/10.1061/(ASCE)LA.1943-4170.0000519
Insufficient labor force to meet project demands (term used without further elaboration). | Human Resources | 30 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2022). Investigating the Relationship between Reworks and Contractual Claims: The Salience of Contract Conditions. J. Legal Aff. Disput. Resolut. Eng. Construction. Vol. 14. Iss. 1. doi: https://doi.org/10.1061/(ASCE)LA.1943-4170.0000519
Low morale and lack of incentives leading to mistakes (not explicitly defined). | Human Resources | 30 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2022). Investigating the Relationship between Reworks and Contractual Claims: The Salience of Contract Conditions. J. Legal Aff. Disput. Resolut. Eng. Construction. Vol. 14. Iss. 1. doi: https://doi.org/10.1061/(ASCE)LA.1943-4170.0000519
Lack of clear safety and job security measures (term used without further detail). | Safety Culture | 30 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2022). Investigating the Relationship between Reworks and Contractual Claims: The Salience of Contract Conditions. J. Legal Aff. Disput. Resolut. Eng. Construction. Vol. 14. Iss. 1. doi: https://doi.org/10.1061/(ASCE)LA.1943-4170.0000519
Insufficient supervisory personnel for effective oversight (not explicitly defined). | Management and Supervision | 30 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2022). Investigating the Relationship between Reworks and Contractual Claims: The Salience of Contract Conditions. J. Legal Aff. Disput. Resolut. Eng. Construction. Vol. 14. Iss. 1. doi: https://doi.org/10.1061/(ASCE)LA.1943-4170.0000519
Use of inferior materials or errors during prefabrication (not explicitly defined). | Material Resources | 30 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2022). Investigating the Relationship between Reworks and Contractual Claims: The Salience of Contract Conditions. J. Legal Aff. Disput. Resolut. Eng. Construction. Vol. 14. Iss. 1. doi: https://doi.org/10.1061/(ASCE)LA.1943-4170.0000519
Materials that fail to meet required standards (term used without detailed definition). | Material Resources | 30 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2022). Investigating the Relationship between Reworks and Contractual Claims: The Salience of Contract Conditions. J. Legal Aff. Disput. Resolut. Eng. Construction. Vol. 14. Iss. 1. doi: https://doi.org/10.1061/(ASCE)LA.1943-4170.0000519
Improper use of equipment or modifications in material use that lead to inefficiencies (not explicitly defined). | Material Resources | 30 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2022). Investigating the Relationship between Reworks and Contractual Claims: The Salience of Contract Conditions. J. Legal Aff. Disput. Resolut. Eng. Construction. Vol. 14. Iss. 1. doi: https://doi.org/10.1061/(ASCE)LA.1943-4170.0000519
Incorrect handling or relocation of materials/equipment causing delays (term used without further detail). | Material Resources | 30 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2022). Investigating the Relationship between Reworks and Contractual Claims: The Salience of Contract Conditions. J. Legal Aff. Disput. Resolut. Eng. Construction. Vol. 14. Iss. 1. doi: https://doi.org/10.1061/(ASCE)LA.1943-4170.0000519
Late deliveries that hinder project progress (not explicitly defined). | Time & Planning | 30 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2022). Investigating the Relationship between Reworks and Contractual Claims: The Salience of Contract Conditions. J. Legal Aff. Disput. Resolut. Eng. Construction. Vol. 14. Iss. 1. doi: https://doi.org/10.1061/(ASCE)LA.1943-4170.0000519
Ineffective communication among project stakeholders (term used without further detail). | Communication | 30 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2022). Investigating the Relationship between Reworks and Contractual Claims: The Salience of Contract Conditions. J. Legal Aff. Disput. Resolut. Eng. Construction. Vol. 14. Iss. 1. doi: https://doi.org/10.1061/(ASCE)LA.1943-4170.0000519
Poor implementation of quality control measures (not explicitly defined). | Management and Supervision | 30 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2022). Investigating the Relationship between Reworks and Contractual Claims: The Salience of Contract Conditions. J. Legal Aff. Disput. Resolut. Eng. Construction. Vol. 14. Iss. 1. doi: https://doi.org/10.1061/(ASCE)LA.1943-4170.0000519
Underutilization of IT and technology in project management (term used without further detail). | Technology Utilization | 30 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2022). Investigating the Relationship between Reworks and Contractual Claims: The Salience of Contract Conditions. J. Legal Aff. Disput. Resolut. Eng. Construction. Vol. 14. Iss. 1. doi: https://doi.org/10.1061/(ASCE)LA.1943-4170.0000519
Deficiencies in overall management and on-site supervision (not explicitly defined). | Management and Supervision | 30 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2022). Investigating the Relationship between Reworks and Contractual Claims: The Salience of Contract Conditions. J. Legal Aff. Disput. Resolut. Eng. Construction. Vol. 14. Iss. 1. doi: https://doi.org/10.1061/(ASCE)LA.1943-4170.0000519
Inadequate or ambiguous documentation that creates confusion (term used without further explanation). | Documentation & Information Management | 30 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2022). Investigating the Relationship between Reworks and Contractual Claims: The Salience of Contract Conditions. J. Legal Aff. Disput. Resolut. Eng. Construction. Vol. 14. Iss. 1. doi: https://doi.org/10.1061/(ASCE)LA.1943-4170.0000519
Inconsistencies and gaps in information that lead to errors (not explicitly defined). | Documentation & Information Management | 30 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2022). Investigating the Relationship between Reworks and Contractual Claims: The Salience of Contract Conditions. J. Legal Aff. Disput. Resolut. Eng. Construction. Vol. 14. Iss. 1. doi: https://doi.org/10.1061/(ASCE)LA.1943-4170.0000519
Insufficient planning and scheduling leading to operational pressure (not explicitly defined). | Time & Planning | 30 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2022). Investigating the Relationship between Reworks and Contractual Claims: The Salience of Contract Conditions. J. Legal Aff. Disput. Resolut. Eng. Construction. Vol. 14. Iss. 1. doi: https://doi.org/10.1061/(ASCE)LA.1943-4170.0000519
Financial constraints that affect project execution (not explicitly defined). | Financial Constraints | 30 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2022). Investigating the Relationship between Reworks and Contractual Claims: The Salience of Contract Conditions. J. Legal Aff. Disput. Resolut. Eng. Construction. Vol. 14. Iss. 1. doi: https://doi.org/10.1061/(ASCE)LA.1943-4170.0000519
Under time pressure, project managers and teams must meet demanding timelines that hinder thorough checking, coordination, and correction of mistakes. | Time & Planning | 30 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2022). Investigating the Relationship between Reworks and Contractual Claims: The Salience of Contract Conditions. J. Legal Aff. Disput. Resolut. Eng. Construction. Vol. 14. Iss. 1. doi: https://doi.org/10.1061/(ASCE)LA.1943-4170.0000519
Physical damage or deviations caused by improper handling (not explicitly defined). | Material Resources | 30 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2022). Investigating the Relationship between Reworks and Contractual Claims: The Salience of Contract Conditions. J. Legal Aff. Disput. Resolut. Eng. Construction. Vol. 14. Iss. 1. doi: https://doi.org/10.1061/(ASCE)LA.1943-4170.0000519
Adverse weather or site-related factors impacting work quality (not explicitly defined). | External Influences | 30 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2022). Investigating the Relationship between Reworks and Contractual Claims: The Salience of Contract Conditions. J. Legal Aff. Disput. Resolut. Eng. Construction. Vol. 14. Iss. 1. doi: https://doi.org/10.1061/(ASCE)LA.1943-4170.0000519
Inadequate consideration of practical construction methods during design (not explicitly defined). | Design | 30 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2022). Investigating the Relationship between Reworks and Contractual Claims: The Salience of Contract Conditions. J. Legal Aff. Disput. Resolut. Eng. Construction. Vol. 14. Iss. 1. doi: https://doi.org/10.1061/(ASCE)LA.1943-4170.0000519
Changes in regulations or policies that impact project requirements (not explicitly defined). | Legal & Regulatory | 30 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2022). Investigating the Relationship between Reworks and Contractual Claims: The Salience of Contract Conditions. J. Legal Aff. Disput. Resolut. Eng. Construction. Vol. 14. Iss. 1. doi: https://doi.org/10.1061/(ASCE)LA.1943-4170.0000519
Ambiguity in decision-making roles within the project organization (not explicitly defined). | Management and Supervision | 30 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2022). Investigating the Relationship between Reworks and Contractual Claims: The Salience of Contract Conditions. J. Legal Aff. Disput. Resolut. Eng. Construction. Vol. 14. Iss. 1. doi: https://doi.org/10.1061/(ASCE)LA.1943-4170.0000519
Unforeseen events or external uncertainties that disrupt project progress (not explicitly defined). | External Influences | 30 | ASADI R.; ROTIMI J.O.B.; WILKINSON S. (2022). Investigating the Relationship between Reworks and Contractual Claims: The Salience of Contract Conditions. J. Legal Aff. Disput. Resolut. Eng. Construction. Vol. 14. Iss. 1. doi: https://doi.org/10.1061/(ASCE)LA.1943-4170.0000519
Mistakes in design, improper planning, and a not well-defined scope that lead to rework | Design | 31 | MAHAMID I. (2022). Impact of rework on material waste in building construction projects. Int. J. Constr. Manage.. Vol. 22. Iss. 8. doi: https://doi.org/10.1080/15623599.2020.1728607
Insufficient skills among workers that lead to mistakes requiring rework | Human Resources | 31 | MAHAMID I. (2022). Impact of rework on material waste in building construction projects. Int. J. Constr. Manage.. Vol. 22. Iss. 8. doi: https://doi.org/10.1080/15623599.2020.1728607
Work or materials that do not meet the predefined quality or design standards | Material Resources | 31 | MAHAMID I. (2022). Impact of rework on material waste in building construction projects. Int. J. Constr. Manage.. Vol. 22. Iss. 8. doi: https://doi.org/10.1080/15623599.2020.1728607
Insufficient oversight during construction leading to errors and the need for rework | Management and Supervision | 31 | MAHAMID I. (2022). Impact of rework on material waste in building construction projects. Int. J. Constr. Manage.. Vol. 22. Iss. 8. doi: https://doi.org/10.1080/15623599.2020.1728607
Modifications or alterations in the project scope after initial planning that result in additional work (rework) | Design | 31 | MAHAMID I. (2022). Impact of rework on material waste in building construction projects. Int. J. Constr. Manage.. Vol. 22. Iss. 8. doi: https://doi.org/10.1080/15623599.2020.1728607
Regulatory changes and policy shifts that affect project requirements. | Legal & Regulatory | 32 | ELSEUFY S.M.; HUSSEIN A.; BADAWY M. (2022). A hybrid SEM-ANN model for predicting overall rework impact on the performance of bridge construction projects. Structures. Vol. 46. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.istruc.2022.10.100
Weather-related conditions that impact construction activities. | External Influences | 32 | ELSEUFY S.M.; HUSSEIN A.; BADAWY M. (2022). A hybrid SEM-ANN model for predicting overall rework impact on the performance of bridge construction projects. Structures. Vol. 46. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.istruc.2022.10.100
Inadequate or unfavorable site conditions that hinder smooth construction. | External Influences | 32 | ELSEUFY S.M.; HUSSEIN A.; BADAWY M. (2022). A hybrid SEM-ANN model for predicting overall rework impact on the performance of bridge construction projects. Structures. Vol. 46. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.istruc.2022.10.100
Prolonged work hours that may lead to fatigue and errors. | Time & Planning | 32 | ELSEUFY S.M.; HUSSEIN A.; BADAWY M. (2022). A hybrid SEM-ANN model for predicting overall rework impact on the performance of bridge construction projects. Structures. Vol. 46. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.istruc.2022.10.100
Inadequate technical expertise leading to mistakes in work execution. | Human Resources | 32 | ELSEUFY S.M.; HUSSEIN A.; BADAWY M. (2022). A hybrid SEM-ANN model for predicting overall rework impact on the performance of bridge construction projects. Structures. Vol. 46. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.istruc.2022.10.100
Lack of adequate training programs to build necessary competencies. | Human Resources | 32 | ELSEUFY S.M.; HUSSEIN A.; BADAWY M. (2022). A hybrid SEM-ANN model for predicting overall rework impact on the performance of bridge construction projects. Structures. Vol. 46. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.istruc.2022.10.100
Non-compliance with safety protocols which can indirectly lead to errors. | Safety Culture | 32 | ELSEUFY S.M.; HUSSEIN A.; BADAWY M. (2022). A hybrid SEM-ANN model for predicting overall rework impact on the performance of bridge construction projects. Structures. Vol. 46. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.istruc.2022.10.100
Poor management practices that lead to coordination and oversight problems. | Management and Supervision | 32 | ELSEUFY S.M.; HUSSEIN A.; BADAWY M. (2022). A hybrid SEM-ANN model for predicting overall rework impact on the performance of bridge construction projects. Structures. Vol. 46. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.istruc.2022.10.100
Inadequate oversight during project execution that fails to catch errors early. | Management and Supervision | 32 | ELSEUFY S.M.; HUSSEIN A.; BADAWY M. (2022). A hybrid SEM-ANN model for predicting overall rework impact on the performance of bridge construction projects. Structures. Vol. 46. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.istruc.2022.10.100
Mistakes made during design or construction due to oversight or miscommunication. | Design | 32 | ELSEUFY S.M.; HUSSEIN A.; BADAWY M. (2022). A hybrid SEM-ANN model for predicting overall rework impact on the performance of bridge construction projects. Structures. Vol. 46. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.istruc.2022.10.100
Ineffective information exchange among project stakeholders. | Communication | 32 | ELSEUFY S.M.; HUSSEIN A.; BADAWY M. (2022). A hybrid SEM-ANN model for predicting overall rework impact on the performance of bridge construction projects. Structures. Vol. 46. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.istruc.2022.10.100
Inadequate funding affecting the quality of pre-construction studies and design work. | Financial Constraints | 32 | ELSEUFY S.M.; HUSSEIN A.; BADAWY M. (2022). A hybrid SEM-ANN model for predicting overall rework impact on the performance of bridge construction projects. Structures. Vol. 46. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.istruc.2022.10.100
Flaws or delays in the design process that result in unclear or incorrect designs. | Design | 32 | ELSEUFY S.M.; HUSSEIN A.; BADAWY M. (2022). A hybrid SEM-ANN model for predicting overall rework impact on the performance of bridge construction projects. Structures. Vol. 46. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.istruc.2022.10.100
Ambiguities or discrepancies in contract documents leading to misinterpretation during execution. | Documentation & Information Management | 32 | ELSEUFY S.M.; HUSSEIN A.; BADAWY M. (2022). A hybrid SEM-ANN model for predicting overall rework impact on the performance of bridge construction projects. Structures. Vol. 46. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.istruc.2022.10.100
Inadequate implementation of quality control procedures. | Management and Supervision | 32 | ELSEUFY S.M.; HUSSEIN A.; BADAWY M. (2022). A hybrid SEM-ANN model for predicting overall rework impact on the performance of bridge construction projects. Structures. Vol. 46. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.istruc.2022.10.100
Unrealistic scheduling in project management results in time pressure, compelling rushed decisions that sidestep vital procedures and reduce quality oversight. | Time & Planning | 32 | ELSEUFY S.M.; HUSSEIN A.; BADAWY M. (2022). A hybrid SEM-ANN model for predicting overall rework impact on the performance of bridge construction projects. Structures. Vol. 46. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.istruc.2022.10.100
Deviations from or non‐compliance with the required material/equipment standards. | Documentation & Information Management | 32 | ELSEUFY S.M.; HUSSEIN A.; BADAWY M. (2022). A hybrid SEM-ANN model for predicting overall rework impact on the performance of bridge construction projects. Structures. Vol. 46. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.istruc.2022.10.100
Mistakes arising from the use of unsuitable construction methods or technology. | Material Resources | 32 | ELSEUFY S.M.; HUSSEIN A.; BADAWY M. (2022). A hybrid SEM-ANN model for predicting overall rework impact on the performance of bridge construction projects. Structures. Vol. 46. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.istruc.2022.10.100
Unintended deviations from plans, goals, or feedback processes; an incorrect action resulting from lack of knowledge. | Management and Supervision | 33 | LOVE P.E.D.; MATTHEWS J. (2022). There Is Strength in Numbers: Seven Principles to Contain and Reduce Error and Mitigate Rework in Transport Mega-Projects. IEEE Eng Manage Rev. Vol. 50. Iss. 1. doi: https://doi.org/10.1109/EMR.2022.3145367
Underlying conditions (stemming from management decisions, shared norms, and work practices) that create an environment prone to errors. | Management and Supervision | 33 | LOVE P.E.D.; MATTHEWS J. (2022). There Is Strength in Numbers: Seven Principles to Contain and Reduce Error and Mitigate Rework in Transport Mega-Projects. IEEE Eng Manage Rev. Vol. 50. Iss. 1. doi: https://doi.org/10.1109/EMR.2022.3145367
A zero-tolerance, error aversion mindset in which errors are seen as highly negative, leading to concealment or under-reporting of mistakes. | Management and Supervision | 33 | LOVE P.E.D.; MATTHEWS J. (2022). There Is Strength in Numbers: Seven Principles to Contain and Reduce Error and Mitigate Rework in Transport Mega-Projects. IEEE Eng Manage Rev. Vol. 50. Iss. 1. doi: https://doi.org/10.1109/EMR.2022.3145367
Inadequate sharing of error information among team members, which delays detection and correction of errors. | Documentation & Information Management | 33 | LOVE P.E.D.; MATTHEWS J. (2022). There Is Strength in Numbers: Seven Principles to Contain and Reduce Error and Mitigate Rework in Transport Mega-Projects. IEEE Eng Manage Rev. Vol. 50. Iss. 1. doi: https://doi.org/10.1109/EMR.2022.3145367
Insufficient involvement by management in promoting error learning and creating an environment where errors can be openly discussed and addressed. | Management and Supervision | 33 | LOVE P.E.D.; MATTHEWS J. (2022). There Is Strength in Numbers: Seven Principles to Contain and Reduce Error and Mitigate Rework in Transport Mega-Projects. IEEE Eng Manage Rev. Vol. 50. Iss. 1. doi: https://doi.org/10.1109/EMR.2022.3145367
Failure to anticipate, plan for, and adapt to potential errors, resulting in an inability to respond quickly when errors occur. | Management and Supervision | 33 | LOVE P.E.D.; MATTHEWS J. (2022). There Is Strength in Numbers: Seven Principles to Contain and Reduce Error and Mitigate Rework in Transport Mega-Projects. IEEE Eng Manage Rev. Vol. 50. Iss. 1. doi: https://doi.org/10.1109/EMR.2022.3145367
The failure to report or document errors—often due to fear of blame—which results in “ghost data” and recurrent issues going unaddressed. | Management and Supervision | 33 | LOVE P.E.D.; MATTHEWS J. (2022). There Is Strength in Numbers: Seven Principles to Contain and Reduce Error and Mitigate Rework in Transport Mega-Projects. IEEE Eng Manage Rev. Vol. 50. Iss. 1. doi: https://doi.org/10.1109/EMR.2022.3145367
Changes/modifications initiated by the user/owner during the construction process. | Client-Driven Influences | 34 | TAGHIZADEH K.; NOORZAI E.; ZAMAN Z.; AMIRI M.; SAMAEE RAHNEE N. (2021). Identifying the Most Important Rework Factors in Building Projects and Providing a Solution to Reduce Their Effects. J. Inst. Eng. Ser. A. Vol. 102. Iss. 4. doi: https://doi.org/10.1007/s40030-021-00570-9
Rushing the construction schedule reduces quality and accuracy, resulting in errors. | Time & Planning | 34 | TAGHIZADEH K.; NOORZAI E.; ZAMAN Z.; AMIRI M.; SAMAEE RAHNEE N. (2021). Identifying the Most Important Rework Factors in Building Projects and Providing a Solution to Reduce Their Effects. J. Inst. Eng. Ser. A. Vol. 102. Iss. 4. doi: https://doi.org/10.1007/s40030-021-00570-9
Substituting materials or technology mid-process causes rework due to re‐execution with different inputs. | Material Resources | 34 | TAGHIZADEH K.; NOORZAI E.; ZAMAN Z.; AMIRI M.; SAMAEE RAHNEE N. (2021). Identifying the Most Important Rework Factors in Building Projects and Providing a Solution to Reduce Their Effects. J. Inst. Eng. Ser. A. Vol. 102. Iss. 4. doi: https://doi.org/10.1007/s40030-021-00570-9
Conflicting or unclear instructions from project executives lead to improper execution. | Management and Supervision | 34 | TAGHIZADEH K.; NOORZAI E.; ZAMAN Z.; AMIRI M.; SAMAEE RAHNEE N. (2021). Identifying the Most Important Rework Factors in Building Projects and Providing a Solution to Reduce Their Effects. J. Inst. Eng. Ser. A. Vol. 102. Iss. 4. doi: https://doi.org/10.1007/s40030-021-00570-9
Fluctuations or reductions in contract cost disrupt project continuity and lead to rework. | Financial Constraints | 34 | TAGHIZADEH K.; NOORZAI E.; ZAMAN Z.; AMIRI M.; SAMAEE RAHNEE N. (2021). Identifying the Most Important Rework Factors in Building Projects and Providing a Solution to Reduce Their Effects. J. Inst. Eng. Ser. A. Vol. 102. Iss. 4. doi: https://doi.org/10.1007/s40030-021-00570-9
Deliberate redoing of work by the contractor to improve quality, which in turn increases rework. | Contractor Selection & Performance | 34 | TAGHIZADEH K.; NOORZAI E.; ZAMAN Z.; AMIRI M.; SAMAEE RAHNEE N. (2021). Identifying the Most Important Rework Factors in Building Projects and Providing a Solution to Reduce Their Effects. J. Inst. Eng. Ser. A. Vol. 102. Iss. 4. doi: https://doi.org/10.1007/s40030-021-00570-9
Redesign or modifications by the design team aimed at improving quality that result in additional work. | Design | 34 | TAGHIZADEH K.; NOORZAI E.; ZAMAN Z.; AMIRI M.; SAMAEE RAHNEE N. (2021). Identifying the Most Important Rework Factors in Building Projects and Providing a Solution to Reduce Their Effects. J. Inst. Eng. Ser. A. Vol. 102. Iss. 4. doi: https://doi.org/10.1007/s40030-021-00570-9
Failure to align design with actual construction conditions leads to execution errors. | Design | 34 | TAGHIZADEH K.; NOORZAI E.; ZAMAN Z.; AMIRI M.; SAMAEE RAHNEE N. (2021). Identifying the Most Important Rework Factors in Building Projects and Providing a Solution to Reduce Their Effects. J. Inst. Eng. Ser. A. Vol. 102. Iss. 4. doi: https://doi.org/10.1007/s40030-021-00570-9
Ineffective collaboration among architects, engineers, and planners causes conflicts and errors. | Management and Supervision | 34 | TAGHIZADEH K.; NOORZAI E.; ZAMAN Z.; AMIRI M.; SAMAEE RAHNEE N. (2021). Identifying the Most Important Rework Factors in Building Projects and Providing a Solution to Reduce Their Effects. J. Inst. Eng. Ser. A. Vol. 102. Iss. 4. doi: https://doi.org/10.1007/s40030-021-00570-9
A large volume of tasks leads to oversight and design errors that later necessitate rework. | Design | 34 | TAGHIZADEH K.; NOORZAI E.; ZAMAN Z.; AMIRI M.; SAMAEE RAHNEE N. (2021). Identifying the Most Important Rework Factors in Building Projects and Providing a Solution to Reduce Their Effects. J. Inst. Eng. Ser. A. Vol. 102. Iss. 4. doi: https://doi.org/10.1007/s40030-021-00570-9
Employment of poor quality materials results in failures that require rework. | Material Resources | 34 | TAGHIZADEH K.; NOORZAI E.; ZAMAN Z.; AMIRI M.; SAMAEE RAHNEE N. (2021). Identifying the Most Important Rework Factors in Building Projects and Providing a Solution to Reduce Their Effects. J. Inst. Eng. Ser. A. Vol. 102. Iss. 4. doi: https://doi.org/10.1007/s40030-021-00570-9
Substandard construction practices lead to defects that must be remedied. | Human Resources | 34 | TAGHIZADEH K.; NOORZAI E.; ZAMAN Z.; AMIRI M.; SAMAEE RAHNEE N. (2021). Identifying the Most Important Rework Factors in Building Projects and Providing a Solution to Reduce Their Effects. J. Inst. Eng. Ser. A. Vol. 102. Iss. 4. doi: https://doi.org/10.1007/s40030-021-00570-9
New or changed requests from the end-user during construction result in modifications and rework. | Client-Driven Influences | 34 | TAGHIZADEH K.; NOORZAI E.; ZAMAN Z.; AMIRI M.; SAMAEE RAHNEE N. (2021). Identifying the Most Important Rework Factors in Building Projects and Providing a Solution to Reduce Their Effects. J. Inst. Eng. Ser. A. Vol. 102. Iss. 4. doi: https://doi.org/10.1007/s40030-021-00570-9
Mistakes during the handling or transport of materials lead to errors that must be corrected. | Material Resources | 34 | TAGHIZADEH K.; NOORZAI E.; ZAMAN Z.; AMIRI M.; SAMAEE RAHNEE N. (2021). Identifying the Most Important Rework Factors in Building Projects and Providing a Solution to Reduce Their Effects. J. Inst. Eng. Ser. A. Vol. 102. Iss. 4. doi: https://doi.org/10.1007/s40030-021-00570-9
Low motivation among workers leads to errors and delays that necessitate rework. | Human Resources | 34 | TAGHIZADEH K.; NOORZAI E.; ZAMAN Z.; AMIRI M.; SAMAEE RAHNEE N. (2021). Identifying the Most Important Rework Factors in Building Projects and Providing a Solution to Reduce Their Effects. J. Inst. Eng. Ser. A. Vol. 102. Iss. 4. doi: https://doi.org/10.1007/s40030-021-00570-9
Insufficient modern technology and inadequate training lead to execution errors and rework. | Technology Utilization | 34 | TAGHIZADEH K.; NOORZAI E.; ZAMAN Z.; AMIRI M.; SAMAEE RAHNEE N. (2021). Identifying the Most Important Rework Factors in Building Projects and Providing a Solution to Reduce Their Effects. J. Inst. Eng. Ser. A. Vol. 102. Iss. 4. doi: https://doi.org/10.1007/s40030-021-00570-9
An organizational mindset that strives for zero errors by focusing on error prevention, emphasizing error eradication and a “zero tolerance” approach. Errors are seen as unacceptable, leading workers to hide mistakes. | Management and Supervision | 35 | MATTHEWS J.; LOVE P.E.D.; IKA L.A.; FANG W. (2022). Error aversion or management? Exploring the impact of culture at the sharp-end of production in a mega-project. Dev. Built. Environ.. Vol. 10. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.dibe.2022.100074
An approach that accepts errors as inevitable and focuses on coping with them through open communication, error analysis, and learning from mistakes to minimize negative consequences and reduce future errors. | Management and Supervision | 35 | MATTHEWS J.; LOVE P.E.D.; IKA L.A.; FANG W. (2022). Error aversion or management? Exploring the impact of culture at the sharp-end of production in a mega-project. Dev. Built. Environ.. Vol. 10. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.dibe.2022.100074
A condition in which workers feel afraid to admit or report errors due to fear of blame or embarrassment. | Safety Culture | 35 | MATTHEWS J.; LOVE P.E.D.; IKA L.A.; FANG W. (2022). Error aversion or management? Exploring the impact of culture at the sharp-end of production in a mega-project. Dev. Built. Environ.. Vol. 10. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.dibe.2022.100074
Insufficient sharing of error information among team members, which prevents collective learning and delays error detection and correction. | Documentation & Information Management | 35 | MATTHEWS J.; LOVE P.E.D.; IKA L.A.; FANG W. (2022). Error aversion or management? Exploring the impact of culture at the sharp-end of production in a mega-project. Dev. Built. Environ.. Vol. 10. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.dibe.2022.100074
Senior management’s practice of under‑reporting or suppressing nonconformance reports to avoid delays and protect schedules. | Management and Supervision | 36 | LOVE P.E.D.; IKA L.; LUO H.; ZHOU Y.; ZHONG B.; FANG W. (2022). Rework, Failures, and Unsafe Behavior: Moving Toward an Error Management Mindset in Construction. IEEE Trans Eng Manage. Vol. 69. Iss. 4. doi: https://doi.org/10.1109/TEM.2020.2982463
Reduced on‑site oversight resulting from tight margins and high production pressures, causing quality issues to be overlooked. | Management and Supervision | 36 | LOVE P.E.D.; IKA L.; LUO H.; ZHOU Y.; ZHONG B.; FANG W. (2022). Rework, Failures, and Unsafe Behavior: Moving Toward an Error Management Mindset in Construction. IEEE Trans Eng Manage. Vol. 69. Iss. 4. doi: https://doi.org/10.1109/TEM.2020.2982463
An organizational mindset focused solely on preventing errors and achieving “zero defects” that discourages error reporting. | Management and Supervision | 36 | LOVE P.E.D.; IKA L.; LUO H.; ZHOU Y.; ZHONG B.; FANG W. (2022). Rework, Failures, and Unsafe Behavior: Moving Toward an Error Management Mindset in Construction. IEEE Trans Eng Manage. Vol. 69. Iss. 4. doi: https://doi.org/10.1109/TEM.2020.2982463
A deliberate prioritization of safety (driven by legislative and regulatory demands) over quality, resulting in quality being neglected. | Safety Culture | 36 | LOVE P.E.D.; IKA L.; LUO H.; ZHOU Y.; ZHONG B.; FANG W. (2022). Rework, Failures, and Unsafe Behavior: Moving Toward an Error Management Mindset in Construction. IEEE Trans Eng Manage. Vol. 69. Iss. 4. doi: https://doi.org/10.1109/TEM.2020.2982463
Inadequate sharing of error information and nonconformances among workers and management, hindering timely corrective action. | Documentation & Information Management | 36 | LOVE P.E.D.; IKA L.; LUO H.; ZHOU Y.; ZHONG B.; FANG W. (2022). Rework, Failures, and Unsafe Behavior: Moving Toward an Error Management Mindset in Construction. IEEE Trans Eng Manage. Vol. 69. Iss. 4. doi: https://doi.org/10.1109/TEM.2020.2982463
The absence of practices that promote learning from errors, resulting in repeated mistakes and ongoing rework. | Management and Supervision | 36 | LOVE P.E.D.; IKA L.; LUO H.; ZHOU Y.; ZHONG B.; FANG W. (2022). Rework, Failures, and Unsafe Behavior: Moving Toward an Error Management Mindset in Construction. IEEE Trans Eng Manage. Vol. 69. Iss. 4. doi: https://doi.org/10.1109/TEM.2020.2982463
Insufficient human and financial resources dedicated to quality management, leading to lapses in quality control. | Financial Constraints | 36 | LOVE P.E.D.; IKA L.; LUO H.; ZHOU Y.; ZHONG B.; FANG W. (2022). Rework, Failures, and Unsafe Behavior: Moving Toward an Error Management Mindset in Construction. IEEE Trans Eng Manage. Vol. 69. Iss. 4. doi: https://doi.org/10.1109/TEM.2020.2982463
A breakdown in communication and integration between design teams and on‑site construction, resulting in misinterpretation of plans. | Design | 36 | LOVE P.E.D.; IKA L.; LUO H.; ZHOU Y.; ZHONG B.; FANG W. (2022). Rework, Failures, and Unsafe Behavior: Moving Toward an Error Management Mindset in Construction. IEEE Trans Eng Manage. Vol. 69. Iss. 4. doi: https://doi.org/10.1109/TEM.2020.2982463
Behaviors in which individuals or managers deliberately hide or fragment nonconformance reports to avoid blame and financial penalties. | Management and Supervision | 36 | LOVE P.E.D.; IKA L.; LUO H.; ZHOU Y.; ZHONG B.; FANG W. (2022). Rework, Failures, and Unsafe Behavior: Moving Toward an Error Management Mindset in Construction. IEEE Trans Eng Manage. Vol. 69. Iss. 4. doi: https://doi.org/10.1109/TEM.2020.2982463
Insufficient and irregular exchange of information among project participants; this barrier prevents timely and accurate information flow. | Documentation & Information Management | 37 | NAVEED F.; KHAN K.I.A. (2022). Investigating the influence of information complexity on construction quality: a systems thinking approach. Eng. Constr. Archit. Manage.. Vol. 29. Iss. 3. doi: https://doi.org/10.1108/ECAM-05-2020-0311
Ambiguous, incomplete, or poorly specified drawings that lead to misinterpretation and errors during construction. | Design | 37 | NAVEED F.; KHAN K.I.A. (2022). Investigating the influence of information complexity on construction quality: a systems thinking approach. Eng. Constr. Archit. Manage.. Vol. 29. Iss. 3. doi: https://doi.org/10.1108/ECAM-05-2020-0311
Repeated modifications or alterations in the project scope or contractual terms that disrupt execution and necessitate rework. | Client-Driven Influences | 37 | NAVEED F.; KHAN K.I.A. (2022). Investigating the influence of information complexity on construction quality: a systems thinking approach. Eng. Constr. Archit. Manage.. Vol. 29. Iss. 3. doi: https://doi.org/10.1108/ECAM-05-2020-0311
Timeliness issues in receiving correct and up‑to‑date information, hindering decision-making and execution. | Communication | 37 | NAVEED F.; KHAN K.I.A. (2022). Investigating the influence of information complexity on construction quality: a systems thinking approach. Eng. Constr. Archit. Manage.. Vol. 29. Iss. 3. doi: https://doi.org/10.1108/ECAM-05-2020-0311
Changes to the design made at the last minute that force revisions. | Client-Driven Influences | 41 | MOHAMED HASSAN A.; RENUKA S.M.; MONIKA T. (2023). Analysis of factors causing rework and their mitigation strategies in construction projects. Mater. Today Proc.. Vol. UNKNOWN. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.matpr.2023.03.517
Poor quality in the execution of work leading to errors. | Human Resources | 41 | MOHAMED HASSAN A.; RENUKA S.M.; MONIKA T. (2023). Analysis of factors causing rework and their mitigation strategies in construction projects. Mater. Today Proc.. Vol. UNKNOWN. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.matpr.2023.03.517
Structural damage occurring during commissioning because inferior materials were used. | Material Resources | 41 | MOHAMED HASSAN A.; RENUKA S.M.; MONIKA T. (2023). Analysis of factors causing rework and their mitigation strategies in construction projects. Mater. Today Proc.. Vol. UNKNOWN. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.matpr.2023.03.517
The owner’s inflexible or stubborn approach causing delays or disputes. | Client-Driven Influences | 41 | MOHAMED HASSAN A.; RENUKA S.M.; MONIKA T. (2023). Analysis of factors causing rework and their mitigation strategies in construction projects. Mater. Today Proc.. Vol. UNKNOWN. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.matpr.2023.03.517
Delays caused by inefficiencies in sub-contractor or consultant activities. | Contractor Selection & Performance | 41 | MOHAMED HASSAN A.; RENUKA S.M.; MONIKA T. (2023). Analysis of factors causing rework and their mitigation strategies in construction projects. Mater. Today Proc.. Vol. UNKNOWN. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.matpr.2023.03.517
Insufficient funds or financial instability of a stakeholder. | Financial Constraints | 41 | MOHAMED HASSAN A.; RENUKA S.M.; MONIKA T. (2023). Analysis of factors causing rework and their mitigation strategies in construction projects. Mater. Today Proc.. Vol. UNKNOWN. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.matpr.2023.03.517
Discrepancies or inconsistencies among contractual documents. | Documentation & Information Management | 41 | MOHAMED HASSAN A.; RENUKA S.M.; MONIKA T. (2023). Analysis of factors causing rework and their mitigation strategies in construction projects. Mater. Today Proc.. Vol. UNKNOWN. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.matpr.2023.03.517
Disagreements regarding the final settlement of accounts. | Documentation & Information Management | 41 | MOHAMED HASSAN A.; RENUKA S.M.; MONIKA T. (2023). Analysis of factors causing rework and their mitigation strategies in construction projects. Mater. Today Proc.. Vol. UNKNOWN. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.matpr.2023.03.517
Price increases that lead to disputes over final account settlements. | Financial Constraints | 41 | MOHAMED HASSAN A.; RENUKA S.M.; MONIKA T. (2023). Analysis of factors causing rework and their mitigation strategies in construction projects. Mater. Today Proc.. Vol. UNKNOWN. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.matpr.2023.03.517
Disputes arising from changes that were not properly documented. | Documentation & Information Management | 41 | MOHAMED HASSAN A.; RENUKA S.M.; MONIKA T. (2023). Analysis of factors causing rework and their mitigation strategies in construction projects. Mater. Today Proc.. Vol. UNKNOWN. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.matpr.2023.03.517
Delays caused by missing or incomplete handover documentation. | Documentation & Information Management | 41 | MOHAMED HASSAN A.; RENUKA S.M.; MONIKA T. (2023). Analysis of factors causing rework and their mitigation strategies in construction projects. Mater. Today Proc.. Vol. UNKNOWN. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.matpr.2023.03.517
External opposition or protests that disrupt project progress. | External Influences | 41 | MOHAMED HASSAN A.; RENUKA S.M.; MONIKA T. (2023). Analysis of factors causing rework and their mitigation strategies in construction projects. Mater. Today Proc.. Vol. UNKNOWN. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.matpr.2023.03.517
Mandatory legal requirements imposed by authorities. | Legal & Regulatory | 41 | MOHAMED HASSAN A.; RENUKA S.M.; MONIKA T. (2023). Analysis of factors causing rework and their mitigation strategies in construction projects. Mater. Today Proc.. Vol. UNKNOWN. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.matpr.2023.03.517
Unforeseen events such as natural disasters or social unrest. | External Influences | 41 | MOHAMED HASSAN A.; RENUKA S.M.; MONIKA T. (2023). Analysis of factors causing rework and their mitigation strategies in construction projects. Mater. Today Proc.. Vol. UNKNOWN. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.matpr.2023.03.517
The intentional breaking of established rules and procedures—sometimes as a means to save time or reduce costs, or when rules are inapplicable to the dynamic work environment. | Human Resources | 42 | LOVE P.E.D.; MATTHEWS J.; SING M.C.P.; PORTER S.R.; FANG W. (2022). State of Science: Why Does Rework Occur in Construction? What Are Its Consequences? And What Can be Done to Mitigate Its Occurrence?. Engineering. Vol. 18. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.eng.2022.05.010
The incapacity or disinclination of organizational members to engage in critical reflection—resulting in repetitive errors due to unchallenged routines and inadequate reasoning. | Human Resources | 42 | LOVE P.E.D.; MATTHEWS J.; SING M.C.P.; PORTER S.R.; FANG W. (2022). State of Science: Why Does Rework Occur in Construction? What Are Its Consequences? And What Can be Done to Mitigate Its Occurrence?. Engineering. Vol. 18. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.eng.2022.05.010
The trade-off between quality and safety where prioritizing safety (due to strict regulations) often leads to compromises in quality, subsequently causing errors that require rework. | Safety Culture | 42 | LOVE P.E.D.; MATTHEWS J.; SING M.C.P.; PORTER S.R.; FANG W. (2022). State of Science: Why Does Rework Occur in Construction? What Are Its Consequences? And What Can be Done to Mitigate Its Occurrence?. Engineering. Vol. 18. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.eng.2022.05.010
The deliberate suppression of error reporting by managers (through direct suppression, agenda setting, or shaping ideological settings) to avoid blame or negative perceptions. | Management and Supervision | 42 | LOVE P.E.D.; MATTHEWS J.; SING M.C.P.; PORTER S.R.; FANG W. (2022). State of Science: Why Does Rework Occur in Construction? What Are Its Consequences? And What Can be Done to Mitigate Its Occurrence?. Engineering. Vol. 18. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.eng.2022.05.010
A cultural orientation that views errors as wholly negative, leading to their concealment and suppression of learning opportunities, which in turn perpetuates rework. | Management and Supervision | 42 | LOVE P.E.D.; MATTHEWS J.; SING M.C.P.; PORTER S.R.; FANG W. (2022). State of Science: Why Does Rework Occur in Construction? What Are Its Consequences? And What Can be Done to Mitigate Its Occurrence?. Engineering. Vol. 18. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.eng.2022.05.010
Inconsistencies between project documents (both within a single discipline and between different disciplines) that cause direct conflicts (e.g., mismatches between structural, architectural, and MEP details). | Documentation & Information Management | 44 | TRACH R.; LENDO-SIWICKA M.; PAWLUK K.; POŁOŃSKI M. (2021). Analysis of direct rework costs in Ukrainian construction; [Analiza kosztów bezpośrednich robót naprawczych w projektach budowlanych na Ukrainie]. Arch Civ Eng. Vol. 67. Iss. 2. doi: https://doi.org/10.24425/ace.2021.137175
Mistakes or omissions in design documents—including missing details (identifier numbers, dimensions, etc.), insufficient site studies (e.g., soil analysis), failure to account for fire standards, and calculation errors. | Design | 44 | TRACH R.; LENDO-SIWICKA M.; PAWLUK K.; POŁOŃSKI M. (2021). Analysis of direct rework costs in Ukrainian construction; [Analiza kosztów bezpośrednich robót naprawczych w projektach budowlanych na Ukrainie]. Arch Civ Eng. Vol. 67. Iss. 2. doi: https://doi.org/10.24425/ace.2021.137175
Mistakes made during construction—often due to poor workmanship or the use of low-quality materials—that result in issues like formwork displacement, deformations, inaccurate dimensions, and insufficient reinforcement. | Human Resources | 44 | TRACH R.; LENDO-SIWICKA M.; PAWLUK K.; POŁOŃSKI M. (2021). Analysis of direct rework costs in Ukrainian construction; [Analiza kosztów bezpośrednich robót naprawczych w projektach budowlanych na Ukrainie]. Arch Civ Eng. Vol. 67. Iss. 2. doi: https://doi.org/10.24425/ace.2021.137175
Ineffective communication and coordination among project stakeholders that leads to conflicts and delays—for example, when interdisciplinary collaboration is lacking or crucial information is provided too late, necessitating rework. | Communication | 44 | TRACH R.; LENDO-SIWICKA M.; PAWLUK K.; POŁOŃSKI M. (2021). Analysis of direct rework costs in Ukrainian construction; [Analiza kosztów bezpośrednich robót naprawczych w projektach budowlanych na Ukrainie]. Arch Civ Eng. Vol. 67. Iss. 2. doi: https://doi.org/10.24425/ace.2021.137175
The premature initiation of construction activities before all essential preconstruction processes have been completed. | Time & Planning | 45 | IBRAHIM M.W.; LABIB Y.; VEERAMANI D.; HANNA A.S.; RUSSELL J. (2021). Comprehensive Model for Construction Readiness Assessment. J Manage Eng. Vol. 37. Iss. 1. doi: https://doi.org/10.1061/(ASCE)ME.1943-5479.0000832
A state in which a project has not completed or sufficiently implemented necessary preconstruction activities and readiness factors. | Management and Supervision | 45 | IBRAHIM M.W.; LABIB Y.; VEERAMANI D.; HANNA A.S.; RUSSELL J. (2021). Comprehensive Model for Construction Readiness Assessment. J Manage Eng. Vol. 37. Iss. 1. doi: https://doi.org/10.1061/(ASCE)ME.1943-5479.0000832
External stakeholder pressure that drives a project to mobilize before it is fully prepared. | External Influences | 45 | IBRAHIM M.W.; LABIB Y.; VEERAMANI D.; HANNA A.S.; RUSSELL J. (2021). Comprehensive Model for Construction Readiness Assessment. J Manage Eng. Vol. 37. Iss. 1. doi: https://doi.org/10.1061/(ASCE)ME.1943-5479.0000832
Aggressive project deadlines can induce time pressure, which negatively impacts the ability to properly review, coordinate, or fix issues during implementation. | Time & Planning | 46 | AL-JANABI A.M.; ABDEL-MONEM M.S.; EL-DASH K.M. (2020). Factors causing rework and their impact on projects' performance in Egypt. J. Civ. Eng. Manage.. Vol. 26. Iss. 7. doi: https://doi.org/10.3846/jcem.2020.12916
Modifications in design—often due to conflicts (e.g., with underground utilities) or unforeseen site conditions—that require rework. | Design | 46 | AL-JANABI A.M.; ABDEL-MONEM M.S.; EL-DASH K.M. (2020). Factors causing rework and their impact on projects' performance in Egypt. J. Civ. Eng. Manage.. Vol. 26. Iss. 7. doi: https://doi.org/10.3846/jcem.2020.12916
Alterations in the project specifications initiated by the client during construction that necessitate major adjustments in planning and execution. | Client-Driven Influences | 46 | AL-JANABI A.M.; ABDEL-MONEM M.S.; EL-DASH K.M. (2020). Factors causing rework and their impact on projects' performance in Egypt. J. Civ. Eng. Manage.. Vol. 26. Iss. 7. doi: https://doi.org/10.3846/jcem.2020.12916
Insufficient availability of skilled workers leads to overburdened teams, increased mistakes, and consequent rework. | Human Resources | 49 | SAFAPOUR E.; KERMANSHACHI S. (2021). Uncertainty analysis of rework predictors in post-hurricane reconstruction of critical transportation infrastructure. Prog. Disaster Sci.. Vol. 11. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.pdisas.2021.100194
The effectiveness with which knowledge, data, and information are shared among project stakeholders; poor information management leads to misunderstandings and errors. | Documentation & Information Management | 49 | SAFAPOUR E.; KERMANSHACHI S. (2021). Uncertainty analysis of rework predictors in post-hurricane reconstruction of critical transportation infrastructure. Prog. Disaster Sci.. Vol. 11. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.pdisas.2021.100194
The degree of effective communication and integration among project parties; poor coordination leads to misunderstandings and increased rework. | Management and Supervision | 49 | SAFAPOUR E.; KERMANSHACHI S. (2021). Uncertainty analysis of rework predictors in post-hurricane reconstruction of critical transportation infrastructure. Prog. Disaster Sci.. Vol. 11. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.pdisas.2021.100194
Periods during which work is halted (due to environmental, safety, or other issues), leading to delays and increased error rates upon resumption. | External Influences | 49 | SAFAPOUR E.; KERMANSHACHI S. (2021). Uncertainty analysis of rework predictors in post-hurricane reconstruction of critical transportation infrastructure. Prog. Disaster Sci.. Vol. 11. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.pdisas.2021.100194
Strict or changing regulatory demands that require project modifications; these may force alterations in work to meet new standards. | Legal & Regulatory | 49 | SAFAPOUR E.; KERMANSHACHI S. (2021). Uncertainty analysis of rework predictors in post-hurricane reconstruction of critical transportation infrastructure. Prog. Disaster Sci.. Vol. 11. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.pdisas.2021.100194
Described as workers’ insufficient skills and experience—leading to labor mistakes, misunderstanding of drawings/specifications, and misuse of available resources. | Human Resources | 52 | LIU Q.; YE G.; FENG Y.; WANG C.; PENG Y. (2020). Case-based insights into rework costs of residential building projects in China. Int. J. Constr. Manage.. Vol. 20. Iss. 4. doi: https://doi.org/10.1080/15623599.2018.1484856
Involves repeated modifications initiated during construction that force previously completed work to be redone. | Design | 52 | LIU Q.; YE G.; FENG Y.; WANG C.; PENG Y. (2020). Case-based insights into rework costs of residential building projects in China. Int. J. Constr. Manage.. Vol. 20. Iss. 4. doi: https://doi.org/10.1080/15623599.2018.1484856
Describes poor planning and scheduling of work activities, leading to mismanagement and delays that trigger rework. | Time & Planning | 52 | LIU Q.; YE G.; FENG Y.; WANG C.; PENG Y. (2020). Case-based insights into rework costs of residential building projects in China. Int. J. Constr. Manage.. Vol. 20. Iss. 4. doi: https://doi.org/10.1080/15623599.2018.1484856
Refers to the lack of effective communication and integration among project stakeholders, which results in misunderstandings and errors that lead to rework. | Communication | 52 | LIU Q.; YE G.; FENG Y.; WANG C.; PENG Y. (2020). Case-based insights into rework costs of residential building projects in China. Int. J. Constr. Manage.. Vol. 20. Iss. 4. doi: https://doi.org/10.1080/15623599.2018.1484856
Failure to effectively organize and align tasks, meetings, and information among stakeholders, leading to misalignment and errors. | Management and Supervision | 53 | YAP J.B.H.; ROU CHONG J.; SKITMORE M.; LEE W.P. (2020). Rework Causation that Undermines Safety Performance during Production in Construction. J Constr Eng Manage. Vol. 146. Iss. 9. doi: https://doi.org/10.1061/(ASCE)CO.1943-7862.0001902
Lack of timely, clear, and effective exchange of information among project participants, resulting in outdated or erroneous instructions. | Communication | 53 | YAP J.B.H.; ROU CHONG J.; SKITMORE M.; LEE W.P. (2020). Rework Causation that Undermines Safety Performance during Production in Construction. J Constr Eng Manage. Vol. 146. Iss. 9. doi: https://doi.org/10.1061/(ASCE)CO.1943-7862.0001902
Inadequate oversight, selection, and supervision of subcontractors that leads to errors and subsequent rework. | Contractor Selection & Performance | 53 | YAP J.B.H.; ROU CHONG J.; SKITMORE M.; LEE W.P. (2020). Rework Causation that Undermines Safety Performance during Production in Construction. J Constr Eng Manage. Vol. 146. Iss. 9. doi: https://doi.org/10.1061/(ASCE)CO.1943-7862.0001902
Inadequate supervision and inspection practices that fail to catch errors early, leading to risky work practices and subsequent rework. | Management and Supervision | 53 | YAP J.B.H.; ROU CHONG J.; SKITMORE M.; LEE W.P. (2020). Rework Causation that Undermines Safety Performance during Production in Construction. J Constr Eng Manage. Vol. 146. Iss. 9. doi: https://doi.org/10.1061/(ASCE)CO.1943-7862.0001902
Inefficient management of the worksite including poor planning, resource allocation, and materials handling, which leads to disorganized operations and errors. | Management and Supervision | 53 | YAP J.B.H.; ROU CHONG J.; SKITMORE M.; LEE W.P. (2020). Rework Causation that Undermines Safety Performance during Production in Construction. J Constr Eng Manage. Vol. 146. Iss. 9. doi: https://doi.org/10.1061/(ASCE)CO.1943-7862.0001902
Effective exchange of information among owners; poor communication may lead to documentation errors and subsequent rework. | Communication | 56 | TAMMY N.J.; ISMAIL I.I.; NOOR R.N.H.R.M.; YUNUS J.N.; DOLLAH Z. (2021). Analysis of rework causes in infrastructure projects in pulau pinang. Civil Engi. Arc.. Vol. 9. Iss. 5. doi: https://doi.org/10.13189/cea.2021.091317
Design or construction changes initiated by the client that disrupt planned work and require rework. | Client-Driven Influences | 56 | TAMMY N.J.; ISMAIL I.I.; NOOR R.N.H.R.M.; YUNUS J.N.; DOLLAH Z. (2021). Analysis of rework causes in infrastructure projects in pulau pinang. Civil Engi. Arc.. Vol. 9. Iss. 5. doi: https://doi.org/10.13189/cea.2021.091317
An insufficient number of trained supervisory staff, resulting in poor oversight of work execution. | Human Resources | 56 | TAMMY N.J.; ISMAIL I.I.; NOOR R.N.H.R.M.; YUNUS J.N.; DOLLAH Z. (2021). Analysis of rework causes in infrastructure projects in pulau pinang. Civil Engi. Arc.. Vol. 9. Iss. 5. doi: https://doi.org/10.13189/cea.2021.091317
Vague or ambiguous instructions given to workers, leading to misinterpretation and errors. | Documentation & Information Management | 56 | TAMMY N.J.; ISMAIL I.I.; NOOR R.N.H.R.M.; YUNUS J.N.; DOLLAH Z. (2021). Analysis of rework causes in infrastructure projects in pulau pinang. Civil Engi. Arc.. Vol. 9. Iss. 5. doi: https://doi.org/10.13189/cea.2021.091317
Insufficient supervisory staff relative to the workforce, leading to inadequate oversight and quality control. | Human Resources | 56 | TAMMY N.J.; ISMAIL I.I.; NOOR R.N.H.R.M.; YUNUS J.N.; DOLLAH Z. (2021). Analysis of rework causes in infrastructure projects in pulau pinang. Civil Engi. Arc.. Vol. 9. Iss. 5. doi: https://doi.org/10.13189/cea.2021.091317
Poor quality execution of tasks that results in errors, requiring subsequent correction. | Human Resources | 56 | TAMMY N.J.; ISMAIL I.I.; NOOR R.N.H.R.M.; YUNUS J.N.; DOLLAH Z. (2021). Analysis of rework causes in infrastructure projects in pulau pinang. Civil Engi. Arc.. Vol. 9. Iss. 5. doi: https://doi.org/10.13189/cea.2021.091317
A lack of necessary skills or expertise among the labor force, leading to mistakes that necessitate rework. | Human Resources | 56 | TAMMY N.J.; ISMAIL I.I.; NOOR R.N.H.R.M.; YUNUS J.N.; DOLLAH Z. (2021). Analysis of rework causes in infrastructure projects in pulau pinang. Civil Engi. Arc.. Vol. 9. Iss. 5. doi: https://doi.org/10.13189/cea.2021.091317
Challenges arising from design or planning that make construction difficult or inefficient. | Design | 56 | TAMMY N.J.; ISMAIL I.I.; NOOR R.N.H.R.M.; YUNUS J.N.; DOLLAH Z. (2021). Analysis of rework causes in infrastructure projects in pulau pinang. Civil Engi. Arc.. Vol. 9. Iss. 5. doi: https://doi.org/10.13189/cea.2021.091317
Alterations to the original project plan or scope once work is underway, causing disruption and rework. | Client-Driven Influences | 56 | TAMMY N.J.; ISMAIL I.I.; NOOR R.N.H.R.M.; YUNUS J.N.; DOLLAH Z. (2021). Analysis of rework causes in infrastructure projects in pulau pinang. Civil Engi. Arc.. Vol. 9. Iss. 5. doi: https://doi.org/10.13189/cea.2021.091317
Inadequate emphasis on quality management mechanisms that lead to defects and subsequent rework. (Not explicitly defined beyond its high significance.) | Management and Supervision | 57 | YAP J.B.H.; TAN S.M. (2021). Investigating Rework: Insights from the Malaysian Construction Industry. ASM Sci. J.. Vol. 14. Iss. UNKNOWN. doi: https://doi.org/10.32802/asmscj.2020.636
Implies a lack of effective planning—including scheduling, resource allocation, and pre-construction coordination. (Not further elaborated.) | Time & Planning | 57 | YAP J.B.H.; TAN S.M. (2021). Investigating Rework: Insights from the Malaysian Construction Industry. ASM Sci. J.. Vol. 14. Iss. UNKNOWN. doi: https://doi.org/10.32802/asmscj.2020.636
Inadequate exchange of information among project stakeholders, leading to misunderstandings and errors. (Definition inferred from context.) | Communication | 57 | YAP J.B.H.; TAN S.M. (2021). Investigating Rework: Insights from the Malaysian Construction Industry. ASM Sci. J.. Vol. 14. Iss. UNKNOWN. doi: https://doi.org/10.32802/asmscj.2020.636
Refers to modifications in the design—often due to unclear initial designs or client-driven changes—that necessitate rework. (Not elaborated in detail.) | Design | 57 | YAP J.B.H.; TAN S.M. (2021). Investigating Rework: Insights from the Malaysian Construction Industry. ASM Sci. J.. Vol. 14. Iss. UNKNOWN. doi: https://doi.org/10.32802/asmscj.2020.636
Indicates ineffective oversight and coordination of subcontractors that results in errors and rework. (Not explicitly defined beyond the ranking.) | Contractor Selection & Performance | 57 | YAP J.B.H.; TAN S.M. (2021). Investigating Rework: Insights from the Malaysian Construction Industry. ASM Sci. J.. Vol. 14. Iss. UNKNOWN. doi: https://doi.org/10.32802/asmscj.2020.636
Errors or omissions in design documents, poor coordination between disciplines causing conflicts (e.g. M&E vs. architectural or structural design). | Design | 59 | ZHANG S.; DUAN H.; ZHAO X.; XIA B.; FENG Y.; GALVIN S. (2021). Learning on rework management of construction projects: a case study. Int. J. Constr. Manage.. Vol. 21. Iss. 3. doi: https://doi.org/10.1080/15623599.2018.1521361
Inadequate storage and handling of materials leading to deterioration (e.g. floor coating material exposed to low temperatures). | Material Resources | 59 | ZHANG S.; DUAN H.; ZHAO X.; XIA B.; FENG Y.; GALVIN S. (2021). Learning on rework management of construction projects: a case study. Int. J. Constr. Manage.. Vol. 21. Iss. 3. doi: https://doi.org/10.1080/15623599.2018.1521361
Lack of skilled craftsmanship in executing specialized tasks (e.g. cutting and sealing piping) resulting in failures such as pipe explosions. | Contractor Selection & Performance | 59 | ZHANG S.; DUAN H.; ZHAO X.; XIA B.; FENG Y.; GALVIN S. (2021). Learning on rework management of construction projects: a case study. Int. J. Constr. Manage.. Vol. 21. Iss. 3. doi: https://doi.org/10.1080/15623599.2018.1521361
Inadequate information flow between parties leading to misunderstandings – such as using incorrect drawings or ordering the wrong materials. | Communication | 59 | ZHANG S.; DUAN H.; ZHAO X.; XIA B.; FENG Y.; GALVIN S. (2021). Learning on rework management of construction projects: a case study. Int. J. Constr. Manage.. Vol. 21. Iss. 3. doi: https://doi.org/10.1080/15623599.2018.1521361
Aggressive cost-saving measures that compromise quality, resulting in structural issues (e.g. uneven settlement of concrete floor). | Financial Constraints | 59 | ZHANG S.; DUAN H.; ZHAO X.; XIA B.; FENG Y.; GALVIN S. (2021). Learning on rework management of construction projects: a case study. Int. J. Constr. Manage.. Vol. 21. Iss. 3. doi: https://doi.org/10.1080/15623599.2018.1521361
Lack of knowledge regarding local regulatory standards and qualification requirements, leading to repeated permit applications. | Legal & Regulatory | 59 | ZHANG S.; DUAN H.; ZHAO X.; XIA B.; FENG Y.; GALVIN S. (2021). Learning on rework management of construction projects: a case study. Int. J. Constr. Manage.. Vol. 21. Iss. 3. doi: https://doi.org/10.1080/15623599.2018.1521361
Inadequate safeguarding of installed components leading to physical damage (e.g. deformation of facade cladding panels). | Material Resources | 59 | ZHANG S.; DUAN H.; ZHAO X.; XIA B.; FENG Y.; GALVIN S. (2021). Learning on rework management of construction projects: a case study. Int. J. Constr. Manage.. Vol. 21. Iss. 3. doi: https://doi.org/10.1080/15623599.2018.1521361
Insufficient experience, training, or mentorship among team members that leads to errors or omissions in design. | Human Resources | 60 | WOO J.; O'CONNOR J.T. (2021). Causal Factors for Engineering Design Defects and Their Impacts. Pract Period Struct Des Constr. Vol. 26. Iss. 2. doi: https://doi.org/10.1061/(ASCE)SC.1943-5576.0000562
Not having an adequate number of skilled personnel to complete design tasks effectively. | Human Resources | 60 | WOO J.; O'CONNOR J.T. (2021). Causal Factors for Engineering Design Defects and Their Impacts. Pract Period Struct Des Constr. Vol. 26. Iss. 2. doi: https://doi.org/10.1061/(ASCE)SC.1943-5576.0000562
Inadequate training and professional development resulting in a workforce that is ill-prepared to meet design requirements. | Human Resources | 60 | WOO J.; O'CONNOR J.T. (2021). Causal Factors for Engineering Design Defects and Their Impacts. Pract Period Struct Des Constr. Vol. 26. Iss. 2. doi: https://doi.org/10.1061/(ASCE)SC.1943-5576.0000562
Inadequate establishment and adherence to standardized design procedures, resulting in inconsistent or error-prone deliverables. | Design | 60 | WOO J.; O'CONNOR J.T. (2021). Causal Factors for Engineering Design Defects and Their Impacts. Pract Period Struct Des Constr. Vol. 26. Iss. 2. doi: https://doi.org/10.1061/(ASCE)SC.1943-5576.0000562
Required alterations to the original design or scope—typically formalized as change orders—that modify planned work. | Client-Driven Influences | 61 | LOVE P.E.D.; MATTHEWS J.; FANG W. (2020). Rework in Construction: A Focus on Error and Violation. J Constr Eng Manage. Vol. 146. Iss. 9. doi: https://doi.org/10.1061/(ASCE)CO.1943-7862.0001901
Failures to include necessary elements in the design, leading to errors when issues are discovered later. | Design | 61 | LOVE P.E.D.; MATTHEWS J.; FANG W. (2020). Rework in Construction: A Focus on Error and Violation. J Constr Eng Manage. Vol. 146. Iss. 9. doi: https://doi.org/10.1061/(ASCE)CO.1943-7862.0001901
A prevailing managerial mindset that emphasizes preventing rework by focusing on what went wrong and who is to blame. | Management and Supervision | 61 | LOVE P.E.D.; MATTHEWS J.; FANG W. (2020). Rework in Construction: A Focus on Error and Violation. J Constr Eng Manage. Vol. 146. Iss. 9. doi: https://doi.org/10.1061/(ASCE)CO.1943-7862.0001901
Leaders who adopt a top–down, blame-focused approach that hinders open communication and error reporting. | Management and Supervision | 62 | LOVE P.E.D. (2020). Creating a mindfulness to learn from errors: Enablers of rework containment and reduction in construction. Dev. Built. Environ.. Vol. 1. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.dibe.2019.100001
A lack of organizational norms, values, and practices that encourage learning from mistakes and sharing error-related information. | Management and Supervision | 62 | LOVE P.E.D. (2020). Creating a mindfulness to learn from errors: Enablers of rework containment and reduction in construction. Dev. Built. Environ.. Vol. 1. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.dibe.2019.100001
A mindset focused on preventing errors by assigning blame rather than exploring root causes and fostering improvement. | Management and Supervision | 62 | LOVE P.E.D. (2020). Creating a mindfulness to learn from errors: Enablers of rework containment and reduction in construction. Dev. Built. Environ.. Vol. 1. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.dibe.2019.100001
Inherent human limitations—such as forgetfulness, inattention, poor motivation, carelessness, negligence, and even recklessness—that result in errors. | Human Resources | 62 | LOVE P.E.D. (2020). Creating a mindfulness to learn from errors: Enablers of rework containment and reduction in construction. Dev. Built. Environ.. Vol. 1. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.dibe.2019.100001
Strategic and operational decisions that, intentionally or not, create latent conditions for errors by focusing on short-term gains or by neglecting systemic issues. | Management and Supervision | 62 | LOVE P.E.D. (2020). Creating a mindfulness to learn from errors: Enablers of rework containment and reduction in construction. Dev. Built. Environ.. Vol. 1. Iss. UNKNOWN. doi: https://doi.org/10.1016/j.dibe.2019.100001
Late delivery, defective materials, difficulty in installation, or delivery of the wrong type of materials. | Material Resources | 65 | BALOUCHI M.; GHOLHAKI M.; NIOUSHA A. (2019). Reworks causes and related costs in construction: case of Parand mass housing project in Iran. Int. J. Qual. Reliab. Manage.. Vol. 36. Iss. 8. doi: https://doi.org/10.1108/IJQRM-06-2018-0155
Ambiguous and inadequately defined management procedures, inappropriate tools/techniques, and sequencing that causes interference among activities. | Management and Supervision | 65 | BALOUCHI M.; GHOLHAKI M.; NIOUSHA A. (2019). Reworks causes and related costs in construction: case of Parand mass housing project in Iran. Int. J. Qual. Reliab. Manage.. Vol. 36. Iss. 8. doi: https://doi.org/10.1108/IJQRM-06-2018-0155
Lack of knowledge, carelessness, inadequate supervision, low skill levels, and poor material usage among sub-contractors. | Contractor Selection & Performance | 65 | BALOUCHI M.; GHOLHAKI M.; NIOUSHA A. (2019). Reworks causes and related costs in construction: case of Parand mass housing project in Iran. Int. J. Qual. Reliab. Manage.. Vol. 36. Iss. 8. doi: https://doi.org/10.1108/IJQRM-06-2018-0155
Inadequate constructability in the design or misinterpretation of the design intent by the execution team; often due to poor communication between designers and executors. | Design | 65 | BALOUCHI M.; GHOLHAKI M.; NIOUSHA A. (2019). Reworks causes and related costs in construction: case of Parand mass housing project in Iran. Int. J. Qual. Reliab. Manage.. Vol. 36. Iss. 8. doi: https://doi.org/10.1108/IJQRM-06-2018-0155
Lack of effective, proactive monitoring and quality control; supervision done solely by quality control staff without pre-execution checks. | Management and Supervision | 65 | BALOUCHI M.; GHOLHAKI M.; NIOUSHA A. (2019). Reworks causes and related costs in construction: case of Parand mass housing project in Iran. Int. J. Qual. Reliab. Manage.. Vol. 36. Iss. 8. doi: https://doi.org/10.1108/IJQRM-06-2018-0155
Ambiguous contract documentation that fails to clearly define the scope, expectations, and penalties for low quality work. | Documentation & Information Management | 65 | BALOUCHI M.; GHOLHAKI M.; NIOUSHA A. (2019). Reworks causes and related costs in construction: case of Parand mass housing project in Iran. Int. J. Qual. Reliab. Manage.. Vol. 36. Iss. 8. doi: https://doi.org/10.1108/IJQRM-06-2018-0155
Subcontractors engage in unsafe or shortcut practices (e.g., “not getting it right the first time”) driven by pressure to save time and cost. | Contractor Selection & Performance | 68 | LOVE P.E.D.; TEO P.; ACKERMANN F.; SMITH J.; ALEXANDER J.; PALANEESWARAN E.; MORRISON J. (2018). Reduce rework, improve safety: an empirical inquiry into the precursors to error in construction. Prod Plann Control. Vol. 29. Iss. 5. doi: https://doi.org/10.1080/09537287.2018.1424961
Excessive pressure to meet tight, often overly optimistic project schedules that forces workers to cut corners. | Time & Planning | 68 | LOVE P.E.D.; TEO P.; ACKERMANN F.; SMITH J.; ALEXANDER J.; PALANEESWARAN E.; MORRISON J. (2018). Reduce rework, improve safety: an empirical inquiry into the precursors to error in construction. Prod Plann Control. Vol. 29. Iss. 5. doi: https://doi.org/10.1080/09537287.2018.1424961
Insufficient prioritization of quality—where senior management neglects to enforce or value quality processes, resulting in inconsistent policies and under-reporting of errors. | Management and Supervision | 68 | LOVE P.E.D.; TEO P.; ACKERMANN F.; SMITH J.; ALEXANDER J.; PALANEESWARAN E.; MORRISON J. (2018). Reduce rework, improve safety: an empirical inquiry into the precursors to error in construction. Prod Plann Control. Vol. 29. Iss. 5. doi: https://doi.org/10.1080/09537287.2018.1424961
Inadequate oversight whereby supervisors fail to monitor or check work effectively, allowing errors to persist and escalate into rework. | Management and Supervision | 68 | LOVE P.E.D.; TEO P.; ACKERMANN F.; SMITH J.; ALEXANDER J.; PALANEESWARAN E.; MORRISON J. (2018). Reduce rework, improve safety: an empirical inquiry into the precursors to error in construction. Prod Plann Control. Vol. 29. Iss. 5. doi: https://doi.org/10.1080/09537287.2018.1424961
Deficiencies in communication among project team members (e.g., between designers, contractors, and owners) that result in misunderstandings and errors. | Communication | 68 | LOVE P.E.D.; TEO P.; ACKERMANN F.; SMITH J.; ALEXANDER J.; PALANEESWARAN E.; MORRISON J. (2018). Reduce rework, improve safety: an empirical inquiry into the precursors to error in construction. Prod Plann Control. Vol. 29. Iss. 5. doi: https://doi.org/10.1080/09537287.2018.1424961
Mistakes stemming from cognitive biases or heuristic shortcuts taken by individuals when making decisions under stress. | Human Resources | 68 | LOVE P.E.D.; TEO P.; ACKERMANN F.; SMITH J.; ALEXANDER J.; PALANEESWARAN E.; MORRISON J. (2018). Reduce rework, improve safety: an empirical inquiry into the precursors to error in construction. Prod Plann Control. Vol. 29. Iss. 5. doi: https://doi.org/10.1080/09537287.2018.1424961
An absence of structured processes to detect, learn from, and recover from errors; a punitive “zero vision” discourages reporting and learning from mistakes. | Management and Supervision | 68 | LOVE P.E.D.; TEO P.; ACKERMANN F.; SMITH J.; ALEXANDER J.; PALANEESWARAN E.; MORRISON J. (2018). Reduce rework, improve safety: an empirical inquiry into the precursors to error in construction. Prod Plann Control. Vol. 29. Iss. 5. doi: https://doi.org/10.1080/09537287.2018.1424961
The inefficient decision-making process of the client—for example, a reluctance to promptly hire specialty contractors—which delays required work and triggers rework. | Client-Driven Influences | 72 | ABDELBARY M.; EDKINS A.; DORRA E.M. (2020). Reducing crr in fast-track projects through bim. J. Inf. Technol. Constr.. Vol. 25. Iss. UNKNOWN. doi: https://doi.org/10.36680/j.itcon.2020.009
The act of the client changing the materials used—often after work has begun—which forces rework to match new specifications. | Client-Driven Influences | 72 | ABDELBARY M.; EDKINS A.; DORRA E.M. (2020). Reducing crr in fast-track projects through bim. J. Inf. Technol. Constr.. Vol. 25. Iss. UNKNOWN. doi: https://doi.org/10.36680/j.itcon.2020.009
Financial constraints or difficulties faced by the client that force budget reductions or change orders. | Financial Constraints | 72 | ABDELBARY M.; EDKINS A.; DORRA E.M. (2020). Reducing crr in fast-track projects through bim. J. Inf. Technol. Constr.. Vol. 25. Iss. UNKNOWN. doi: https://doi.org/10.36680/j.itcon.2020.009
Changes initiated by the client in project plans or scope after work has commenced, thereby necessitating rework. | Client-Driven Influences | 72 | ABDELBARY M.; EDKINS A.; DORRA E.M. (2020). Reducing crr in fast-track projects through bim. J. Inf. Technol. Constr.. Vol. 25. Iss. UNKNOWN. doi: https://doi.org/10.36680/j.itcon.2020.009
Deficiencies in the communication flow between the client and the design team that result in errors and omissions in documentation. | Communication | 72 | ABDELBARY M.; EDKINS A.; DORRA E.M. (2020). Reducing crr in fast-track projects through bim. J. Inf. Technol. Constr.. Vol. 25. Iss. UNKNOWN. doi: https://doi.org/10.36680/j.itcon.2020.009
The absence of clear and unambiguous project objectives from the client, causing redefinition and subsequent rework. | Client-Driven Influences | 72 | ABDELBARY M.; EDKINS A.; DORRA E.M. (2020). Reducing crr in fast-track projects through bim. J. Inf. Technol. Constr.. Vol. 25. Iss. UNKNOWN. doi: https://doi.org/10.36680/j.itcon.2020.009
The client’s insufficient experience or expertise, which leads to frequent changes in decisions during project execution. | Client-Driven Influences | 72 | ABDELBARY M.; EDKINS A.; DORRA E.M. (2020). Reducing crr in fast-track projects through bim. J. Inf. Technol. Constr.. Vol. 25. Iss. UNKNOWN. doi: https://doi.org/10.36680/j.itcon.2020.009
Project managers deliberately ignore or amend standardized, organization‐wide procedures to suit their own goals and devalue the recording/learning from non‐conformances. | Management and Supervision | 77 | LOVE P.E.D.; SMITH J.; ACKERMANN F.; IRANI Z. (2019). Making sense of rework and its unintended consequence in projects: The emergence of uncomfortable knowledge. Int. J. Proj. Manage.. Vol. 37. Iss. 3. doi: https://doi.org/10.1016/j.ijproman.2019.02.004
Inadequate or ineffective controls and routines that fail to contain or reduce rework. | Management and Supervision | 77 | LOVE P.E.D.; SMITH J.; ACKERMANN F.; IRANI Z. (2019). Making sense of rework and its unintended consequence in projects: The emergence of uncomfortable knowledge. Int. J. Proj. Manage.. Vol. 37. Iss. 3. doi: https://doi.org/10.1016/j.ijproman.2019.02.004
A lack of an environment that supports open reporting and collective learning, leading workers to conceal errors. | Safety Culture | 77 | LOVE P.E.D.; SMITH J.; ACKERMANN F.; IRANI Z. (2019). Making sense of rework and its unintended consequence in projects: The emergence of uncomfortable knowledge. Int. J. Proj. Manage.. Vol. 37. Iss. 3. doi: https://doi.org/10.1016/j.ijproman.2019.02.004
Subcontractors engage in deceptive practices (e.g., sourcing non‐compliant, cheaper components) to improve margins and expedite work. | Contractor Selection & Performance | 77 | LOVE P.E.D.; SMITH J.; ACKERMANN F.; IRANI Z. (2019). Making sense of rework and its unintended consequence in projects: The emergence of uncomfortable knowledge. Int. J. Proj. Manage.. Vol. 37. Iss. 3. doi: https://doi.org/10.1016/j.ijproman.2019.02.004
Poor planning and sequencing of tasks leading to errors (e.g., mixing incompatible materials, misallocation of equipment). | Time & Planning | 77 | LOVE P.E.D.; SMITH J.; ACKERMANN F.; IRANI Z. (2019). Making sense of rework and its unintended consequence in projects: The emergence of uncomfortable knowledge. Int. J. Proj. Manage.. Vol. 37. Iss. 3. doi: https://doi.org/10.1016/j.ijproman.2019.02.004
Errors arising from individual factors such as overwork, boredom, fatigue, or misapplication of standard routines. | Human Resources | 77 | LOVE P.E.D.; SMITH J.; ACKERMANN F.; IRANI Z. (2019). Making sense of rework and its unintended consequence in projects: The emergence of uncomfortable knowledge. Int. J. Proj. Manage.. Vol. 37. Iss. 3. doi: https://doi.org/10.1016/j.ijproman.2019.02.004
Pressure imposed by strict cost and schedule requirements that may force operatives to cut corners, resulting in defects. | Financial Constraints | 78 | SHAHPARVARI M.; FONG D. (2018). The review of rework causes and costs in housing construction supply chain. IGLC - Proc. Annu. Conf. Int. Group for Lean Constr.: Evol. Lean Constr. Towards Mature Prod. Manag. Across Cult. Front.. Vol. 2. Iss. UNKNOWN. doi: https://doi.org/10.24928/2018/0514
Delay in incorporating end-user feedback during design and planning, which leads to misaligned expectations. | Client-Driven Influences | 78 | SHAHPARVARI M.; FONG D. (2018). The review of rework causes and costs in housing construction supply chain. IGLC - Proc. Annu. Conf. Int. Group for Lean Constr.: Evol. Lean Constr. Towards Mature Prod. Manag. Across Cult. Front.. Vol. 2. Iss. UNKNOWN. doi: https://doi.org/10.24928/2018/0514
Slow client decisions that postpone necessary changes, thereby causing errors to persist into later stages. | Client-Driven Influences | 78 | SHAHPARVARI M.; FONG D. (2018). The review of rework causes and costs in housing construction supply chain. IGLC - Proc. Annu. Conf. Int. Group for Lean Constr.: Evol. Lean Constr. Towards Mature Prod. Manag. Across Cult. Front.. Vol. 2. Iss. UNKNOWN. doi: https://doi.org/10.24928/2018/0514
Poor integration and communication among various supply chain actors leading to unaligned processes and errors. | Communication | 78 | SHAHPARVARI M.; FONG D. (2018). The review of rework causes and costs in housing construction supply chain. IGLC - Proc. Annu. Conf. Int. Group for Lean Constr.: Evol. Lean Constr. Towards Mature Prod. Manag. Across Cult. Front.. Vol. 2. Iss. UNKNOWN. doi: https://doi.org/10.24928/2018/0514
Inadequate skills, knowledge, or motivation among workers that result in incorrect execution of tasks. | Human Resources | 78 | SHAHPARVARI M.; FONG D. (2018). The review of rework causes and costs in housing construction supply chain. IGLC - Proc. Annu. Conf. Int. Group for Lean Constr.: Evol. Lean Constr. Towards Mature Prod. Manag. Across Cult. Front.. Vol. 2. Iss. UNKNOWN. doi: https://doi.org/10.24928/2018/0514
Ineffective design processes including insufficient design reviews that lead to errors in production. | Design | 78 | SHAHPARVARI M.; FONG D. (2018). The review of rework causes and costs in housing construction supply chain. IGLC - Proc. Annu. Conf. Int. Group for Lean Constr.: Evol. Lean Constr. Towards Mature Prod. Manag. Across Cult. Front.. Vol. 2. Iss. UNKNOWN. doi: https://doi.org/10.24928/2018/0514
Ineffective leadership and poor communication that hinder timely error detection and correction. | Communication | 78 | SHAHPARVARI M.; FONG D. (2018). The review of rework causes and costs in housing construction supply chain. IGLC - Proc. Annu. Conf. Int. Group for Lean Constr.: Evol. Lean Constr. Towards Mature Prod. Manag. Across Cult. Front.. Vol. 2. Iss. UNKNOWN. doi: https://doi.org/10.24928/2018/0514
Inadequate planning and scheduling that cause overlaps, conflicts, or delays in detecting errors. | Time & Planning | 78 | SHAHPARVARI M.; FONG D. (2018). The review of rework causes and costs in housing construction supply chain. IGLC - Proc. Annu. Conf. Int. Group for Lean Constr.: Evol. Lean Constr. Towards Mature Prod. Manag. Across Cult. Front.. Vol. 2. Iss. UNKNOWN. doi: https://doi.org/10.24928/2018/0514
Problems in procuring or supplying quality materials and equipment that lead to defects. | Material Resources | 78 | SHAHPARVARI M.; FONG D. (2018). The review of rework causes and costs in housing construction supply chain. IGLC - Proc. Annu. Conf. Int. Group for Lean Constr.: Evol. Lean Constr. Towards Mature Prod. Manag. Across Cult. Front.. Vol. 2. Iss. UNKNOWN. doi: https://doi.org/10.24928/2018/0514
A highly fragmented housing supply chain—with numerous small subcontractors—that leads to a lack of coordinated quality control. | Contractor Selection & Performance | 78 | SHAHPARVARI M.; FONG D. (2018). The review of rework causes and costs in housing construction supply chain. IGLC - Proc. Annu. Conf. Int. Group for Lean Constr.: Evol. Lean Constr. Towards Mature Prod. Manag. Across Cult. Front.. Vol. 2. Iss. UNKNOWN. doi: https://doi.org/10.24928/2018/0514
Absence of strong, trust-based relationships between small-to-medium enterprises (SMEs) and larger contractors, hindering effective collaboration. | Contractor Selection & Performance | 78 | SHAHPARVARI M.; FONG D. (2018). The review of rework causes and costs in housing construction supply chain. IGLC - Proc. Annu. Conf. Int. Group for Lean Constr.: Evol. Lean Constr. Towards Mature Prod. Manag. Across Cult. Front.. Vol. 2. Iss. UNKNOWN. doi: https://doi.org/10.24928/2018/0514
Ineffective or unsupportive management that fails to enforce quality controls, proper coordination, and clear decision‐making. | Management and Supervision | 80 | OYEWOBI L.O.; ABIOLA-FALEMU O.; IBIRONKE O.T. (2016). The impact of rework and organisational culture on project delivery. J. Eng. Des. Technol.. Vol. 14. Iss. 2. doi: https://doi.org/10.1108/JEDT-05-2013-0038
Lack of collaboration and coordination among team members, resulting in misaligned efforts and increased errors. | Communication | 80 | OYEWOBI L.O.; ABIOLA-FALEMU O.; IBIRONKE O.T. (2016). The impact of rework and organisational culture on project delivery. J. Eng. Des. Technol.. Vol. 14. Iss. 2. doi: https://doi.org/10.1108/JEDT-05-2013-0038
Inadequate exchange and misinterpretation of information among stakeholders, leading to errors and rework. | Communication | 80 | OYEWOBI L.O.; ABIOLA-FALEMU O.; IBIRONKE O.T. (2016). The impact of rework and organisational culture on project delivery. J. Eng. Des. Technol.. Vol. 14. Iss. 2. doi: https://doi.org/10.1108/JEDT-05-2013-0038
Tight timelines in project management create a high-pressure environment where essential activities are hurried, often skipping key validation and coordination phases. | Time & Planning | 80 | OYEWOBI L.O.; ABIOLA-FALEMU O.; IBIRONKE O.T. (2016). The impact of rework and organisational culture on project delivery. J. Eng. Des. Technol.. Vol. 14. Iss. 2. doi: https://doi.org/10.1108/JEDT-05-2013-0038
Unplanned disruptions or interruptions in the workflow that cause deviations from planned activities. | External Influences | 80 | OYEWOBI L.O.; ABIOLA-FALEMU O.; IBIRONKE O.T. (2016). The impact of rework and organisational culture on project delivery. J. Eng. Des. Technol.. Vol. 14. Iss. 2. doi: https://doi.org/10.1108/JEDT-05-2013-0038
A low level of employee drive that results in reduced diligence and quality, increasing errors and the need to redo work. | Human Resources | 80 | OYEWOBI L.O.; ABIOLA-FALEMU O.; IBIRONKE O.T. (2016). The impact of rework and organisational culture on project delivery. J. Eng. Des. Technol.. Vol. 14. Iss. 2. doi: https://doi.org/10.1108/JEDT-05-2013-0038
Changes or deviations from the original work plan or design—often due to ambiguous instructions or client-driven modifications—that require work to be redone. | Client-Driven Influences | 80 | OYEWOBI L.O.; ABIOLA-FALEMU O.; IBIRONKE O.T. (2016). The impact of rework and organisational culture on project delivery. J. Eng. Des. Technol.. Vol. 14. Iss. 2. doi: https://doi.org/10.1108/JEDT-05-2013-0038
Inadequate or misinterpreted communication of project instructions that contributes to rework (e.g. as noted by Ye et al., 2014). | Communication | 84 | LOVE P.E.D.; EDWARDS D.J.; SMITH J. (2016). Rework causation: Emergent theoretical insights and implications for research. J Constr Eng Manage. Vol. 142. Iss. 6. doi: https://doi.org/10.1061/(ASCE)CO.1943-7862.0001114
Errors stemming from human factors—mistakes (rule- or knowledge-based), slips, lapses of attention, and acts of omission/commission. | Human Resources | 84 | LOVE P.E.D.; EDWARDS D.J.; SMITH J. (2016). Rework causation: Emergent theoretical insights and implications for research. J Constr Eng Manage. Vol. 142. Iss. 6. doi: https://doi.org/10.1061/(ASCE)CO.1943-7862.0001114
The tendency for project team members to hide errors or rework to avoid blame, thereby allowing problems to persist. | Management and Supervision | 84 | LOVE P.E.D.; EDWARDS D.J.; SMITH J. (2016). Rework causation: Emergent theoretical insights and implications for research. J Constr Eng Manage. Vol. 142. Iss. 6. doi: https://doi.org/10.1061/(ASCE)CO.1943-7862.0001114
Errors arising from poor contract documentation, limited design documentation time, inadequate design audits, and insufficient coordination between design and construction. | Documentation & Information Management | 84 | LOVE P.E.D.; EDWARDS D.J.; SMITH J. (2016). Rework causation: Emergent theoretical insights and implications for research. J Constr Eng Manage. Vol. 142. Iss. 6. doi: https://doi.org/10.1061/(ASCE)CO.1943-7862.0001114
Underreporting or misrepresenting project issues—driven by competitive pressures and a desire to maximize margins—which can lead to errors that later require rework. | Management and Supervision | 84 | LOVE P.E.D.; EDWARDS D.J.; SMITH J. (2016). Rework causation: Emergent theoretical insights and implications for research. J Constr Eng Manage. Vol. 142. Iss. 6. doi: https://doi.org/10.1061/(ASCE)CO.1943-7862.0001114
Poor or ambiguous process management and low-quality construction technologies that indirectly lead to rework. | Material Resources | 84 | LOVE P.E.D.; EDWARDS D.J.; SMITH J. (2016). Rework causation: Emergent theoretical insights and implications for research. J Constr Eng Manage. Vol. 142. Iss. 6. doi: https://doi.org/10.1061/(ASCE)CO.1943-7862.0001114
Poor on‐site management including inadequate control over material and equipment quality and low skill levels among workers (many migrant workers with limited formal education). | Contractor Selection & Performance | 85 | YE G.; JIN Z.; XIA B.; SKITMORE M. (2015). Analyzing causes for reworks in construction projects in China. J Manage Eng. Vol. 31. Iss. 6. doi: https://doi.org/10.1061/(ASCE)ME.1943-5479.0000347
Adverse natural conditions (extreme weather, earthquakes, floods), end-user requirement changes, and socio-cultural/legal/market influences. | External Influences | 85 | YE G.; JIN Z.; XIA B.; SKITMORE M. (2015). Analyzing causes for reworks in construction projects in China. J Manage Eng. Vol. 31. Iss. 6. doi: https://doi.org/10.1061/(ASCE)ME.1943-5479.0000347
Inadequate negotiation and ambiguous contract documentation that lead to payment issues and unclear work scopes. | Documentation & Information Management | 85 | YE G.; JIN Z.; XIA B.; SKITMORE M. (2015). Analyzing causes for reworks in construction projects in China. J Manage Eng. Vol. 31. Iss. 6. doi: https://doi.org/10.1061/(ASCE)ME.1943-5479.0000347
Poor management of subcontractors due to lack of proper qualifications and ineffective communication among subcontractors. | Contractor Selection & Performance | 85 | YE G.; JIN Z.; XIA B.; SKITMORE M. (2015). Analyzing causes for reworks in construction projects in China. J Manage Eng. Vol. 31. Iss. 6. doi: https://doi.org/10.1061/(ASCE)ME.1943-5479.0000347
Compromised design quality resulting from rushed submissions, fragmented design teams, poor communication, and the limitations of the traditional design-bid-build system. | Design | 85 | YE G.; JIN Z.; XIA B.; SKITMORE M. (2015). Analyzing causes for reworks in construction projects in China. J Manage Eng. Vol. 31. Iss. 6. doi: https://doi.org/10.1061/(ASCE)ME.1943-5479.0000347
Ineffective communication structures and limited use of information and communication technologies (ICT) leading to misunderstandings and conflicts. | Communication | 85 | YE G.; JIN Z.; XIA B.; SKITMORE M. (2015). Analyzing causes for reworks in construction projects in China. J Manage Eng. Vol. 31. Iss. 6. doi: https://doi.org/10.1061/(ASCE)ME.1943-5479.0000347
Inadequate adherence to established project management processes, including “three-way projects” (where surveying, designing, and constructing occur concurrently) leading to continuous changes and reworks. | Management and Supervision | 85 | YE G.; JIN Z.; XIA B.; SKITMORE M. (2015). Analyzing causes for reworks in construction projects in China. J Manage Eng. Vol. 31. Iss. 6. doi: https://doi.org/10.1061/(ASCE)ME.1943-5479.0000347
Projects under time pressure often neglect important quality and coordination practices due to the demand for quick completion under unrealistic deadlines. | Time & Planning | 88 | LOVE P.E.D.; EDWARDS D.J.; IRANI Z.; FORCADA N. (2014). The latent causes of rework in floating production storage and offloading projects. J. Civ. Eng. Manage.. Vol. 20. Iss. 3. doi: https://doi.org/10.3846/13923730.2013.802725
Ineffective coordination and integration among different project components (e.g., vessel, topsides, subsea systems). | Management and Supervision | 88 | LOVE P.E.D.; EDWARDS D.J.; IRANI Z.; FORCADA N. (2014). The latent causes of rework in floating production storage and offloading projects. J. Civ. Eng. Manage.. Vol. 20. Iss. 3. doi: https://doi.org/10.3846/13923730.2013.802725
Inadequate design—such as errors in process facility details—that results in performance issues (e.g., excessive gas flare, underproduction). | Design | 88 | LOVE P.E.D.; EDWARDS D.J.; IRANI Z.; FORCADA N. (2014). The latent causes of rework in floating production storage and offloading projects. J. Civ. Eng. Manage.. Vol. 20. Iss. 3. doi: https://doi.org/10.3846/13923730.2013.802725
Insufficient training of personnel and inadequate resource allocation that increases the likelihood of operational errors. | Human Resources | 88 | LOVE P.E.D.; EDWARDS D.J.; IRANI Z.; FORCADA N. (2014). The latent causes of rework in floating production storage and offloading projects. J. Civ. Eng. Manage.. Vol. 20. Iss. 3. doi: https://doi.org/10.3846/13923730.2013.802725
Adoption of new technology without adequate testing or justification, resulting in performance and reliability issues. | Technology Utilization | 88 | LOVE P.E.D.; EDWARDS D.J.; IRANI Z.; FORCADA N. (2014). The latent causes of rework in floating production storage and offloading projects. J. Civ. Eng. Manage.. Vol. 20. Iss. 3. doi: https://doi.org/10.3846/13923730.2013.802725
Awarding contracts based on the lowest bid, which limits error margins and compromises quality. | Contractor Selection & Performance | 88 | LOVE P.E.D.; EDWARDS D.J.; IRANI Z.; FORCADA N. (2014). The latent causes of rework in floating production storage and offloading projects. J. Civ. Eng. Manage.. Vol. 20. Iss. 3. doi: https://doi.org/10.3846/13923730.2013.802725
Unsafe acts (slips, lapses, deliberate rule violations) by individuals that occur due to underlying systemic deficiencies. | Safety Culture | 88 | LOVE P.E.D.; EDWARDS D.J.; IRANI Z.; FORCADA N. (2014). The latent causes of rework in floating production storage and offloading projects. J. Civ. Eng. Manage.. Vol. 20. Iss. 3. doi: https://doi.org/10.3846/13923730.2013.802725
The practice of awarding contracts based solely on the lowest bid, which can compromise quality and long‐term relationships. | Contractor Selection & Performance | 89 | EMUZE F.; SMALLWOOD J.; BEETGE W. (2014). Supply chain integration barriers in construction: Views from two south african projects. Proceedings of International Structural Engineering and Construction. Vol. 1. Iss. 1. doi: https://doi.org/10.14455/ISEC.res.2014.71
In environments where project schedules are compressed, time pressure forces a trade-off between speed and thoroughness, leading to missed opportunities for correction and review. | Time & Planning | 89 | EMUZE F.; SMALLWOOD J.; BEETGE W. (2014). Supply chain integration barriers in construction: Views from two south african projects. Proceedings of International Structural Engineering and Construction. Vol. 1. Iss. 1. doi: https://doi.org/10.14455/ISEC.res.2014.71
A lack of confidence and mutual belief among supply chain partners that undermines cooperation. | Contractor Selection & Performance | 89 | EMUZE F.; SMALLWOOD J.; BEETGE W. (2014). Supply chain integration barriers in construction: Views from two south african projects. Proceedings of International Structural Engineering and Construction. Vol. 1. Iss. 1. doi: https://doi.org/10.14455/ISEC.res.2014.71
Inadequate and opaque exchange of critical information among project participants. | Documentation & Information Management | 89 | EMUZE F.; SMALLWOOD J.; BEETGE W. (2014). Supply chain integration barriers in construction: Views from two south african projects. Proceedings of International Structural Engineering and Construction. Vol. 1. Iss. 1. doi: https://doi.org/10.14455/ISEC.res.2014.71
Insufficient recognition and valuing of individuals involved in the project, leading to adversarial attitudes. | Human Resources | 89 | EMUZE F.; SMALLWOOD J.; BEETGE W. (2014). Supply chain integration barriers in construction: Views from two south african projects. Proceedings of International Structural Engineering and Construction. Vol. 1. Iss. 1. doi: https://doi.org/10.14455/ISEC.res.2014.71
Insufficient dialogue and collaborative discussion between project partners during decision making. | Communication | 89 | EMUZE F.; SMALLWOOD J.; BEETGE W. (2014). Supply chain integration barriers in construction: Views from two south african projects. Proceedings of International Structural Engineering and Construction. Vol. 1. Iss. 1. doi: https://doi.org/10.14455/ISEC.res.2014.71
A conventional procurement approach that prioritizes lowest bid rather than overall value and quality. | Contractor Selection & Performance | 89 | EMUZE F.; SMALLWOOD J.; BEETGE W. (2014). Supply chain integration barriers in construction: Views from two south african projects. Proceedings of International Structural Engineering and Construction. Vol. 1. Iss. 1. doi: https://doi.org/10.14455/ISEC.res.2014.71
Limited adoption or ineffective integration of modern information and communication technologies within the supply chain. | Technology Utilization | 89 | EMUZE F.; SMALLWOOD J.; BEETGE W. (2014). Supply chain integration barriers in construction: Views from two south african projects. Proceedings of International Structural Engineering and Construction. Vol. 1. Iss. 1. doi: https://doi.org/10.14455/ISEC.res.2014.71
Changes in project scope initiated by the owner that alter design requirements and increase complexity. | Client-Driven Influences | 91 | FORCADA N.; GANGOLELLS M.; CASALS M.; MACARULLA M. (2017). Factors Affecting Rework Costs in Construction. J Constr Eng Manage. Vol. 143. Iss. 8. doi: https://doi.org/10.1061/(ASCE)CO.1943-7862.0001324
Mistakes, faults, or omissions in the design that lead to rework when the constructed product deviates from requirements. | Design | 91 | FORCADA N.; GANGOLELLS M.; CASALS M.; MACARULLA M. (2017). Factors Affecting Rework Costs in Construction. J Constr Eng Manage. Vol. 143. Iss. 8. doi: https://doi.org/10.1061/(ASCE)CO.1943-7862.0001324
Rushed design work resulting in inconsistencies and errors due to insufficient time for quality checks. | Design | 91 | FORCADA N.; GANGOLELLS M.; CASALS M.; MACARULLA M. (2017). Factors Affecting Rework Costs in Construction. J Constr Eng Manage. Vol. 143. Iss. 8. doi: https://doi.org/10.1061/(ASCE)CO.1943-7862.0001324
Over-reliance on outputs from IT applications for design decisions without adequate human validation. | Technology Utilization | 91 | FORCADA N.; GANGOLELLS M.; CASALS M.; MACARULLA M. (2017). Factors Affecting Rework Costs in Construction. J Constr Eng Manage. Vol. 143. Iss. 8. doi: https://doi.org/10.1061/(ASCE)CO.1943-7862.0001324
The geographical distance between the project site and the contractor’s headquarters, affecting managerial oversight and quality control. | Management and Supervision | 91 | FORCADA N.; GANGOLELLS M.; CASALS M.; MACARULLA M. (2017). Factors Affecting Rework Costs in Construction. J Constr Eng Manage. Vol. 143. Iss. 8. doi: https://doi.org/10.1061/(ASCE)CO.1943-7862.0001324
Missing elements in the contract documents that later require correction | Documentation & Information Management | 125 | LOVE P.E.D.; IRANI Z.; EDWARDS D.J. (2004). A rework reduction model for construction projects. IEEE Trans Eng Manage. Vol. 51. Iss. 4. doi: https://doi.org/10.1109/TEM.2004.835092
Mistakes or inaccuracies made in the preparation of contract documents | Documentation & Information Management | 125 | LOVE P.E.D.; IRANI Z.; EDWARDS D.J. (2004). A rework reduction model for construction projects. IEEE Trans Eng Manage. Vol. 51. Iss. 4. doi: https://doi.org/10.1109/TEM.2004.835092
Failure to properly implement or utilize quality management (QM) in the design process | Management and Supervision | 125 | LOVE P.E.D.; IRANI Z.; EDWARDS D.J. (2004). A rework reduction model for construction projects. IEEE Trans Eng Manage. Vol. 51. Iss. 4. doi: https://doi.org/10.1109/TEM.2004.835092
Allocating a fixed period to complete design tasks regardless of completeness | Time & Planning | 125 | LOVE P.E.D.; IRANI Z.; EDWARDS D.J. (2004). A rework reduction model for construction projects. IEEE Trans Eng Manage. Vol. 51. Iss. 4. doi: https://doi.org/10.1109/TEM.2004.835092
Design work that has not been fully developed when tender documents are issued | Design | 125 | LOVE P.E.D.; IRANI Z.; EDWARDS D.J. (2004). A rework reduction model for construction projects. IEEE Trans Eng Manage. Vol. 51. Iss. 4. doi: https://doi.org/10.1109/TEM.2004.835092
Lack of effective communication and collaboration among design professionals | Communication | 125 | LOVE P.E.D.; IRANI Z.; EDWARDS D.J. (2004). A rework reduction model for construction projects. IEEE Trans Eng Manage. Vol. 51. Iss. 4. doi: https://doi.org/10.1109/TEM.2004.835092
Ineffective allocation and scheduling of resources that leads to changes and redocumentation | Time & Planning | 125 | LOVE P.E.D.; IRANI Z.; EDWARDS D.J. (2004). A rework reduction model for construction projects. IEEE Trans Eng Manage. Vol. 51. Iss. 4. doi: https://doi.org/10.1109/TEM.2004.835092
Alterations or modifications made by the client (or occupier) after a process has been completed | Client-Driven Influences | 125 | LOVE P.E.D.; IRANI Z.; EDWARDS D.J. (2004). A rework reduction model for construction projects. IEEE Trans Eng Manage. Vol. 51. Iss. 4. doi: https://doi.org/10.1109/TEM.2004.835092
The practice of locking down the design scope to prevent changes, which may backfire if clients feel constrained | Design | 125 | LOVE P.E.D.; IRANI Z.; EDWARDS D.J. (2004). A rework reduction model for construction projects. IEEE Trans Eng Manage. Vol. 51. Iss. 4. doi: https://doi.org/10.1109/TEM.2004.835092
Failure to use IT tools effectively to manage design data and facilitate communication | Technology Utilization | 125 | LOVE P.E.D.; IRANI Z.; EDWARDS D.J. (2004). A rework reduction model for construction projects. IEEE Trans Eng Manage. Vol. 51. Iss. 4. doi: https://doi.org/10.1109/TEM.2004.835092
Errors stemming from inadequate knowledge, poor training, and carelessness or negligence in execution. | Human Resources | 131 | LOVE P.E.D.; EDWARDS D.J.; IRANI Z. (2008). Forensic project management: An exploratory examination of the causal behavior of design-induced rework. IEEE Trans Eng Manage. Vol. 55. Iss. 2. doi: https://doi.org/10.1109/TEM.2008.919677
Failure to fully understand and clearly communicate the client’s or end-user’s needs, leading to design changes and subsequent rework. | Communication | 131 | LOVE P.E.D.; EDWARDS D.J.; IRANI Z. (2008). Forensic project management: An exploratory examination of the causal behavior of design-induced rework. IEEE Trans Eng Manage. Vol. 55. Iss. 2. doi: https://doi.org/10.1109/TEM.2008.919677
Rushed design work forced by unrealistic schedules and low design fees that lead to fixed time allocations (“time boxing”) regardless of task completeness. | Time & Planning | 131 | LOVE P.E.D.; EDWARDS D.J.; IRANI Z. (2008). Forensic project management: An exploratory examination of the causal behavior of design-induced rework. IEEE Trans Eng Manage. Vol. 55. Iss. 2. doi: https://doi.org/10.1109/TEM.2008.919677
Lack of rigorous quality management practices that fail to detect or correct errors early in the design process. | Design | 131 | LOVE P.E.D.; EDWARDS D.J.; IRANI Z. (2008). Forensic project management: An exploratory examination of the causal behavior of design-induced rework. IEEE Trans Eng Manage. Vol. 55. Iss. 2. doi: https://doi.org/10.1109/TEM.2008.919677
Ineffective coordination and communication between different design disciplines (e.g., between architects and engineers), leading to inconsistent or conflicting outputs. | Communication | 131 | LOVE P.E.D.; EDWARDS D.J.; IRANI Z. (2008). Forensic project management: An exploratory examination of the causal behavior of design-induced rework. IEEE Trans Eng Manage. Vol. 55. Iss. 2. doi: https://doi.org/10.1109/TEM.2008.919677
Increased error likelihood due to physical and mental fatigue resulting from high workload and relentless schedule pressures. | Human Resources | 131 | LOVE P.E.D.; EDWARDS D.J.; IRANI Z. (2008). Forensic project management: An exploratory examination of the causal behavior of design-induced rework. IEEE Trans Eng Manage. Vol. 55. Iss. 2. doi: https://doi.org/10.1109/TEM.2008.919677
Elevated error rates caused by concurrent execution of multiple design tasks under tight cost constraints that force low fees and, in turn, demotivate staff. | Design | 131 | LOVE P.E.D.; EDWARDS D.J.; IRANI Z. (2008). Forensic project management: An exploratory examination of the causal behavior of design-induced rework. IEEE Trans Eng Manage. Vol. 55. Iss. 2. doi: https://doi.org/10.1109/TEM.2008.919677
Structural drawing missing critical dimension. | Design | -1 | Synthetic augmentation via LLM
Architectural door swing conflicts with egress clearance. | Design | -1 | Synthetic augmentation via LLM
HVAC duct routing clashes with primary beam as designed. | Design | -1 | Synthetic augmentation via LLM
Rebar lap length specified below code minimum. | Design | -1 | Synthetic augmentation via LLM
Wet-area floor slopes to drain omitted in plan. | Design | -1 | Synthetic augmentation via LLM
Façade panel module inconsistent with structural grid. | Design | -1 | Synthetic augmentation via LLM
Equipment loads underestimated in foundation design. | Design | -1 | Synthetic augmentation via LLM
MEP maintenance clearances not provided around air-handling unit. | Design | -1 | Synthetic augmentation via LLM
Crew deployed without required trade certification. | Human Resources | -1 | Synthetic augmentation via LLM
Untrained new hires misinterpreted installation procedure. | Human Resources | -1 | Synthetic augmentation via LLM
Incorrect skill mix assigned to a specialized task. | Human Resources | -1 | Synthetic augmentation via LLM
Language barrier between subcontract crews led to instruction errors. | Human Resources | -1 | Synthetic augmentation via LLM
Fatigue from excessive overtime reduced workmanship quality. | Human Resources | -1 | Synthetic augmentation via LLM
Temporary labor unfamiliar with site QA/QC protocols. | Human Resources | -1 | Synthetic augmentation via LLM
Late mobilization of critical crew delayed prerequisite inspections. | Human Resources | -1 | Synthetic augmentation via LLM
Mandatory safety and quality inductions not completed pre-task. | Human Resources | -1 | Synthetic augmentation via LLM
Expired equipment-operator licenses went unchecked. | Human Resources | -1 | Synthetic augmentation via LLM
Payroll dispute caused work stoppage and rushed rework on restart. | Human Resources | -1 | Synthetic augmentation via LLM
Roster error substituted an unqualified worker into a certified role. | Human Resources | -1 | Synthetic augmentation via LLM
Latest drawing revision not distributed to field crews. | Documentation & Information Management | -1 | Synthetic augmentation via LLM
RFI response not logged, leaving outdated instructions in use. | Documentation & Information Management | -1 | Synthetic augmentation via LLM
Submittal approved 'with comments' but comments not incorporated into IFC set. | Documentation & Information Management | -1 | Synthetic augmentation via LLM
As-built markups lost due to noncompliant file naming. | Documentation & Information Management | -1 | Synthetic augmentation via LLM
BIM model parameters missing fire-rating attributes. | Documentation & Information Management | -1 | Synthetic augmentation via LLM
Transmittal omitted structural addendum A-04. | Documentation & Information Management | -1 | Synthetic augmentation via LLM
Document control updated shared drive only; CDE not synchronized. | Documentation & Information Management | -1 | Synthetic augmentation via LLM
Superseded detail remained posted on site notice board. | Documentation & Information Management | -1 | Synthetic augmentation via LLM
Change order text ambiguous after version merge conflict. | Documentation & Information Management | -1 | Synthetic augmentation via LLM
Drawing index inconsistent with actual sheet set. | Documentation & Information Management | -1 | Synthetic augmentation via LLM
Field order issued without attaching referenced sketch. | Documentation & Information Management | -1 | Synthetic augmentation via LLM
Vendor O&M manual not uploaded prior to commissioning. | Documentation & Information Management | -1 | Synthetic augmentation via LLM
Revision clouds removed without delta tag reference. | Documentation & Information Management | -1 | Synthetic augmentation via LLM
Material takeoff exported in incorrect units to site. | Documentation & Information Management | -1 | Synthetic augmentation via LLM
Metadata mislabeling routed notification to wrong trade. | Documentation & Information Management | -1 | Synthetic augmentation via LLM
Email directive lacked traceable document number. | Documentation & Information Management | -1 | Synthetic augmentation via LLM
Daily reports not synced, creating duplicate work tickets. | Documentation & Information Management | -1 | Synthetic augmentation via LLM
QA photo evidence missing geotag and timestamp. | Documentation & Information Management | -1 | Synthetic augmentation via LLM
Shop drawing revision control failed; superseded sheet built. | Documentation & Information Management | -1 | Synthetic augmentation via LLM
Unapproved redlines were treated as authorized change. | Documentation & Information Management | -1 | Synthetic augmentation via LLM
Document retention purge deleted active work package. | Documentation & Information Management | -1 | Synthetic augmentation via LLM
Field tablets cached stale drawings for offline use. | Documentation & Information Management | -1 | Synthetic augmentation via LLM
Master spec conflicted with project addendum; no clarification issued. | Documentation & Information Management | -1 | Synthetic augmentation via LLM
Model coordination comments not exported to clash list. | Documentation & Information Management | -1 | Synthetic augmentation via LLM
Supplier datasheet version mismatched installed lot. | Documentation & Information Management | -1 | Synthetic augmentation via LLM
Work pack missing latest method statement attachment. | Documentation & Information Management | -1 | Synthetic augmentation via LLM
QR code on site signage linked to obsolete procedure. | Documentation & Information Management | -1 | Synthetic augmentation via LLM
Submittal log entries lacked approval stamps. | Documentation & Information Management | -1 | Synthetic augmentation via LLM
File permissions blocked site access to updated ITP. | Documentation & Information Management | -1 | Synthetic augmentation via LLM
Numbering convention changed mid-project, breaking traceability. | Documentation & Information Management | -1 | Synthetic augmentation via LLM
CDE audit found untracked external file sharing. | Documentation & Information Management | -1 | Synthetic augmentation via LLM
Transmittal dates inconsistent with revision history. | Documentation & Information Management | -1 | Synthetic augmentation via LLM
Verbal instruction issued without written confirmation. | Communication | -1 | Synthetic augmentation via LLM
Shift handover missed a late design change note. | Communication | -1 | Synthetic augmentation via LLM
Pre-task briefing did not cover revised method statement. | Communication | -1 | Synthetic augmentation via LLM
Toolbox talk omitted critical hold-point inspection. | Communication | -1 | Synthetic augmentation via LLM
Email with change directive sent to outdated distribution list. | Communication | -1 | Synthetic augmentation via LLM
RFI escalation not communicated to site before work start. | Communication | -1 | Synthetic augmentation via LLM
Conflicting instructions issued by client rep and superintendent. | Communication | -1 | Synthetic augmentation via LLM
Weekly coordination minutes not circulated to subcontractors. | Communication | -1 | Synthetic augmentation via LLM
Language barrier caused misinterpretation of lift plan. | Communication | -1 | Synthetic augmentation via LLM
Schedule update posted but not announced to field crews. | Communication | -1 | Synthetic augmentation via LLM
Clarification call not followed by written record of decision. | Communication | -1 | Synthetic augmentation via LLM
Change approval given verbally during walkdown; no memo issued. | Communication | -1 | Synthetic augmentation via LLM
Critical notice sent via chat app and lost in thread noise. | Communication | -1 | Synthetic augmentation via LLM
Incorrect radio channel used during concrete pour coordination. | Communication | -1 | Synthetic augmentation via LLM
Ambiguous acronym in instruction led to wrong material pick. | Communication | -1 | Synthetic augmentation via LLM
Hold tag color change not communicated to quality inspectors. | Communication | -1 | Synthetic augmentation via LLM
Permit-to-work conditions updated but not briefed to crew. | Communication | -1 | Synthetic augmentation via LLM
Site signage wording unclear about access restrictions. | Communication | -1 | Synthetic augmentation via LLM
Outage window change not relayed to night shift. | Communication | -1 | Synthetic augmentation via LLM
Supplier substitution approval email not forwarded to installation team. | Communication | -1 | Synthetic augmentation via LLM
Meeting reschedule notice missed a key stakeholder. | Communication | -1 | Synthetic augmentation via LLM
Incorrect phone tree contact used for urgent hold resolution. | Communication | -1 | Synthetic augmentation via LLM
Units not specified in message; crew assumed millimeters. | Communication | -1 | Synthetic augmentation via LLM
Two-way radio dead spot prevented lift-stop command from reaching rigger. | Communication | -1 | Synthetic augmentation via LLM
Pre-construction meeting action items not assigned owners. | Communication | -1 | Synthetic augmentation via LLM
Interface point change at trade boundary not communicated across teams. | Communication | -1 | Synthetic augmentation via LLM
Delivery driver instructions lacked gate and laydown location. | Communication | -1 | Synthetic augmentation via LLM
Hot work restriction emailed after crew had already mobilized. | Communication | -1 | Synthetic augmentation via LLM
Unclear acceptance criteria communicated to testing subcontractor. | Communication | -1 | Synthetic augmentation via LLM
Design clarification reply buried in long email thread chain. | Communication | -1 | Synthetic augmentation via LLM
Time zone confusion caused missed coordination call with vendor. | Communication | -1 | Synthetic augmentation via LLM
Color-only markups not legible for color-blind crew member. | Communication | -1 | Synthetic augmentation via LLM
Numeric format (comma vs period) in message misread torque values. | Communication | -1 | Synthetic augmentation via LLM
Crane hand signals inconsistent between spotter and operator. | Communication | -1 | Synthetic augmentation via LLM
Notice to proceed posted on board but not verbally briefed. | Communication | -1 | Synthetic augmentation via LLM
Client change directive sent to PM but not cascaded to field. | Communication | -1 | Synthetic augmentation via LLM
Lookahead plan not updated to reflect latest design change. | Time & Planning | -1 | Synthetic augmentation via LLM
Critical path misidentified; noncritical activity delayed and burned float. | Time & Planning | -1 | Synthetic augmentation via LLM
Out-of-sequence work started without prerequisite inspection. | Time & Planning | -1 | Synthetic augmentation via LLM
Permit lead time omitted from baseline schedule. | Time & Planning | -1 | Synthetic augmentation via LLM
Long-lead equipment not fast-tracked in planning phase. | Time & Planning | -1 | Synthetic augmentation via LLM
Concrete curing duration underestimated in activity logic. | Time & Planning | -1 | Synthetic augmentation via LLM
Weather contingency not included for roofing works. | Time & Planning | -1 | Synthetic augmentation via LLM
Night-shift access windows not coordinated with operations. | Time & Planning | -1 | Synthetic augmentation via LLM
Resource leveling removed required parallel crews on critical path. | Time & Planning | -1 | Synthetic augmentation via LLM
Delivery time slot missed due to unrealistic travel estimates. | Time & Planning | -1 | Synthetic augmentation via LLM
Crane availability not aligned with steel erection sequence. | Time & Planning | -1 | Synthetic augmentation via LLM
Commissioning activities not integrated with construction schedule. | Time & Planning | -1 | Synthetic augmentation via LLM
Utility shutdown window incorrectly booked; reschedule required. | Time & Planning | -1 | Synthetic augmentation via LLM
Inspection hold points allocated insufficient time. | Time & Planning | -1 | Synthetic augmentation via LLM
Submittal/approval cycle time underestimated in procurement plan. | Time & Planning | -1 | Synthetic augmentation via LLM
Takt plan not followed, causing downstream idle time. | Time & Planning | -1 | Synthetic augmentation via LLM
Prefab module installation sequence reversed in planning. | Time & Planning | -1 | Synthetic augmentation via LLM
Workface planning omitted setup of temporary works. | Time & Planning | -1 | Synthetic augmentation via LLM
Crew handoff buffers removed during rebaseline. | Time & Planning | -1 | Synthetic augmentation via LLM
Access scaffolding removal scheduled before punchlist completion. | Time & Planning | -1 | Synthetic augmentation via LLM
Subcontractor mobilization planned during site closure period. | Time & Planning | -1 | Synthetic augmentation via LLM
Trade stacking planned beyond safe workface capacity. | Time & Planning | -1 | Synthetic augmentation via LLM
Constraint log not cleared before issuing weekly work plan. | Time & Planning | -1 | Synthetic augmentation via LLM
Schedule logic lacked finish-to-start ties at interfaces. | Time & Planning | -1 | Synthetic augmentation via LLM
Cure-to-test interval for coatings not planned. | Time & Planning | -1 | Synthetic augmentation via LLM
Legal holidays not blocked in master schedule. | Time & Planning | -1 | Synthetic augmentation via LLM
Supplier change increased lead time, but schedule not rebaselined. | Time & Planning | -1 | Synthetic augmentation via LLM
Sequencing did not account for MEP rough-in before drywall. | Time & Planning | -1 | Synthetic augmentation via LLM
Float theft by discretionary logic not monitored. | Time & Planning | -1 | Synthetic augmentation via LLM
Temporary power availability not planned for equipment start-up. | Time & Planning | -1 | Synthetic augmentation via LLM
Road closure for oversized load not scheduled with authorities. | Time & Planning | -1 | Synthetic augmentation via LLM
Demobilization planned prior to client acceptance testing. | Time & Planning | -1 | Synthetic augmentation via LLM
Rework window after change order approval not inserted. | Time & Planning | -1 | Synthetic augmentation via LLM
Instrument calibration scheduled only after handover. | Time & Planning | -1 | Synthetic augmentation via LLM
Permit-to-work expiration overlapped planned activity start. | Time & Planning | -1 | Synthetic augmentation via LLM
Welding procedure qualification duration not planned before production. | Time & Planning | -1 | Synthetic augmentation via LLM
Wrong concrete mix design delivered to site. | Material Resources | -1 | Synthetic augmentation via LLM
Structural steel arrived with incorrect grade marking. | Material Resources | -1 | Synthetic augmentation via LLM
Moisture-damaged gypsum boards from improper storage. | Material Resources | -1 | Synthetic augmentation via LLM
Batch traceability lost due to repackaging of fasteners. | Material Resources | -1 | Synthetic augmentation via LLM
PVC pipe schedule lower than specified. | Material Resources | -1 | Synthetic augmentation via LLM
Counterfeit rebar supplied without mill certificates. | Material Resources | -1 | Synthetic augmentation via LLM
Sealant incompatible with substrate per datasheet. | Material Resources | -1 | Synthetic augmentation via LLM
Admixture dosage mislabeled, causing set delay. | Material Resources | -1 | Synthetic augmentation via LLM
Paint supplied beyond shelf life. | Material Resources | -1 | Synthetic augmentation via LLM
Aggregates contaminated with clay fines above limit. | Material Resources | -1 | Synthetic augmentation via LLM
Anchor bolts delivered with damaged threads. | Material Resources | -1 | Synthetic augmentation via LLM
Insulation thickness not as per approved submittal. | Material Resources | -1 | Synthetic augmentation via LLM
Firestop materials substituted without authorization. | Material Resources | -1 | Synthetic augmentation via LLM
Gasket material not rated for operating temperature. | Material Resources | -1 | Synthetic augmentation via LLM
Facade panel finish/color not per spec. | Material Resources | -1 | Synthetic augmentation via LLM
Cement bags exposed to rain during transport. | Material Resources | -1 | Synthetic augmentation via LLM
Tile batch shade variation unmanaged across rooms. | Material Resources | -1 | Synthetic augmentation via LLM
Cable trays of undersized width delivered. | Material Resources | -1 | Synthetic augmentation via LLM
HVAC filters not meeting specified MERV rating. | Material Resources | -1 | Synthetic augmentation via LLM
Valve pressure class lower than required. | Material Resources | -1 | Synthetic augmentation via LLM
Fastener corrosion class unsuitable for coastal environment. | Material Resources | -1 | Synthetic augmentation via LLM
Precast panels delivered without required lifting inserts. | Material Resources | -1 | Synthetic augmentation via LLM
Insulated glass units with incorrect low-E coating. | Material Resources | -1 | Synthetic augmentation via LLM
Waterproofing membrane roll width off specification. | Material Resources | -1 | Synthetic augmentation via LLM
Primer and topcoat from incompatible systems supplied. | Material Resources | -1 | Synthetic augmentation via LLM
Concrete admixture delivered in contaminated tote. | Material Resources | -1 | Synthetic augmentation via LLM
Epoxy grout kit missing hardener component. | Material Resources | -1 | Synthetic augmentation via LLM
Timber not treated to required preservative class. | Material Resources | -1 | Synthetic augmentation via LLM
Rebar couplers mismatched thread series. | Material Resources | -1 | Synthetic augmentation via LLM
Copper piping supplied as Type M instead of Type L. | Material Resources | -1 | Synthetic augmentation via LLM
Electrical cable insulation temperature rating below code. | Material Resources | -1 | Synthetic augmentation via LLM
Masonry mortar premix wrong strength class. | Material Resources | -1 | Synthetic augmentation via LLM
Roofing screws supplied without sealing washers. | Material Resources | -1 | Synthetic augmentation via LLM
Flooring adhesive not low-VOC as specified. | Material Resources | -1 | Synthetic augmentation via LLM
Backer rod diameter incorrect for joint width. | Material Resources | -1 | Synthetic augmentation via LLM
Geotextile fabric permeability grade not per design. | Material Resources | -1 | Synthetic augmentation via LLM
Subbase aggregate gradation out of specification. | Material Resources | -1 | Synthetic augmentation via LLM
Embedded anchors supplied with wrong sleeve length. | Material Resources | -1 | Synthetic augmentation via LLM
Pre-insulated pipe sections with damaged foam jacket. | Material Resources | -1 | Synthetic augmentation via LLM
Calcium silicate boards cracked due to poor packaging. | Material Resources | -1 | Synthetic augmentation via LLM
Chemical anchor cartridges delivered expired. | Material Resources | -1 | Synthetic augmentation via LLM
Lowest-bid award ignored technical capability requirements. | Contractor Selection & Performance | -1 | Synthetic augmentation via LLM
Prequalification did not verify comparable project experience. | Contractor Selection & Performance | -1 | Synthetic augmentation via LLM
Reference checks for critical subcontractor were skipped. | Contractor Selection & Performance | -1 | Synthetic augmentation via LLM
Bid leveling omitted testing and commissioning allowances. | Contractor Selection & Performance | -1 | Synthetic augmentation via LLM
Scope gaps between GC and subcontractor left unassigned. | Contractor Selection & Performance | -1 | Synthetic augmentation via LLM
Contract KPIs lacked quality metrics, focusing only on time/cost. | Contractor Selection & Performance | -1 | Synthetic augmentation via LLM
Subcontractor QA/QC plan not implemented on site. | Contractor Selection & Performance | -1 | Synthetic augmentation via LLM
Superintendent turnover caused loss of site leadership. | Contractor Selection & Performance | -1 | Synthetic augmentation via LLM
Crew size consistently below planned productivity. | Contractor Selection & Performance | -1 | Synthetic augmentation via LLM
Foreman failed to enforce ITP hold points. | Contractor Selection & Performance | -1 | Synthetic augmentation via LLM
Contractor used unapproved installation method. | Contractor Selection & Performance | -1 | Synthetic augmentation via LLM
Daily reports overstated percent complete. | Contractor Selection & Performance | -1 | Synthetic augmentation via LLM
Punchlist items recurred due to ineffective corrective actions. | Contractor Selection & Performance | -1 | Synthetic augmentation via LLM
Welding performed by uncertified personnel. | Contractor Selection & Performance | -1 | Synthetic augmentation via LLM
Contractor missed mandatory coordination meetings. | Contractor Selection & Performance | -1 | Synthetic augmentation via LLM
Subcontractor failed to protect finished work from damage. | Contractor Selection & Performance | -1 | Synthetic augmentation via LLM
Rework backlog not tracked in contractor system. | Contractor Selection & Performance | -1 | Synthetic augmentation via LLM
Tooling inadequate to achieve specified tolerances. | Contractor Selection & Performance | -1 | Synthetic augmentation via LLM
Contractor submitted RFIs late, causing idle time. | Contractor Selection & Performance | -1 | Synthetic augmentation via LLM
Change orders priced without impact analysis, later rework. | Contractor Selection & Performance | -1 | Synthetic augmentation via LLM
Safety noncompliance led to stop-work and resequencing. | Contractor Selection & Performance | -1 | Synthetic augmentation via LLM
Poor housekeeping damaged installed work. | Contractor Selection & Performance | -1 | Synthetic augmentation via LLM
Mockup lessons not applied in production. | Contractor Selection & Performance | -1 | Synthetic augmentation via LLM
Field engineer misread datum, causing layout misalignment. | Contractor Selection & Performance | -1 | Synthetic augmentation via LLM
Subcontractor failed to supervise third-tier labor. | Contractor Selection & Performance | -1 | Synthetic augmentation via LLM
Allowances exhausted; contractor switched to inferior process. | Contractor Selection & Performance | -1 | Synthetic augmentation via LLM
Crew not trained on project-specific specifications. | Contractor Selection & Performance | -1 | Synthetic augmentation via LLM
Turnover package incomplete; post-handover rework required. | Contractor Selection & Performance | -1 | Synthetic augmentation via LLM
Late submittals compressed review windows, increasing errors. | Contractor Selection & Performance | -1 | Synthetic augmentation via LLM
Contractor skipped pre-installation conference. | Contractor Selection & Performance | -1 | Synthetic augmentation via LLM
Commissioning support under-resourced by contractor. | Contractor Selection & Performance | -1 | Synthetic augmentation via LLM
Payment disputes triggered subcontractor demobilization. | Contractor Selection & Performance | -1 | Synthetic augmentation via LLM
As-built updates not maintained during construction. | Contractor Selection & Performance | -1 | Synthetic augmentation via LLM
Contractor IT systems delayed site access to documents. | Contractor Selection & Performance | -1 | Synthetic augmentation via LLM
QC inspections closed without verifying NCR closure. | Contractor Selection & Performance | -1 | Synthetic augmentation via LLM
Tools not calibrated per contractor schedule. | Contractor Selection & Performance | -1 | Synthetic augmentation via LLM
Subcontractor deviated from shop drawings without approval. | Contractor Selection & Performance | -1 | Synthetic augmentation via LLM
Trade stacking planned beyond contractor’s managed capacity. | Contractor Selection & Performance | -1 | Synthetic augmentation via LLM
Temporary protection requirements not enforced by contractor. | Contractor Selection & Performance | -1 | Synthetic augmentation via LLM
Delivery coordination windows repeatedly missed by contractor. | Contractor Selection & Performance | -1 | Synthetic augmentation via LLM
Pull plan commitments ignored by subcontractor. | Contractor Selection & Performance | -1 | Synthetic augmentation via LLM
No backfill for site manager during leave period. | Contractor Selection & Performance | -1 | Synthetic augmentation via LLM
Late client change to room layout after rough-in. | Client-Driven Influences | -1 | Synthetic augmentation via LLM
Client-supplied equipment dimensions changed post-approval. | Client-Driven Influences | -1 | Synthetic augmentation via LLM
Finish color re-selection after painting complete. | Client-Driven Influences | -1 | Synthetic augmentation via LLM
Brand standard update forced hardware swap. | Client-Driven Influences | -1 | Synthetic augmentation via LLM
Client-provided survey datum incorrect. | Client-Driven Influences | -1 | Synthetic augmentation via LLM
Furniture plan revision required power/data relocation. | Client-Driven Influences | -1 | Synthetic augmentation via LLM
Owner-directed value engineering reversed later. | Client-Driven Influences | -1 | Synthetic augmentation via LLM
Client-approved mockup rejected by new stakeholder. | Client-Driven Influences | -1 | Synthetic augmentation via LLM
Client delayed submittal approvals beyond review window. | Client-Driven Influences | -1 | Synthetic augmentation via LLM
Client deferred decision on fixture type, causing hold. | Client-Driven Influences | -1 | Synthetic augmentation via LLM
Owner added scope without schedule relief. | Client-Driven Influences | -1 | Synthetic augmentation via LLM
Client restricted work hours, disrupting sequence. | Client-Driven Influences | -1 | Synthetic augmentation via LLM
Client's IT standards forced re-cabling. | Client-Driven Influences | -1 | Synthetic augmentation via LLM
Client-supplied material failed quality check. | Client-Driven Influences | -1 | Synthetic augmentation via LLM
Owner changed security access levels late. | Client-Driven Influences | -1 | Synthetic augmentation via LLM
Client altered signage package after fabrication. | Client-Driven Influences | -1 | Synthetic augmentation via LLM
Owner-directed vendor substitution incompatible. | Client-Driven Influences | -1 | Synthetic augmentation via LLM
Client requested premium finish with excessive lead time. | Client-Driven Influences | -1 | Synthetic augmentation via LLM
Client increased acoustic rating requirement midstream. | Client-Driven Influences | -1 | Synthetic augmentation via LLM
Owner added accessibility features beyond code. | Client-Driven Influences | -1 | Synthetic augmentation via LLM
Client revised energy targets requiring re-design. | Client-Driven Influences | -1 | Synthetic augmentation via LLM
End-user walkthrough triggered layout changes. | Client-Driven Influences | -1 | Synthetic augmentation via LLM
Client moved opening date up, compressing tasks. | Client-Driven Influences | -1 | Synthetic augmentation via LLM
Owner changed warranty terms requiring rework. | Client-Driven Influences | -1 | Synthetic augmentation via LLM
Client's legal team rejected permit language. | Client-Driven Influences | -1 | Synthetic augmentation via LLM
Client changed BIM deliverable level post-contract. | Client-Driven Influences | -1 | Synthetic augmentation via LLM
Client mandated alternate fire alarm vendor. | Client-Driven Influences | -1 | Synthetic augmentation via LLM
Owner requested additional MEP spare capacity. | Client-Driven Influences | -1 | Synthetic augmentation via LLM
Client changed ceiling type, affecting sprinkler layout. | Client-Driven Influences | -1 | Synthetic augmentation via LLM
Owner-provided freezer specs changed power needs. | Client-Driven Influences | -1 | Synthetic augmentation via LLM
Client instructed relocation of mechanical room. | Client-Driven Influences | -1 | Synthetic augmentation via LLM
Owner changed wayfinding strategy after install. | Client-Driven Influences | -1 | Synthetic augmentation via LLM
Client added data ports after drywall. | Client-Driven Influences | -1 | Synthetic augmentation via LLM
Owner revised door hardware set late. | Client-Driven Influences | -1 | Synthetic augmentation via LLM
Client banned certain adhesives due to VOC policy. | Client-Driven Influences | -1 | Synthetic augmentation via LLM
Client required extra cleanroom classification. | Client-Driven Influences | -1 | Synthetic augmentation via LLM
Owner changed tile pattern after installation start. | Client-Driven Influences | -1 | Synthetic augmentation via LLM
Client updated corporate color palette mid-project. | Client-Driven Influences | -1 | Synthetic augmentation via LLM
Client-supplied fixture anchor template inaccurate. | Client-Driven Influences | -1 | Synthetic augmentation via LLM
Owner's procurement delay forced substitute then revert. | Client-Driven Influences | -1 | Synthetic augmentation via LLM
Client demanded last-minute scope split across trades. | Client-Driven Influences | -1 | Synthetic augmentation via LLM
End-user ergonomics feedback changed counter heights. | Client-Driven Influences | -1 | Synthetic augmentation via LLM
Client required additional commissioning tests. | Client-Driven Influences | -1 | Synthetic augmentation via LLM
Budget cut canceled constructability mockup; errors surfaced in production. | Financial Constraints | -1 | Synthetic augmentation via LLM
Cost cap forced substitution to lower-grade material. | Financial Constraints | -1 | Synthetic augmentation via LLM
Funding release delay halted inspections, causing resequencing. | Financial Constraints | -1 | Synthetic augmentation via LLM
Cash-flow holdback led to premature demobilization of quality staff. | Financial Constraints | -1 | Synthetic augmentation via LLM
Contingency exhausted; corrective work deferred then rushed. | Financial Constraints | -1 | Synthetic augmentation via LLM
Owner payment delay put supplier on credit hold. | Financial Constraints | -1 | Synthetic augmentation via LLM
Value engineering removed redundant seal, causing leakage. | Financial Constraints | -1 | Synthetic augmentation via LLM
Low-bid procurement excluded factory acceptance testing. | Financial Constraints | -1 | Synthetic augmentation via LLM
Price escalation exceeded allowance; partial order placed. | Financial Constraints | -1 | Synthetic augmentation via LLM
FX variance reduced budget for imported equipment spares. | Financial Constraints | -1 | Synthetic augmentation via LLM
Warranty extension dropped to save cost; rework not covered. | Financial Constraints | -1 | Synthetic augmentation via LLM
Budget-driven scope split increased interfaces and errors. | Financial Constraints | -1 | Synthetic augmentation via LLM
Reduced survey hours eliminated second check of benchmarks. | Financial Constraints | -1 | Synthetic augmentation via LLM
Overtime ban extended activity beyond cure window. | Financial Constraints | -1 | Synthetic augmentation via LLM
Tool rental off-hired early to cut cost; rework during reinstall. | Financial Constraints | -1 | Synthetic augmentation via LLM
Training budget cut; crew misapplied new system. | Financial Constraints | -1 | Synthetic augmentation via LLM
QA/QC staffing reduced below plan, defects went undetected. | Financial Constraints | -1 | Synthetic augmentation via LLM
Testing lab switched to cheaper provider with longer turnaround. | Financial Constraints | -1 | Synthetic augmentation via LLM
Nonconformance repair kit not stocked due to cost freeze. | Financial Constraints | -1 | Synthetic augmentation via LLM
Spare parts omitted from order to meet cap. | Financial Constraints | -1 | Synthetic augmentation via LLM
Temporary protection downgraded to cheaper material; damage occurred. | Financial Constraints | -1 | Synthetic augmentation via LLM
Subcontract included unrealistic productivity to meet budget. | Financial Constraints | -1 | Synthetic augmentation via LLM
Inspection hold points reduced to save time and cost. | Financial Constraints | -1 | Synthetic augmentation via LLM
Metering instruments not calibrated to avoid fee. | Financial Constraints | -1 | Synthetic augmentation via LLM
Cheaper scaffolding system lacked required access; workarounds failed. | Financial Constraints | -1 | Synthetic augmentation via LLM
Concrete cylinder tests reduced; strength issue missed. | Financial Constraints | -1 | Synthetic augmentation via LLM
Budget drove single-source purchase; vendor underperformed. | Financial Constraints | -1 | Synthetic augmentation via LLM
Early procurement canceled to avoid cash tie-up; lead time slipped. | Financial Constraints | -1 | Synthetic augmentation via LLM
Material storage covers not purchased; weather damage. | Financial Constraints | -1 | Synthetic augmentation via LLM
Reduced geotechnical investigation scope mischaracterized soil. | Financial Constraints | -1 | Synthetic augmentation via LLM
Design hours capped; coordination left unresolved. | Financial Constraints | -1 | Synthetic augmentation via LLM
Commissioning scope trimmed; systems not balanced. | Financial Constraints | -1 | Synthetic augmentation via LLM
Temporary power capacity downsized; equipment tripped. | Financial Constraints | -1 | Synthetic augmentation via LLM
Cheaper adhesive selected contrary to spec to cut cost. | Financial Constraints | -1 | Synthetic augmentation via LLM
Spare filter sets omitted; startup repeated after fouling. | Financial Constraints | -1 | Synthetic augmentation via LLM
Cheapest shipping option used; components arrived damaged. | Financial Constraints | -1 | Synthetic augmentation via LLM
Retainage increased, subcontractor slowed work and quality. | Financial Constraints | -1 | Synthetic augmentation via LLM
Budget did not include rebar couplers; field splicing failed. | Financial Constraints | -1 | Synthetic augmentation via LLM
Cheaper fasteners corroded in service environment. | Financial Constraints | -1 | Synthetic augmentation via LLM
Cheapest paint system used; coverage inadequate. | Financial Constraints | -1 | Synthetic augmentation via LLM
PPE replenishment deferred; work interruptions caused rework. | Financial Constraints | -1 | Synthetic augmentation via LLM
Survey equipment hire limited; as-built not verified. | Financial Constraints | -1 | Synthetic augmentation via LLM
Design assist phase removed to save cost; clashes emerged. | Financial Constraints | -1 | Synthetic augmentation via LLM
Preconstruction coordination meetings reduced; interface gaps. | Financial Constraints | -1 | Synthetic augmentation via LLM
Lower-cost prefabricator lacked tolerances; on-site rework. | Financial Constraints | -1 | Synthetic augmentation via LLM
Budget omitted third-party peer review; error persisted. | Financial Constraints | -1 | Synthetic augmentation via LLM
Flushing chemicals skipped due to cost; system fouled. | Financial Constraints | -1 | Synthetic augmentation via LLM
Cheaper formwork oil caused surface defects. | Financial Constraints | -1 | Synthetic augmentation via LLM
Low-cost gasket substitute incompatible with medium. | Financial Constraints | -1 | Synthetic augmentation via LLM
Concrete pump time restricted; cold joints formed. | Financial Constraints | -1 | Synthetic augmentation via LLM
Budget capped test runs; commissioning defects missed. | Financial Constraints | -1 | Synthetic augmentation via LLM
Samples and mockups limited; finish mismatch accepted. | Financial Constraints | -1 | Synthetic augmentation via LLM
Low-cost crane share created access conflicts. | Financial Constraints | -1 | Synthetic augmentation via LLM
Cheaper survey crew unfamiliar with project controls. | Financial Constraints | -1 | Synthetic augmentation via LLM
Severe storm flooded work areas and halted activities. | External Influences | -1 | Synthetic augmentation via LLM
Municipal inspection backlog delayed concrete pour approvals. | External Influences | -1 | Synthetic augmentation via LLM
Grid power outage from utility cut temporary power to site. | External Influences | -1 | Synthetic augmentation via LLM
Public transit strike reduced crew attendance below plan. | External Influences | -1 | Synthetic augmentation via LLM
Port congestion delayed arrival of imported curtain wall. | External Influences | -1 | Synthetic augmentation via LLM
Customs hold detained critical equipment at the border. | External Influences | -1 | Synthetic augmentation via LLM
Supplier factory shutdown due to regional lockdown. | External Influences | -1 | Synthetic augmentation via LLM
Asphalt plant closure during heat restrictions postponed paving. | External Influences | -1 | Synthetic augmentation via LLM
Local curfew limited permitted night-shift activities. | External Influences | -1 | Synthetic augmentation via LLM
City marathon road closures blocked scheduled deliveries. | External Influences | -1 | Synthetic augmentation via LLM
Neighbor injunction temporarily halted noisy operations. | External Influences | -1 | Synthetic augmentation via LLM
Community protest obstructed main gate access. | External Influences | -1 | Synthetic augmentation via LLM
Permit moratorium paused earthworks across jurisdiction. | External Influences | -1 | Synthetic augmentation via LLM
Archaeological find triggered regulator stop-work order. | External Influences | -1 | Synthetic augmentation via LLM
Protected species nesting season restricted tree removal. | External Influences | -1 | Synthetic augmentation via LLM
Offsite traffic accident delayed ready-mix trucks. | External Influences | -1 | Synthetic augmentation via LLM
Regional fuel shortage limited generator operation hours. | External Influences | -1 | Synthetic augmentation via LLM
National holiday shutdown extended supplier lead times. | External Influences | -1 | Synthetic augmentation via LLM
Wildfire smoke AQI exceeded threshold; exterior work suspended. | External Influences | -1 | Synthetic augmentation via LLM
River flooding washed out temporary access bridge. | External Influences | -1 | Synthetic augmentation via LLM
Earthquake aftershock required engineering re-inspection. | External Influences | -1 | Synthetic augmentation via LLM
High winds exceeded crane operating limits; lifts deferred. | External Influences | -1 | Synthetic augmentation via LLM
Lightning alarm forced tower crane shutdown cycles. | External Influences | -1 | Synthetic augmentation via LLM
Extreme cold snap compromised concrete curing windows. | External Influences | -1 | Synthetic augmentation via LLM
Heatwave mandated reduced work hours by authority. | External Influences | -1 | Synthetic augmentation via LLM
Epidemic quarantine removed key subcontractor crew. | External Influences | -1 | Synthetic augmentation via LLM
Cyberattack on logistics provider disrupted dispatching. | External Influences | -1 | Synthetic augmentation via LLM
National rail strike delayed structural steel shipments. | External Influences | -1 | Synthetic augmentation via LLM
Insurer imposed new hot-work conditions mid-project. | External Influences | -1 | Synthetic augmentation via LLM
Regulatory change updated fire damper spec post-award. | External Influences | -1 | Synthetic augmentation via LLM
Landfill capacity cap prevented debris haul-off. | External Influences | -1 | Synthetic augmentation via LLM
Adjacent blasting exceeded site vibration limits. | External Influences | -1 | Synthetic augmentation via LLM
Airport airspace restriction limited drone surveys. | External Influences | -1 | Synthetic augmentation via LLM
Temporary noise ordinance restricted use of impact tools. | External Influences | -1 | Synthetic augmentation via LLM
Wastewater utility outage blocked hydrotest discharge. | External Influences | -1 | Synthetic augmentation via LLM
Vendor bankruptcy stalled material release in transit. | External Influences | -1 | Synthetic augmentation via LLM
Offsite water main break flooded laydown area. | External Influences | -1 | Synthetic augmentation via LLM
Industrial park security incident closed all entrances. | External Influences | -1 | Synthetic augmentation via LLM
Police cordon on adjacent street removed site access. | External Influences | -1 | Synthetic augmentation via LLM
Storm debris blocked entrance until municipal clearance. | External Influences | -1 | Synthetic augmentation via LLM
Sandstorm reduced visibility; exterior tasks suspended. | External Influences | -1 | Synthetic augmentation via LLM
New import tariff forced re-procurement of equipment. | External Influences | -1 | Synthetic augmentation via LLM
Trade embargo blocked specified material source. | External Influences | -1 | Synthetic augmentation via LLM
Container lost at sea; components required re-fabrication. | External Influences | -1 | Synthetic augmentation via LLM
Insurance claim processing delayed replacement pump. | External Influences | -1 | Synthetic augmentation via LLM
PPE mandate during outbreak reduced allowable crew density. | External Influences | -1 | Synthetic augmentation via LLM
Third-party lab backlog delayed concrete break results. | External Influences | -1 | Synthetic augmentation via LLM
Grid brownouts forced staged shutdown of equipment. | External Influences | -1 | Synthetic augmentation via LLM
Telecom outage disabled digital permit system access. | External Influences | -1 | Synthetic augmentation via LLM
Election regulatory blackout paused permit approvals. | External Influences | -1 | Synthetic augmentation via LLM
Ecology agency imposed temporary water-use restrictions. | External Influences | -1 | Synthetic augmentation via LLM
Mosquito control fogging required brief site evacuation. | External Influences | -1 | Synthetic augmentation via LLM
Nearby chemical spill triggered shelter-in-place order. | External Influences | -1 | Synthetic augmentation via LLM
Snowstorm closed regional highways to heavy trucks. | External Influences | -1 | Synthetic augmentation via LLM
Landslide damaged haul road to borrow pit. | External Influences | -1 | Synthetic augmentation via LLM
Quarry blast schedule change missed aggregate delivery window. | External Influences | -1 | Synthetic augmentation via LLM
Harbor pilot shortage delayed vessel berthing. | External Influences | -1 | Synthetic augmentation via LLM
Toll plaza system failure caused delivery queuing. | External Influences | -1 | Synthetic augmentation via LLM
Pre-task risk assessment not completed before work. | Safety Culture | -1 | Synthetic augmentation via LLM
Permit-to-work conditions ignored to save time. | Safety Culture | -1 | Synthetic augmentation via LLM
LOTO procedure bypassed during equipment maintenance. | Safety Culture | -1 | Synthetic augmentation via LLM
Fall protection not used at heights above 2 m. | Safety Culture | -1 | Synthetic augmentation via LLM
Scaffold tag missing; platform used regardless. | Safety Culture | -1 | Synthetic augmentation via LLM
Barricades removed to speed access through hazard zone. | Safety Culture | -1 | Synthetic augmentation via LLM
Hot work performed without active fire watch. | Safety Culture | -1 | Synthetic augmentation via LLM
Confined space entry without continuous gas monitoring. | Safety Culture | -1 | Synthetic augmentation via LLM
PPE requirements relaxed by supervisor under schedule pressure. | Safety Culture | -1 | Synthetic augmentation via LLM
Near-miss reports discouraged, lessons not captured. | Safety Culture | -1 | Synthetic augmentation via LLM
JSA copy not available at point of work. | Safety Culture | -1 | Synthetic augmentation via LLM
Housekeeping neglected; trip hazard caused rework damage. | Safety Culture | -1 | Synthetic augmentation via LLM
Crane exclusion zone not enforced during lift. | Safety Culture | -1 | Synthetic augmentation via LLM
Improper ladder angle and tie-off used for access. | Safety Culture | -1 | Synthetic augmentation via LLM
Tool tethering omitted; dropped object damaged install. | Safety Culture | -1 | Synthetic augmentation via LLM
Pinch point guards removed from rotating equipment. | Safety Culture | -1 | Synthetic augmentation via LLM
Incorrect respiratory protection used for silica dust. | Safety Culture | -1 | Synthetic augmentation via LLM
Hearing protection not worn in high dB area. | Safety Culture | -1 | Synthetic augmentation via LLM
GFCI not used on temporary power tools. | Safety Culture | -1 | Synthetic augmentation via LLM
Voltage absence test skipped before contact. | Safety Culture | -1 | Synthetic augmentation via LLM
Daily equipment pre-use inspections not performed. | Safety Culture | -1 | Synthetic augmentation via LLM
Outdated SDS kept on site; wrong spill response. | Safety Culture | -1 | Synthetic augmentation via LLM
Chemical containers unlabeled; incompatible storage occurred. | Safety Culture | -1 | Synthetic augmentation via LLM
Spill kits not staged near workface. | Safety Culture | -1 | Synthetic augmentation via LLM
Emergency egress route blocked by stored materials. | Safety Culture | -1 | Synthetic augmentation via LLM
Muster point not briefed; evacuation delayed. | Safety Culture | -1 | Synthetic augmentation via LLM
First-aid kit incomplete; treatment delay worsened damage. | Safety Culture | -1 | Synthetic augmentation via LLM
Complacency normalized minor rule-breaking. | Safety Culture | -1 | Synthetic augmentation via LLM
Production targets prioritized over safe sequence. | Safety Culture | -1 | Synthetic augmentation via LLM
New workers not given site safety induction. | Safety Culture | -1 | Synthetic augmentation via LLM
Supervisor failed to stop visibly unsafe act. | Safety Culture | -1 | Synthetic augmentation via LLM
No management of change review for revised method. | Safety Culture | -1 | Synthetic augmentation via LLM
Toolbox talk attendance not enforced. | Safety Culture | -1 | Synthetic augmentation via LLM
Permit receiver did not brief crew on conditions. | Safety Culture | -1 | Synthetic augmentation via LLM
Fire extinguishers not inspected or within reach. | Safety Culture | -1 | Synthetic augmentation via LLM
Compressed gas cylinders unsecured in laydown area. | Safety Culture | -1 | Synthetic augmentation via LLM
Improper lifting technique caused injury and rework. | Safety Culture | -1 | Synthetic augmentation via LLM
Spotter absent during equipment backing. | Safety Culture | -1 | Synthetic augmentation via LLM
Sling inspection lapsed; frayed sling used. | Safety Culture | -1 | Synthetic augmentation via LLM
Anchor points not verified for tie-off capacity. | Safety Culture | -1 | Synthetic augmentation via LLM
Toeboards missing on elevated platforms. | Safety Culture | -1 | Synthetic augmentation via LLM
Open holes not covered or flagged. | Safety Culture | -1 | Synthetic augmentation via LLM
Heat stress controls not implemented during heatwave. | Safety Culture | -1 | Synthetic augmentation via LLM
Cold-weather PPE not provided; dexterity errors increased. | Safety Culture | -1 | Synthetic augmentation via LLM
Fatigue management ignored after extended overtime. | Safety Culture | -1 | Synthetic augmentation via LLM
Safety audits findings left unresolved. | Safety Culture | -1 | Synthetic augmentation via LLM
Behavior-based observations not fed back to crews. | Safety Culture | -1 | Synthetic augmentation via LLM
Safety incentives penalized reporting of incidents. | Safety Culture | -1 | Synthetic augmentation via LLM
Contractor safety plan not integrated with site rules. | Safety Culture | -1 | Synthetic augmentation via LLM
Permit signage not displayed at workface. | Safety Culture | -1 | Synthetic augmentation via LLM
Gas detectors out of calibration at time of use. | Safety Culture | -1 | Synthetic augmentation via LLM
Temporary lighting inadequate; visibility errors occurred. | Safety Culture | -1 | Synthetic augmentation via LLM
Lock boxes not used for group lockout. | Safety Culture | -1 | Synthetic augmentation via LLM
Working under suspended load tolerated by supervision. | Safety Culture | -1 | Synthetic augmentation via LLM
Excavation lacked benching/shoring; access unsafe. | Safety Culture | -1 | Synthetic augmentation via LLM
Traffic management plan not implemented around delivery. | Safety Culture | -1 | Synthetic augmentation via LLM
Live edge protection removed before task completion. | Safety Culture | -1 | Synthetic augmentation via LLM
Incorrect glove type used for chemical handling. | Safety Culture | -1 | Synthetic augmentation via LLM
No refresher training on changed safety procedures. | Safety Culture | -1 | Synthetic augmentation via LLM
BIM model coordinates not set to site grid, causing layout shift. | Technology Utilization | -1 | Synthetic augmentation via LLM
Point cloud registration error mislocated embedded plates. | Technology Utilization | -1 | Synthetic augmentation via LLM
Drone survey GCPs insufficient; resulting terrain model skewed. | Technology Utilization | -1 | Synthetic augmentation via LLM
Total station used with wrong datum transformation. | Technology Utilization | -1 | Synthetic augmentation via LLM
Machine control file loaded with outdated surface. | Technology Utilization | -1 | Synthetic augmentation via LLM
AR overlay misaligned due to uncalibrated device. | Technology Utilization | -1 | Synthetic augmentation via LLM
Laser scanner miscalibrated; as-built tolerances misread. | Technology Utilization | -1 | Synthetic augmentation via LLM
IFC export dropped rebar attributes used by fabricator. | Technology Utilization | -1 | Synthetic augmentation via LLM
Navisworks clash ruleset excluded critical categories. | Technology Utilization | -1 | Synthetic augmentation via LLM
4D simulation not updated to reflect schedule rebaseline. | Technology Utilization | -1 | Synthetic augmentation via LLM
CDE sync failed; offline edits overwritten on upload. | Technology Utilization | -1 | Synthetic augmentation via LLM
Tablet app cached obsolete drawings in kiosk mode. | Technology Utilization | -1 | Synthetic augmentation via LLM
Issue-tracking IDs not linked to model elements. | Technology Utilization | -1 | Synthetic augmentation via LLM
QR code system not mapped to latest asset tags. | Technology Utilization | -1 | Synthetic augmentation via LLM
RFID readers misconfigured antenna power, missing picks. | Technology Utilization | -1 | Synthetic augmentation via LLM
Barcode labels printed at low contrast; scanners failed. | Technology Utilization | -1 | Synthetic augmentation via LLM
GNSS rover used without RTK correction. | Technology Utilization | -1 | Synthetic augmentation via LLM
Photogrammetry taken under poor lighting; model unreliable. | Technology Utilization | -1 | Synthetic augmentation via LLM
Digital forms lacked mandatory fields; incomplete inspections. | Technology Utilization | -1 | Synthetic augmentation via LLM
API change broke automatic submittal ingestion. | Technology Utilization | -1 | Synthetic augmentation via LLM
Automated quantity takeoff used wrong measurement rules. | Technology Utilization | -1 | Synthetic augmentation via LLM
Parametric family incorrectly constrained; dimension propagated errors. | Technology Utilization | -1 | Synthetic augmentation via LLM
Model authoring units set to feet instead of millimeters. | Technology Utilization | -1 | Synthetic augmentation via LLM
Version mismatch between add-ins corrupted design files. | Technology Utilization | -1 | Synthetic augmentation via LLM
BIM platform permissions blocked trade from viewing updates. | Technology Utilization | -1 | Synthetic augmentation via LLM
Robotic layout uploaded wrong control points set. | Technology Utilization | -1 | Synthetic augmentation via LLM
Tablet OS update broke field app camera integration. | Technology Utilization | -1 | Synthetic augmentation via LLM
Cloud render used previous revision for coordination. | Technology Utilization | -1 | Synthetic augmentation via LLM
IoT temperature sensors drifted; curing plan not adjusted. | Technology Utilization | -1 | Synthetic augmentation via LLM
Data logger clock not synced; sequence analysis invalid. | Technology Utilization | -1 | Synthetic augmentation via LLM
Digital twin not reconciled with field change orders. | Technology Utilization | -1 | Synthetic augmentation via LLM
Dashboards aggregated duplicated work package IDs. | Technology Utilization | -1 | Synthetic augmentation via LLM
Automated alerts throttled as spam; team missed alarms. | Technology Utilization | -1 | Synthetic augmentation via LLM
AI-generated takeoff misclassified assemblies. | Technology Utilization | -1 | Synthetic augmentation via LLM
VR review exported comments to wrong model. | Technology Utilization | -1 | Synthetic augmentation via LLM
Prefab CNC file generated with mirrored orientation. | Technology Utilization | -1 | Synthetic augmentation via LLM
Laser level battery sag caused false level reference. | Technology Utilization | -1 | Synthetic augmentation via LLM
3D printer filament spec changed; part tolerance off. | Technology Utilization | -1 | Synthetic augmentation via LLM
Camera timestamps inconsistent; progress tracking flawed. | Technology Utilization | -1 | Synthetic augmentation via LLM
Wearable BLE beacons interfered with crane telemetry. | Technology Utilization | -1 | Synthetic augmentation via LLM
Thermal imaging set wrong emissivity; leak misdiagnosed. | Technology Utilization | -1 | Synthetic augmentation via LLM
DMS workflow auto-archived active drawings. | Technology Utilization | -1 | Synthetic augmentation via LLM
As-built capture not geofenced; wrong area tagged. | Technology Utilization | -1 | Synthetic augmentation via LLM
Mobile MDM policy blocked file downloads onsite. | Technology Utilization | -1 | Synthetic augmentation via LLM
License server outage disabled key design tools. | Technology Utilization | -1 | Synthetic augmentation via LLM
Dashboard filter default hid NCRs from view. | Technology Utilization | -1 | Synthetic augmentation via LLM
Edge gateway dropped sensor packets under load. | Technology Utilization | -1 | Synthetic augmentation via LLM
Unmanned rover firmware incompatible with base station. | Technology Utilization | -1 | Synthetic augmentation via LLM
Clash report exported without viewpoint context. | Technology Utilization | -1 | Synthetic augmentation via LLM
Cloud permissions let external vendor delete objects. | Technology Utilization | -1 | Synthetic augmentation via LLM
Model coordination used outdated object naming schema. | Technology Utilization | -1 | Synthetic augmentation via LLM
Laser projection system offset not re-zeroed after move. | Technology Utilization | -1 | Synthetic augmentation via LLM
Reality capture control targets removed before scan. | Technology Utilization | -1 | Synthetic augmentation via LLM
Digital permit system failed to prompt for attachments. | Technology Utilization | -1 | Synthetic augmentation via LLM
Construction camera AI mislabeled zones; heatmap wrong. | Technology Utilization | -1 | Synthetic augmentation via LLM
Automated rebar bending list not re-run after design change. | Technology Utilization | -1 | Synthetic augmentation via LLM
Model-based purchase order pulled unapproved alternates. | Technology Utilization | -1 | Synthetic augmentation via LLM
Field AR instructions lacked step indexing; sequence scrambled. | Technology Utilization | -1 | Synthetic augmentation via LLM
GNSS base station relocated without broadcasting update. | Technology Utilization | -1 | Synthetic augmentation via LLM
Tablet screen glare prevented sign-off; form submitted blank. | Technology Utilization | -1 | Synthetic augmentation via LLM
Unvetted plugin altered parameter GUIDs; data lost. | Technology Utilization | -1 | Synthetic augmentation via LLM
Edge-to-cloud sync conflict duplicated punch items. | Technology Utilization | -1 | Synthetic augmentation via LLM
Building permit conditions misinterpreted; work executed out of scope. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Required permit amendment not filed after design change. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Work commenced before permit issuance. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Inspection notification period not honored per ordinance. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Fire code egress width not met per latest edition. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
ADA door hardware noncompliant with reach range. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Handrail height failed accessibility requirement. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Seismic anchorage omitted due to overlooked code update. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Energy code U-value exceeded allowed maximum. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Plumbing vent sizing below code. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Electrical GFCI protection missing where mandated. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Smoke compartmentation not constructed per life-safety code. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Rated wall penetrations not firestopped to listed assembly. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Sprinkler head spacing violated NFPA coverage rules. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Emergency lighting levels below code minimum. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Exit signage not provided at required intersections. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Stair riser/tread geometry outside code tolerance. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Guardrail opening exceeded 4-inch sphere limit. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Combustible cladding installed where prohibited by code. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Shop drawings lacked engineer-of-record stamp as required. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Welding procedure not certified to the applicable standard. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Material certifications missing per specification and code. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Special inspections not performed per IBC schedule. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Temporary structure erected without city permit. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Noise ordinance limits exceeded during restricted hours. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Dust control noncompliant with air quality regulation. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Stormwater BMPs not installed per NPDES permit. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Concrete washout improperly contained per environmental rules. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Hazardous waste manifest incomplete; disposal rejected. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Diesel spill not reported within statutory window. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
SWPPP not updated after site modification. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Tree protection fencing not installed per permit condition. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Wetland buffer encroachment beyond approved limit. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Cultural resource monitoring omitted per permit. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Traffic control plan not approved by authority prior to work. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Lane closure permit expired; work continued. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Utility locate law violated; excavation began before clearance. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Crane permit load data not filed with municipality. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Hoist operation conducted outside permitted hours. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Right-of-way restoration not completed to city standard. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Export soil classification misdeclared for landfill acceptance. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Asbestos survey omitted before demolition. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Lead paint containment not compliant with regulation. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Silica exposure plan absent per occupational standard. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Confined space permit missing attendant signature. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Hot work permit not issued for welding in restricted area. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Fall protection plan not documented as required. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Lockout/tagout records incomplete for audit. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Worker training certificates not retained per labor law. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Certified payroll not submitted by statutory deadline. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Apprenticeship ratio requirements not maintained. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Contractor licensing for specialty trade expired during work. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Zoning conditions of approval not incorporated into plans. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Change of occupancy not filed before tenant fit-out. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Fire department pre-test required but skipped. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Elevator inspection tag not obtained before public use. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Backflow preventer certification lapsed. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Health department approvals for food service not obtained. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Temporary certificate of occupancy conditions violated. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Record drawings not submitted to authority within required timeframe. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Digital permit submittal referenced superseded code edition. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Certificate of compliance for firestopping not submitted to AHJ. | Legal & Regulatory | -1 | Synthetic augmentation via LLM
Accessible signage not installed per code requirements. | Legal & Regulatory | -1 | Synthetic augmentation via LLM